## Cover Page
BIP - BASELINE RISK ASSESSMENT Rev 00
FOR
BELFAST IMPLEMENTATION PROJECT
EXXARO
COMPILED BY: |  |  |  | ACCEPTED AND APPROVED BY:
TITLE | SIGNATURE |  |  | TITLE | SIGNATURE |  | DATE
Denton Marais |  |  |  | Francois Booyens
RECOMMENDED BY: |  |  |  | ACCEPTED AND APPROVED BY:
TITLE | SIGNATURE |  |  | TITLE | SIGNATURE |  | DATE
Deon van Zyl |  |  |  | Johan van der Bijl
DOCUMENT PROPERTIES
Project / Contract Number |  | Knowledge Area |  | Document Type |  | Doc Control No
ECC-000004 |  | Risk Management | RIS | Guideline | GDL | ECC-000004-2841-AOC06-SHE-RIS-0004
Project WBS
[7 empty] | Version: | 0.?

## Doc Properties (hidden)
Doc Type | Acronym | Value | Description
Action List | ACL | Architectural | ARC
Adjudication | ADJ | Blending & Load Out | BLO
Addendum | ADD | Change Management | CHA
Agenda | AGN | Chemical Engineering | CHE
Agreement | AGR | Civil Engineering | CIV
Analysis | ANA | Climate Change | CLI
Approvals | APP | Contractor Management | CMA
Assessment | ASM | Communication Management | COM
Assumption | ASS | Construction Management | CSM
Bills of Material | BOM | Diagnostics | DIA
Bills of Quantity | BOQ | Draughting | DRW
Budget | BUD | Electrical Engineering | ELE
Calculations | CAL | Energy Efficiency | ENE
Corrective Action Request | CAR | Engineering Management | ENG
Certificate | CER | Environmental Management | ENV
Checklist | CHL | Eskom | ESK
Charter | CHR | Facilities Management | FAC
Change Investigation Request | CIR | Finance Management | FIN
Contractors Management Worksheet | CMW | General | GEN
Concession | CON | Geotechnical and Rock Engineering | GEO
Code of Practice | COP | Health and Hygiene | HEA
Costs (Cash flow / Cash flow forecast) | COS | Human Resource Management | HRM
Credit Note | CRN | Information Management | ICT
Change Request | CRQ | Infrastructure Management | IFR
Contract | CTR | Industrial Engineering | IND
Data Book / Sheet / File | DAT | Instrumentation Engineering | INS
Design Change Notice/Change Notice | DCN | Laboratory Services | LAB
Daily Diaries | DDR | Legal Services | LEG
Deviation | DEV | Land Management | LMA
Decision Log | DLG | Logistics | LOG
General Documentation | DOC | Maintenance Management | MAI
Engineering Design Criteria (Excl. Process) | EDC | Marketing Management | MAR
DVD and CD (Electronic Media) | ELC | Minerals and Asset Management | MAS
E-Mail | EML | Mechanical Engineering | MEC
Enquiry | ENQ | Mineralogy | MGY
Estimate | EST | Mining | MIN
Early Warning Notice | EWN | Mobile Equipment | MOB
External Document | EXT | Mineral Resource Development | MRD
Facsimile | FAX | Operations | OPE
Field Engineering Enquiry | FEQ | Physical Asset Management | PAM
Financial Model | FMD | Process Engineering | PEN
Form | FRM | Piping | PIP
Framework | FWK | Project Management | PMG
General Conditions of Contract | GCC | Pyro metallurgy | PYR
Guideline | GDL | Quality Management | QUA
Index | IND | Rail | RAI
Instructions (e.g. Site Ins, Work Ins etc.) | INS | Research and Development | RAD
Invoice | INV | Risk Management | RIS
Letter | LET | Supply Chain Management | SCM
License | LIC | Safety | SHE
List | LIS | Structural Engineering | STE
Mandate | MAD | Surveying | SUR
Manual | MAN | Ventilation | VEN
Map | MAP | Waste Handling | WSH
Matrix | MAT
Memorandum | MEM
Modification | MOD
Minutes of Meeting | MOM
Mini Task Observation | MTO
Non-conformance Report | NCR
Note/Notices/Note of record | NOT
Order | ORD
Organogram | ORG
Overtime Request | ORQ
Project Change Approval | PCA
Project Change Notice | PCN
Process Design Basis | PDB
Process Design Criteria | PDC
Project Directive | PDT
Project Execution Method Statement | PEM
Project Execution Plan | PEP
Permit | PER
Philosophy | PHI
Photo | PHO
Plan | PLN
Punch List Request | PLR
Punch List | PLT
Policy | POL
Proposal | PPL
Procedure/Process | PRO
Profile | PRF
Programme | PRG
Presentation | PRS
Quality Control Plan | QCP
Quotation | QUO
Record | REC
Register (Risk, Change, Document, etc.) | REG
Request for Issue of Enquiry | RFE
Request for Information | RFI
Request for Proposal | RFP
Request for Quotation | RFQ
Result Sheet | RSH
Record of Decision | ROD
Report | RPT
Requirement | RQM
Sample Information | SAM
Special Conditions of Contract | SCC
Schedule | SCH
Site Directive | SDR
Service Level Agreement | SLA
Standard Operating Procedure | SOP
Scope of Work | SOW
Specification | SPC
Standard | STD
Strategy | STR
Summary | SUM
Template | TEM
Tender | TND
Training Material | TRA
Transmittal | TRM
Video | VID
Work Breakdown Structure | WBS
3D Model Views | MDL

## WBC
INSTRUCTIONS: | [7 empty] | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
Open Master Workbook | [8 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
First: select Excel Workbook to be used. | [7 empty] | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
Second: select Module1.bas
Click button to start:
If you click save and the message "The following features cannot be saved in macro-free workbooks:" click YES
CONTROL SHEET FOR VARIABLES (If any of the values below are different, call Len)
Risk Matrix Column Start: | A | 1
Risk Matrix Column End: | H | 8
Risk Matrix Row Start: | 10
Risk Matrix Row End: | 14
Risk Matrix Name: | RiskMatrix
Starting Row: | 4
Ending Row: | 131
Scoring on Risk rating Column: | AA | 27
Scoring on Risk rating Name: | RawRiskClm
Scoring on Risk rating Formula:
Risk Reduction Rating Column: | AF | 32
Risk Reduction Rating Name: | RawReductClm
Risk Reduction Rating Formula:
Risk Control Measure Rating Column: | AG | 33
Risk Control Measure Rating Formula:
Likelihood |  | (Consider near hits as well as actual events) | Risk Rating
5 | (Almost Certain) | The unwanted event has occurred frequently; occurs in order of one or more times per year & is likely to reoccur within 1 year | 11 (M) | 16 (H) | 20 (H) | 23 (Ex) | 25 (Ex)
4 | (Likely) | The unwanted event has occurred infrequently; occurs in order of less than once per year & is likely to reoccur within 5 years | 7 (M) | 12 (M) | 17 (H) | 21 (Ex) | 24 (Ex)
3 | (Possible) | The unwanted event has happened in the business at some time; or could happen within 10 years | 4 (L) | 8 (M) | 13 (H) | 18 (H) | 22 (Ex)
2 | (Unlikely) | The unwanted event has happened in the business at some time; or could happen within 20 years | 2 (L) | 5 (L) | 9 (M) | 14 (H) | 19 (H)
1 | (Rare) | The unwanted event has never been known to occur in the business; or it is highly unlikely that it will occur within 20 years | 1 (L) | 3 (L) | 6 (M) | 10 (M) | 15 (H)
(Ex) – Extreme | 21 | RiskEX
(H) – High | 13 | RiskH
(M) – Medium | 6 | RiskM
(L) – Low | 1 | RiskL
Process Excel Workbook

## Scoring on Risk rating
EXXARO SHEC Risk Matrix by Functions |  |  | Hazard Effect / Consequence Where an event has more than one “Loss Type; choose the ‘Consequence’ with the highest rating)
Impact |  |  | 1 Negligible | 2 Moderate | 3 High | 4 Major | 5 Extreme
Harm to People (S ) |  |  | First aid case / | Medical treatment case | Lost time injury / Loss of shift or hospitalisation however with reversible loss of quality of life | Lost time injury / Irreversible Loss of quality of life | Single and/or Multiple fatalities
Health (H) |  |  | Medical monitoring variance [where deviations are identified through medical screening] | Temporary accommodate [where an employee cannot resume their normal or similar work duties for less than 4 days] | Temporary disability / Lost Time Illness [where an employee cannot resume their normal of similar work duties for 4 or more days] | Permanent disability resulting in irreversible loss of quality of life | fatality / Multiple permanent disability [where a fatality occurred directly linked to an occupational disease or a permanent change in occupation or work area]
Hygiene (HY) |  |  | Exposure ≥ 10% of OEL | Exposure between 10% and 50% of OEL | Exposure between 50% and 100% of OEL | Exposure exceeding OEL | Acute exposure ≥ double the OEL
Environmental Impact (E) |  |  | Minimal environmental harm L1 incident | Moderate environmental effect / short term reversible ecological disturbance – L2 incident Remediable short term within LOM | Significant reportable environmental harm with reversible ecological damage L2 incident Remediable within LOM | Major environmental harm with long term irreversible ecological damage L2 incident Remediable post LOM (Life of Mine) Minor adverse local/public/ media attention and complaints. | Extreme environmental harm Irreversible ecological damage L3 incident Serious national public media outcry
Business Interruption / Material Damage & Other Consequential Losses |  |  | Negligible or minor or superficial damage / business interruption to facility resulting in production losses of less than 1 week. | Moderate damage / business interruption to facility resulting in production losses for a period of 1 to 2 weeks at. | Major damage/ business interruption to facility resulting in production losses for a period of 2 to 3 weeks | Future operations significantly affected by production losses for a period of 3 to 4 weeks | Total loss of production / Future operations untenable for a period of more than a month.
Impact on Reputation / Social / Community (C) |  |  | Minor adverse attention and complaints from authorities, affected and interested parties | Adverse attention and complaints from authorities, affected and interested parties (district level) | Significant adverse attention and complaints from authorities, affected and interested parties (district & regional level) | Major adverse attention and complaints from authorities, affected and interested parties that can lead to revoking of mining right and/or negative JSE/SRI rating (National level) | Extreme adverse attention and complaints from authorities, affected and interested parties that lead to revoking of mining right and negative JSE/SRI rating
Likelihood |  | (Consider near hits as well as actual events) | Risk Rating
5 | (Almost Certain) | The unwanted event has occurred frequently; occurs in order of one or more times per year & is likely to reoccur within 1 year | 11 (M) | 16 (H) | 20 (H) | 23 (Ex) | 25 (Ex)
4 | (Likely) | The unwanted event has occurred infrequently; occurs in order of less than once per year & is likely to reoccur within 5 years | 7 (M) | 12 (M) | 17 (H) | 21 (Ex) | 24 (Ex)
3 | (Possible) | The unwanted event has happened in the business at some time; or could happen within 10 years | 4 (L) | 8 (M) | 13 (H) | 18 (H) | 22 (Ex)
2 | (Unlikely) | The unwanted event has happened in the business at some time; or could happen within 20 years | 2 (L) | 5 (L) | 9 (M) | 14 (H) | 19 (H)
1 | (Rare) | The unwanted event has never been known to occur in the business; or it is highly unlikely that it will occur within 20 years | 1 (L) | 3 (L) | 6 (M) | 10 (M) | 15 (H)
Risk Rating |  | Risk Level | Guidelines for Risk Matrix
21 to 25 |  | (Ex) – Extreme | Eliminate, avoid, implement specific action plans/procedures to manage & monitor
13 to 20 |  | (H) – High | Proactively manage
6 to 12 |  | (M) – Medium | Actively manage
1 t0 5 |  | (L) – Low | Monitor & manage as appropriate

## All Departments
BIP - Belfast Implimentation Project
Phases:
Enabling Works
Construction Phase
Commissioning Phase
Bulk Earth Works
Electrical
High Voltage Reticulation
Electrical Substations
Weighbridges
Transformers
Low Voltage Reticulation
Generators
Siding-Electrical
Electrical Equipment
Engineering Workshop

## Natural & Environment
HS No | Category / Issue | Geographical Area | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[25 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[5 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
Any
1 | Natural | BIP - Project | Over-exposure to the sun | Any / All outdoor activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultraviolet light / radiation | Outcome: Health risk, body harm Consequences: possible - Skin damage, cancer, medical expenses | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 9.75 | 25 |  |  |  | x | x
2 | Natural | BIP - Project | Working outdoor and/or at heights in the presence of lightning | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: lightning Exposure: Struck by | Outcome: Severe body harm / burn Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Lightning SOP 2. Early detection device | 1. BIP-SOP-SHE.006 |  | 7.7 | 65 |  |  | x | x
3 | Natural | BIP - Project | Working in dusty conditions | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Dust Exposure: Inhalation of dust / Nuisance / Poor visibility | Outcome: Respiratory infections / irritations Consequences: possible - Serious illness | x | x |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 9.2 & 11.6 & Mandatory COP | 1. COP for Airborne Pollutants 2. Dust suppression SOP 3. Hygiene monitoring 4. PPE | 1. BIP-COP-001 |  | 9.75 | 25 |  |  |  | x | x
4 | Natural | BIP - Project | Working in the veldt | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Spiders and insects Exposure: Been bitten by | Outcome: Poison of the human body Consequences: possible - fatality / Serious injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Risk assessment for veld work 2. Awareness 3. Buddy System 4. PPE 5. On-site paramedics |  |  | 12.75 | 25 |  |  |  | x | x
5 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Extreme weather conditions Exposure: Extreme heat or cold | Outcome: Health risk Consequences: possible - Hypertension / freeze | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12 | 25 |  |  |  | x | x | Made Change - DvZ
6 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Extreme weather conditions Exposure: Hail storms | Outcome: Severe body harm / burn Consequences: possible - fatality / Serious injury | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. Awareness | 1. BIP-COP-004 |  | 13.6 | 15 |  |  |  | x
7 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Snakes Exposure: Snake bites | Outcome: Poison of the human body Consequences: possible - fatality / Serious injury | x | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Risk assessment for veld work 2. Awareness 3. Buddy System 4. PPE 5. On-site paramedics |  |  | 12.75 | 25 |  |  |  | x | x
8 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Bees Exposure: Bee stings | Outcome: Poison of the human body Consequences: possible - fatality / Serious injury | x | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Risk assessment for veld work 2. Awareness 3. Buddy System 4. On-site paramedics |  |  | 12.75 | 25 |  |  |  | x | x
9 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Drinking water Exposure: No drinking water | Outcome: Severe body harm / Heat exhaustion Consequences: possible - fatality / dehydration | x | x |  |  |  |  | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 22 Construction Regulations | 1. BIP SHE and Security Management Plan Paragraph 8.2 2. COP for Thermal stress 3. Site Inspections | 1. BIP-MPL-SHE.001 2. BIP-COP-004 |  | 17.85 | 15 |  |  |  | x
10 | Natural | BIP - Project | Exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Extreme weather conditions Exposure: Mist / Fog | Outcome: Severe body harm / collisions / accidents Consequences: possible - fatality / serious injury | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. Awareness | 1. BIP-COP-004 |  | 13.6 | 15 |  |  |  | x
11 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Extreme weather conditions Exposure: Wind | Outcome: accidents / fall risks Consequences: possible - fatality / serious injury | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. Inclement weather SOP 2. Weather station 3. Crane on-board monitoring |  |  | 5.6 | 65 |  |  | x | x
12 | Natural | BIP - Project | N/A | All outdoor activities | x |  | Any employee | Source: Extreme weather conditions Exposure: Extreme heat or cold
13 | Natural | BIP - Project | Unprotected / no protection / exposure | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Source: Rain storms Exposure: Slippery surfaces and Floods | Outcome :Slip and fall Consequences: possible - Personal Injury | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Emergency COP 2. Risk Assessments 3. Awareness Training | 1. BIP-COP-010 |  | 13.6 | 15 |  |  |  | x

## General and or Other
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | General / Other | BIP - Project | Operation of vehicles, power tools, Scaffolding | Operation / use | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Exposure: Fatigue | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act - Mandatory COP | 1. COP for fatigue 2. Awareness Training | 1. BIP-COP-007 |  | 18.7 | 15 |  |  |  | x
2 | General / Other | BIP - Project | Operation of vehicles, power tools | Operation / use | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Exposure: Judgement error | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competent and Trained employees and supervisors 2. Risk assessments 3.Awareness Training 4. Visible Felt Leadership (VFL) 5.Planned Task Observation (PTO) |  |  | 18.7 | 15 |  |  |  | x
3 | General / Other | BIP - Project | Operation of vehicles, power tools, Erecting Scaffolding | Operation / use | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Exposure: Incompetency | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Pre-screened employees 2. Competency/Training certificates 3. Risk assessments 4. Awareness Training 5. PTO's 6. VFL 7. Contractor Management SOP | 7. BIP-SOP-SHE.007 |  | 18.7 | 15 |  |  |  | x
4 | Employee working alone - General / Other | BIP - Project | None | Any work related tasks - During ordinary working hours | Work | x | x | Employee - (Male / Female) | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Possible - Physical / sexual assault, serious personal injuries that may escalate to a signal fatality. | x | [6 empty] | x |  |  | x |  |  | 22 | DMR Instruction | 1. Emergency COP 2. Buddy system 3. Risk assessment 4. Communication system | 1. BIP-COP-010 |  | 18.7 | 15 |  |  |  | x
5 | General / Other | BIP - Project | Any | Not following Safe work procedures | Work | x |  | Employees, Artisans, Supervisors, Management. | Exposure: At risk behaviour | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. PTO's 5. VFL 6. Disciplinary code |  |  | 18.7 | 15 |  |  |  | x

## Emergencies
HS No | Category / Issue | Geographical Area | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[23 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
|  |  | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Structural collapse / failure | Possible - Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident. That may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Risk assessments 2. Method statements 3. Inspections 4. Emergency COP 5. On-site paramedics 6. Designs risk based 7. PPE | 4. BIP-COP-010 |  | 18 | 25 |  |  |  | x | x
2 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Accident to a person/s | Possible - Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident. That may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Risk assessments 2. Method statements 3. Inspections 4. Emergency COP 5. On-site paramedics 6. PPE | 4. BIP-COP-010 |  | 18 | 25 |  |  |  | x | x
3 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Fire | Possible - Incident leading to personal injuries. Medical treatment for burns that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  |  |  | x |  | 24 | OHS Act, ERW 9 | 1. COP for firefighting and prevention 2. Emergency COP 3. Firefighting equipment 4. Fire teams 5. PPE 6. Housekeeping | 1. BIP-COP-011 2. BIP-COP-010 |  | 18 | 25 |  |  |  | x | x
4 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Explosions | Possible - Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, ER 14 | 1. COP for firefighting and prevention 2. Emergency COP 3. Firefighting equipment 4. Fire teams 5. PPE 6. Housekeeping | 1. BIP-COP-011 2. BIP-COP-010 |  | 16.5 | 25 |  |  |  | x | x
5 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Flooding (from rain / dam failure) | Possible - Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x
6 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Fall arresting incident rescue | Possible - Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x
7 | Emergency | BIP - Project |  | x | Employees, Supervisors, Management. | Exposure: Labour unrest - turning violent | Possible - Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  |  | x |  |  | 22 |  |  |  |  | 16.5 | 25 |  |  |  | x | x

## Enabling and Bulk Earth Works
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | BIP - Project | Vehicles - TMM's | Operating vehicles - TMM's | Walking and/or Standing | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 6 | 75 |  |  | x | x | x
2 | Geographical | BIP - Project | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 5.5 | 75 |  |  | x | x | x
3 | Geographical | BIP - Project | None | Walking | Walking | x |  | Employees, Supervisors, Management. | Source: Surface, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 9.75 | 25 |  |  |  | x | x
4 | Geographical | BIP - Project | None | Over-exposure to the sun | Any outdoor activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultraviolet light / radiation | Outcome: Skin infection Consequences : possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act - Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12.75 | 25 |  |  |  | x | x
5 | Geographical | BIP - Project | Machinery | Neighbouring processes | Any neighbouring activity | x |  | Employees, Supervisors, Management. | Source: Running machines (mixers / conveyors / generators / compressors and more) Exposure: Excessive noise | Outcome: Hearing loss Consequences : possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | BIP - Project | Scaffolding, man cage, platform | Working in a fall risk | Any working at heights activity and/or fall risk activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. Exxaro Zero Tolerance Safety Rules (EZTSR) 2. I Care Fatal Risk Controls (ICFRC) 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | BIP - Project | A variety of equipment / material / substances | Overhead lifting / working activities | Overhead activities | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
2 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling into trenches at weighbridge Exposure: Uncovered excavation/ trench | Outcome :Twisted/ fracture body parts Consequences: possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.2 CR 13 | 1. Barricading SOP 2. Excavations SOP 3. Excavation permit 4. Signage 5. Physical Barricade | 1. BIP-SOP-SHE.008 2. BIP-SOP-SHE.011 |  | 4.55 | 65 |  |  | x | x
3 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: working on live currents Exposure: Heat | Outcome :Electrocution Consequences: possible - Burn wounds | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. SOP for lock-out 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 6 | 75 |  |  | x | x | x
4 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Slip/trip and fall uneven terrain/cross-overs, walkways/ stairs Exposure: Obstructed objects | Outcome :Twisted/ fracture body parts Consequences: possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
5 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Lightning striking high masts, vehicles etc. Exposure: Heat | Outcome :damage equipment, electrical shock Consequences: possible - Serious injuries/Fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Lightning SOP 2. Risk Assessments & Mini-HIRA 3. Earthing standard 4. Early detection systems 5. Awareness | 1. BIP-SOP-SHE.006 |  | 7.7 | 65 |  |  | x | x
6 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Caught between two surfaces when using hand tools - loosening or fastening fasteners Exposure: Confined working space | Outcome :Body harm Consequences: possible - Injury/hand | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency/Training-employee/artisan 2. Risk Assessments 3. Awareness Training 4. VFL 5. PTO 6. PPE 7. Trained and competent supervisors |  |  | 9.75 | 25 |  |  |  | x | x
7 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Caught by nip point Exposure: Confined space | Outcome :Body harm Consequences: possible - Injury/hand | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency/Training-employee/artisan 2. Risk Assessments 3. Awareness Training 4. VFL 5. PTO 6. PPE 7. Trained and competent supervisors |  |  | 9.75 | 25 |  |  |  | x | x
8 | Functional | BIP - Project | Lights | Fitting light bulb | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Contact with broken glass Exposure: Sharp edges | Outcome :Finger cuts Consequences: possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency/Training-employee/artisan 2. Risk Assessments 3. Awareness Training 4. VFL 5. PTO 6. PPE 7. Trained and competent supervisors |  |  | 9.75 | 25 |  |  |  | x | x
9 | Functional | BIP - Project | Ladder | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Contractor Fall protection/Fall arrest plan 4. Ladder inspections 5. VFL 6. PTO 7. PPE 8. Buddy system |  |  | 3.25 | 75 |  |  | x | x | x
10 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling from elevated surfaces Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: possible - fatality/injury | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, GSR 6 & CR 9 | 1. EZTSR 2. ICFRC 3. Contractor Fall protection/Fall arrest plan 4. VFL 5. PTO 6. PPE |  |  | 13.5 | 25 |  |  |  | x | x
11 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Caught in/between moving parts Exposure: Moving parts | Outcome :Finger cuts Consequences: possible - Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 20.4 / 20.5 | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. Guards 5. Guarding standard 6. PPE |  |  | 4.25 | 75 |  |  | x | x | x
12 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: rain Exposure: Slippery surfaces | Outcome :Slip and fall Consequences: possible - Personal Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. Inclement weather SOP |  |  | 11.05 | 15 |  |  |  | x
13 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Unsafe acts Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Lock-out SOP 2. Guarding standard 3. COP for Conveyors 4. ICFRC 5. EZTSR 6. Lock-out devices 7. PPE | 1. BIP-SOP-ENG.003 2. VVV 3. BIP-COP-012 |  | 6 | 75 |  |  | x | x | x
14 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Wearing Incorrect or damaged PPE Exposure: Sharp edges | Outcome :Finger cuts Consequences: possible - Injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | None | 1. PPE SOP 2. COP for PPE for WIM 3. Risk Assessments 4. Inspections | 1. BIP-SOP-SHE.005 2. BIP-COP-006 |  | 15.75 | 25 |  |  |  | x | x
15 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Working under unsafe conditions – No HIRA done Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: possible - Personal Injury/fatality | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 20.4 / 20.5 / 21.6.1 | 1. ICFRC 2. EZTSR 3. Mini-HIRA 4. Disciplinary code |  |  | 11.05 | 15 |  |  |  | x
16 | Functional | BIP - Project | Hand tools | Lock out procedure | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Accessing without locking out / incorrect / improper lock out. Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Lock-out SOP 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 6 | 75 |  |  | x | x | x
17 | Functional | BIP - Project | Hand tools | Lock out procedure | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Accidental/inadvertent start up Exposure: Electricity/ moving parts | Outcome :Body harm Consequences: possible - fatality/injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3 | 1. Lock-out SOP 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 6 | 75 |  |  | x | x | x
18 | Functional | BIP - Project | Computers | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Trip and fall over cables Exposure: Obstructed objects | Outcome :Body harm Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Risk Assessment & Mini-HIRA 2. Cable routing/trunking |  |  | 4.55 | 65 |  |  | x | x
19 | Functional | BIP - Project | Light bulb | Replacing bulbs | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Contact with broken glass Exposure: Mercury | Outcome :Finger cuts/poison Consequences: possible - Injury/ health risk | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. PPE SOP 2. COP for PPE for WIM 3. Risk Assessments & Mini-HIRA 4. Disposal of fluorescent globes SOP | 1. BIP-SOP-SHE.005 2. BIP-COP-006 |  | 9.75 | 25 |  |  |  | x | x
20 | Functional | BIP - Project | Ladder | Replacing bulbs | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Contractor Fall protection/Fall arrest plan 4. VFL 5. PTO 6. PPE |  |  | 9.75 | 25 |  |  |  | x | x
21 | Functional | BIP - Project | Hand tools | Replacing plugs/switches | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Contact with electricity Exposure: Electricity | Outcome :electrical shock Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.6.1 | 1. Lock-out SOP 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 3.25 | 75 |  |  | x | x | x
1 | Equipment/Material/ Substances | BIP - Project | Hand tools (screw driver / wrench / hammer / pliers) | Using / operating / walking with / | Installations, services, maintenance, ad hoc | x |  | Authorised Artisan & Assistant - Employee | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: possible - Personal injury/fatality | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 12 | 25 |  |  |  | x | x
2 | Equipment/Material/ Substances | BIP - Project | Testing Apparatus | Using / operating / | Installations, services, maintenance, ad hoc | x |  | Authorised Artisan & Assistant - Employee | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Operational standard 2. Monthly Checklist 3. Calibration certificate (as per OEM specs) 4. PPE |  |  | 16.5 | 25 |  |  |  | x | x

## Traffic Management
HS Nr | Category | Geographical Area | Equipment / Material / Substances | Activities | Activity Type |  | Occupation | Process / Task | Hazard | Risk | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[5 empty] | Routine | Non Routine |  |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity on National Roads | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | License, Registration, Authorisation | Source: Vehicle / Driver / Operator Registration and Licensing Exposure: Expired Registration or License | Outcome: Traffic Fine / Vehicle Unroadworthy / Stop Use / Impounded Consequences: Financial Fine / Legal Liability | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act, Sec 4, 12; MCOP - TMM
2 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Vehicle Maintenance - (Roadworthiness; services; functioning of lights/brakes; tires) | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Driving / Operating Properly Maintained Vehicle / Equipment | Source: Unroadworthy vehicle; Warn tires; Warn shocks; Malfunctioning of lights/brakes. Exposure: Unable to stop timeously; Unable to give indication of actions. | Outcome: Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Imprisonment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
3 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Adherence to National Road Traffic Act - Speed Limit / Road Signs / Restrictions | Source: Driver / Operator Competency & Behaviour Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
4 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Adherence to National Road Traffic Act - Passenger Transportation (PDP, Own seat with safety belt) | Source: Driver / Operator without PDP, Vehicle insufficient for passenger transportation Exposure: Lack of PDP License and Registration / Passengers unsecure / Illegal transportation of Passengers | Outcome: Traffic Violations / Vehicle accident(passengers flung from vehicle) / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
5 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Adherence to Traffic Management Plan | Source: Driver / Operator Competency & Behaviour / Lack of Enforcement/Discipline Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
6 | Legal | BIP - Project | All Abnormal / Oversize Mobile Equipment / Transportation / Vehicles | Abnormal Load Clearance and Notification | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Abnormal Load Driving / Operating | Source: Route Not Authorised / Lack of Notification Exposure: Unable to transport | Outcome: Delay in logistics, Traffic Fine Consequences: Delay in Project, Financial Loss | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act, Sec
7 | Legal | BIP - Project | Supplier Trucks / Tankers / Explosives Transportation Vehicle | Hazardous Substances Transportation / Explosives | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Hazardous Substances Transportation / Explosives | Source: Route Not Authorised / Lack of Notification, Registration, Licensing Exposure: Unable to transport | Outcome: Delay in logistics, Traffic Fine Consequences: Delay in Project, Financial Loss | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act (93 of 1996) and Hazardous Substances Act (15 of 1973) ; Explosives Act
8 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity on National Roads | x |  | Management - Operator - Driver - Visitor - Contractor - Any other employee | Vehicle Insurance / Third party Insurance / Employee Insurance (COID) | Source: Vehicle / Driver / Operator Insurance Liability Cover Exposure: Lack of or lapsed insurance policy or Letter of Good Standing | Outcome: Personal Injury Claim / Injury on duty claim / Damaged Equipment / Vehicle Consequences: Financial Loss / Legal Liability / Civil Claim | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act, Sec , COID Act
Any
1 | Geographical | BIP - Project - Access Gates / Booms | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Driving / Operating Trackless Mobile Equipment / Vehicles / Transportation | Source: Close proximity to other vehicles, equipment, structures, pedestrians / Perform Security Access Control Exposure: Struck by, Contact with, Caught between / Unauthorised Access / Intoxicated Driver / Operator | Outcome: Vehicle Accident / Unauthorised Entry / Environmental Impact Consequences: Injuries, Single or Multiple Fatalities / Legal Liability / Theft | x | [6 empty] | x |  |  | x |  |  | 22 | National Road Traffic Act, Sec 54, 55; MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4
2 | Geographical | BIP - Project - Waiting / Parking Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Driving / Operating Trackless Mobile Equipment / Vehicles / Transportation | Source: Close proximity to other vehicles, equipment, structures, pedestrians / Failure to observe / Failure to adhere to mandatory signage and traffic rules Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
3 | Geographical | BIP - Project - Delivery / Loading Zones | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Loading of Material / Equipment / Substances | Source: Interaction between different class mobile equipment / transportation / vehicles. Loading - Heavy Loads Exposure: Right of way / Speeding / Struck by | Outcome: Vehicle Accident / Over exertion / Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability |  | x |  |  |  | x | [5 empty] | x |  | 17 | None
4 | Geographical | BIP - Project - Stockpile Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Building and removing Material from Stockpiles | Source: Interaction between mobile equipment / Failure of Stockpile. Exposure: Right of way / Speeding / Collision / Engulfed. | Outcome: Collision / Overturn Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP
5 | Geographical | BIP - Project - Laydown Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Off-Loading of Material / Equipment | Source: Interaction between Delivery Vehicles / Trucks; Heavy Materials / Equipment; Lifting Operations. Exposure: Caught Between, Under, Struck by, with / Collapse | Outcome: Collision / Contact / Engulf Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8
6 | Geographical | BIP - Project - Weighbridge | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Weighbridge Activities / Control | Source: Absence of or not having the correct delivery/invoice documentation /information in vehicle(Delivery Notes, Weighbridge Clearance, Vehicle and Driver Clearance) Exposure: Uncontrolled Access / Egress of site / Criminal Intent / Incorrect material / equipment | Outcome: Unauthorised Driver / Operator performing activities on site / Theft / Delay in material / equipment delivery Consequences: Property Damage / Production Loss / Legal Liability | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4
7 | Geographical | BIP - Project - Bus/Taxi/ Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Transportation of Passengers | Source: Congestion of vehicles / Travelling within close proximity to other vehicles, equipment, structures, pedestrians Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
8 | Geographical | BIP - Project - Handicap Parking/Access Zones | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Disabled Person Accessibility | Source: Access for persons with disability Exposure: Limited Space / Limited wheelchair access / Distance | Outcome: Site not accessible for persons with disability Consequences: Injuries / Legal Liability |  | x |  |  |  | x | [5 empty] | x |  | 17 | None
9 | Geographical | BIP - Project - Dedicated Travel Ways | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Adherence to Designated Travel Ways | Source: Congestion of vehicles / Travelling within close proximity to other vehicles, equipment, structures, pedestrians Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8
10 | Geographical | BIP - Project - Adjacent Activities | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Adjacent Work Activities - Any work related activities performed by employees or other contractors | Source: Unknown Operations/Activities; Dust, Noise Exposure: Emergency Event; Flying debris | Serious injury or possible multiple fatalities; Property damage. |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP
11 | Geographical | BIP - Project - Road Signs / Demarcation | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Road Signs / Demarcation | Source: Driver / Operator Competency & Behaviour / Lack of Signage/Enforcement/Discipline Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8
12 | Geographical | BIP - Project - Gradient/Slope of Road Surface | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling on gradient/slope road, close to edge, proximity to other vehicles, equipment, structures, pedestrians | Source: Failure to observe / Failure to adhere to mandatory signage and traffic rules / Failure to adjust Speed Exposure: Contact with, Overturn, Gravity/Momentum | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
13 | Geographical | BIP - Project - Road Surface - Tar | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling on Tar Road Surfaces | Source: Driver / Operator Competency & Behaviour / Lack of Signage/Enforcement/Discipline Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
14 | Geographical | BIP - Project - Road Surface - Gravel Construction / Site Roads | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling on Gravel/Dirt Road Surfaces | Source: Driver / Operator Competency & Behaviour / Lack of Signage/Enforcement/Discipline, Loose Gravel/Sand Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking / Loss of Control / Dust | Outcome: Traffic Violations / Vehicle accident / Overturning Vehicle / Collision Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
15 | Geographical | BIP - Project - Road Surface - Haul Roads | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling on Haul roads | Source: Driver / Operator Competency & Behaviour / Oversized Vehicles; Heavy Loads, Loose Gravel/Sand Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking / Loss of Control / Dust | Outcome: Traffic Violations / Vehicle accident / Overturning Vehicle / Collision Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
16 | Geographical | BIP - Project - Width of Road Surface | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling on Narrow Roads | Source: Congestion of vehicles / Travelling within close proximity to other vehicles, equipment, structures, pedestrians Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
17 | Geographical | BIP - Project - Road Surface Condition | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Potholes / Uneven / Loose Surface | Source: Potholes / uneven surfaces / Loose gravel/sand Exposure: Driving into a pothole / Uneven Surfaces / Slippery Surface | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
18 | Geographical | BIP - Project - Overhead Power Lines | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling Under / Close Proximity to Overhead Power Lines | Source: Unauthorised Access; Exceeding the high restriction; Overhead Electrical Lines Exposure: Incompetency; Electricity; Contact with | Outcome: Contact with Electrical Line / Electrocution Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
19 | Geographical | River Crossing / Bridges | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Travelling Through/Over River Crossings/Bridges | Source: Flooded river / stream / mudslide / Uprooted trees Exposure: Trapped in, Caught in, Stuck, Struck by | Outcome : Blocked roads / Vehicle Accident / Drowning Consequences: Loss of Production / Property Damage / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
20 | Geographical | Wild / Domestic Animals | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Attack by Wild / Domestic Animal | Source: Free roaming Wildlife / Domestic Animals Exposure: Bite / Scratch / Contact with | Outcome: Emergency event / Poisoned / Allergic reaction / Attack on Vehicle Consequences: Personal Injury / Fatality / Property Damage | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
21 | Geographical | Blasting Activities | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Blasting Activities close to Roads | Source: Explosions / Flying Debris / Falling objects Exposure: Struck by / Contact with | Outcome: Loss of control of Vehicle / Obscured Vision Consequences: Property Damage; Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident that may escalate to permanent disability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
22 | Geographical | Unauthorised Access - Pedestrians / Vehicles | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Security Access Control | Source: Lack of Access Control / Not adhering to traffic management plan Exposure: Un-Authorised Access; Unlicensed Operators / Drivers; Speeding; Un-Authorised Pedestrians on site | Outcome: Unauthorised Driver / Operator performing activities on site / Pedestrians on site Consequences: Environmental Financial Fine / Production Loss / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
23 | Geographical | Ramps / Platforms | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Driving on Ramps / Platforms | Source: Failure to observe / Failure to adhere to mandatory signage and traffic rules / Failure to adjust Speed Exposure: Contact with, Overturn, Gravity/Momentum | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
24 | Geographical | High Walls / Slopes / Embankments | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Driving / Operating close to High Wall | Source: Unauthorised Access; Close proximity of High Wall; High Wall Collapse Exposure: Engulfed; Struck by, High Wall Wall | Outcome: Uncontrolled release of service line content / Electrocution / Suffocation Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
25 | Geographical | Brake Test Ramp | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Perform Brake Ramp Tests | Source: Failure to observe / Failure to adhere to mandatory signage and Brake Test Ramp Procedure / Failure to adjust Speed or apply Brakes Exposure: Contact with, Overturn, Run-away Vehicle due to Gravity/Momentum | Outcome: Failure of Brakes / Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
26 | Geographical | Road Intersections | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Crossing Intersections / Slipways / T-Junctions | Source: Failure to observe / Failure to adhere to mandatory signage and traffic rules / Failure to adjust Speed/Stop Exposure: Contact with, Speeding Vehicles | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Property Damage / Legal Liability / Single or Multiple Fatalities | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
27 | Geographical | BIP - Project - Remote Off-Road Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Operator - Driver - Passenger - Pedestrian - Visitor - Contractor - Any other employee | Driving in Remote Areas / Any isolated work related tasks - During ordinary or after working hours | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Physical / sexual assault, serious personal injuries that may escalate to a single fatality. | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
Any
1 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Sun Direction related to Travel Direction | Source: Sun Exposure: Blinding of Vision | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
2 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Rain Causing Wet Slippery Road Surface | Source: Rain - Slippery road conditions Exposure: Loss of Control / Spinning / Sliding | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
3 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Poor / Obscured Vision due to Heavy Mist / Rain | Source: Mist / Rain - Exposure: Obscured Vision - Loss of Control / Incorrect Steering Direction | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
4 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Poor / Obscured Vision due to Dust | Source: Heavy Dust - Lack of Dust Suppression Exposure: Obscured Vision - Loss of Control / Incorrect Steering Direction | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
5 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Strong Wind Gusts | Source: Strong Winds Exposure: Loss of Control / Incorrect Steering Direction | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
6 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Night Time Driving / Operating Related Activity | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Darkness / Poor Vision | Source: Night Operations / Activities Exposure: Poor Vision - Loss of Control | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec
7 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Embark / Dis-embark All Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Sun Exposure: Ultra violet radiation | Outcome: Health risk, body harm Consequences: Skin damage, cancer, medical expenses |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | None
8 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Lightning Exposure: Struck by | Outcome: Severe body harm / burn Consequences: fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | None
9 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Dust Exposure: Inhalation of dust | Outcome: Respiratory infections / irritations Consequences: Serious illness |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 9.2 & 11.6 & Mandatory COP
10 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Spiders and insects Exposure: Been bitten by | Outcome: Poison of the human body Consequences: fatality / Serious injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None
11 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Extreme weather conditions Exposure: Extreme heat or cold | Outcome: Health risk Consequences: Hypertension / freeze | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP
12 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Extreme weather conditions Exposure: Hail storms | Outcome: Severe body harm / burn Consequences: fatality / Serious injury | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP
13 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Snakes Exposure: Snake bites | Outcome: Poison of the human body Consequences: fatality / Serious injury | x | x |  |  |  | x | [5 empty] | x |  | 17 | None
14 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Bees Exposure: Bee stings | Outcome: Poison of the human body Consequences: fatality / Serious injury | x | x |  |  |  | x | [5 empty] | x |  | 17 | None
15 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Drinking water Exposure: No drinking water | Outcome: Severe body harm / Heat exhaustion Consequences: fatality / dehydration | x | x |  |  |  |  | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 22
16 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Extreme weather conditions Exposure: Mist / Fog | Outcome: Severe body harm / collisions / accidents Consequences: fatality / serious injury | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP
17 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Extreme weather conditions Exposure: Wind | Outcome: accidents / fall risks Consequences: fatality / serious injury | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP
18 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: Extreme rain Exposure: Falling Trees / Debreu / Rolling Rock / Mud Slide | Outcome: Obstructed roads / Accidents / Fall risks Consequences: Production Delay / Fatality / serious injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 9.2 & Mandatory COP
19 | Natural | BIP - Project | All Mobile Equipment / Transportation / Vehicles | All outdoor environments (Walking between, to an from Mobile Equipment / Transportation / Vehicles | x |  | Pedestrians - Operator - Driver - Visitor - Contractor - Any other employee | N/A | Source: rain storms Exposure: Slippery surfaces and Floods | Outcome :Slip and fall Consequences: Personal Injury | x |  |  |  | x | [7 empty] | x | 16 | None
1 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on national roads / client sites | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Licenced / Authorisation / Appointed - Driver / Operator | Source: Unsilenced / unauthorised driving; Exceeding the speed limit; Not adhering to traffic signs; Driving under the influence of alcohol or drugs. Exposure: Incompetency; Speeding; Traffic violations; Intoxicated. | Outcome: Traffic Fine / Unauthorised Driver / Operator / Suspended Operations / Vehicle Impounded Consequences: Financial Fine / Production Loss / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | National Road Traffic Act, Sec 4, 12; MCOP - TMM MHS Act, Reg. 21.2
2 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Adherence to Road Use Governance / Traffic Management Plan - Speed Control; Sobriety; Safe Operation | Source: Exceeding the speed limit; Not adhering to traffic signs; Driving under the influence of alcohol or drugs. Exposure: Speeding; Traffic violations; Collision. | Outcome: Traffic Fine / Vehicle Accident Consequences: Financial Fine / Injuries, Single or Multiple Fatalities / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | National Road Traffic Act, Sec 63, 64, 65; MHS Act, Reg. 21.2
3 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Adherence to Designated Travel Ways / Route per Classification (LDV, Bus, Taxi, Trucks, Heavy Mobile Equipment, TLB, etc.) | Source: Interaction between different class mobile equipment / transportation / vehicles. Exposure: Right of way / Speeding / Collision. | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.2
4 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Travel times | Source: Fatigue / Exceeding the speed limit / Sun direction / Traffic volume Exposure: Falling Asleep / Speeding / Traffic violations / Collision | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1
5 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Mental / Physical Health | Source: Driving when tired / Medication effects; Exposure: Falling asleep whilst driving or feeling drowsy | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
6 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Travel Routes | Source: Hi-jackers / Obstructed roads / Road conditions / Remote location Exposure: Armed hi-jacking / Armed Protesters / Potholes, Road works | Outcome : Theft / Personal Assault / Collision with/ Lack of Assistance Consequences: Property Loss / Damage to Property / Serious injuries/Fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
7 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Perform Pre-Use Inspection | Source: Non Adherence to perform Pre-use Inspection on Vehicle / TMM Exposure: Cause an accident / Loss of Control / Oils and Substances | Outcome: Vehicle breakdown due to mechanical failure or flat tyre / Damaged vehicles performing activities on site / Environmental Impact through Substance leaks/spills Consequences: Environmental Financial Fine / Production Loss / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
8 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Transportation of Passengers - Driver Competency / Authorisation / Licencing | Source: PDA (licensing of vehicle and license of driver) Exposure: Driving without the correct licensing | Outcome: Traffic Fine / Unauthorised Driver / Suspended Transportation / Vehicle Impounded Consequences: Financial Fine / Production Loss / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
9 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Transportation of Passengers - Passenger Requirements (Each passenger to be secured by own safety belt) | Source: Not wearing a set belt; Seat and Safety belt not available Exposure: Unprotected movement of persons. | Minor injuries; Cuts and lacerations that may escalate to more serious injuries and even multiple fatalities. | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
10 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Transportation of Material / Equipment / Goods | Source: Weight; Shape; Centre of gravity; Movement; Hazardous substances (radio active material). Exposure: Ergonomics; Caught under; Caught in between; Struck by; Exposure to hazardous substances (radio active material); Spills; Dropping of material/equipment. | Cuts; Lacerations; Sprains; Back injuries; Fractures; Hazardous Substance exposure. | x | x |  |  |  | x |  |  |  |  | x |  |  | 13 | None
11 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Transportation of Hazardous Substances | Source: Refuelling / Raptured of Vessel / Overflow Exposure: Oil / Hazardous Substance Leaks / Emissions / Spillages | Outcome : Soil Contamination / Air Pollution / Rehabilitation Consequences: Environmental Fine or Prosecution / Emotion Taxes / Rehabilitation Costs | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8
12 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Interaction between Pedestrians and Mobile Equipment / Transportation / Vehicles | Source: Close proximity between "man and machine" Exposure: Contact with, Struck by | Outcome : Fractures / Lacerations / Trauma Consequences: fatality/injury | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, GSR 6 & CR 9
13 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Access Control - Wayble / Delivery Note/Invoice / | Source: Absence of or not having the correct delivery/invoice documentation /information in vehicle(Delivery Notes, Weighbridge Clearance, Vehicle and Driver Clearance) Exposure: Uncontrolled Access to site / Criminal Intent / Incorrect material / equipment | Outcome: Unauthorised Driver / Operator performing activities on site / Theft / Delay in material / equipment delivery Consequences: Property Damage / Production Loss / Legal Liability | x |  |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 20.4 / 20.5
14 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Loading of tools/equipment /material; Securing tools/equipment /material in the vehicle; Securing and packing. Off loading of tools/equipment /material. | Source: Weight; Shape; Centre of gravity; Movement; Hazardous substances (radio active material). Exposure: Ergonomics; Caught under; Caught in between; Struck by; Exposure to hazardous substances (radio active material); Spills; Dropping of material/equipment. | Cuts; Lacerations; Sprains; Back injuries; Fractures; Hazardous Substance exposure. | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
15 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Use of mobile phones while driving | Source: Mobile phone; Exposure: Use of mobile phone whilst driving | Loss in focus can result in accident causing personal injuries even fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2
16 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Operating - Haul Truck / TLB / Excavator / TMM | Source: Unsilenced / unauthorised driving; Exceeding the speed limit; Not adhering to traffic signs; Driving under the influence of alcohol or drugs. Exposure: Incompetency; Speeding; Traffic violations; Intoxicated. | Source: Unsilenced / unauthorised driving; Exceeding the speed limit; Not adhering to traffic signs; Driving under the influence of alcohol or drugs. Exposure: Incompetency; Speeding; Traffic violations; Intoxicated. | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
17 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Performing Excavation Work | Source: Unauthorised Excavation; Exceeding the excavation depth/width; Not adhering to excavation permit requirements; Submerged Service Pipes/Lines; Submerged Electrical Lines; Collapse Exposure: Incompetency; Electricity; Struck by, High Wall/Trench Wall | Outcome: Uncontrolled release of service line content / Electrocution / Suffocation Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [5 empty] | x |  |  |  |  | x |  | 21 | None
18 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Security Searches / Sobriety Checks | Source: Interaction between different class mobile equipment / transportation / vehicles / drivers / passengers; Sobriety(Alcohol) Testing Exposure: Right of way / Verbal Abuse / Driver / Operator / Passenger Under influence of alcohol / drugs | Outcome: Vehicle Accident / Assault / Intoxicated Operator / Driver on site Consequences: Injuries, Single or Multiple Fatalities / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 20.4 / 20.5 / 21.6.1
19 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Security Vehicle Inspection | Source: Lack of Pre-use Inspection, Lack of Valid Driver / Operator License / Not adhering to traffic management plan Exposure: Un-Authorised Access; Unlicensed Operators / Drivers; Speeding; Traffic violations | Outcome: Unauthorised Driver / Operator performing activities on site / Environmental Impact through Substance leaks/spills Consequences: Environmental Financial Fine / Production Loss / Legal Liability | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2
20 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Performing Lifting Operations | Source: Unauthorised lifting; Exceeding the load limit; Not adhering to lifting operations requirements; Suspended load; Overhead Electrical Lines Exposure: Incompetency; Electricity; Struck by, Crush | Outcome: Uncontrolled release of suspended load / Electrocution Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3
21 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Movement of Passengers / Drivers / Operators | Source: Use of Facilities / Walking through Area Exposure: Site specific hazards / Struck by / Contact with other Vehicles | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
22 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Movement of Mobile Equipment / Transportation / Vehicles | Source: Close proximity between "man and machine" Exposure: Contact with, Struck by | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
23 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Stacking and Storage | Source: Weight; Shape; Centre of gravity; Movement; Hazardous substances (radio active material). Exposure: Ergonomics; Caught under; Caught in between; Struck by; Exposure to hazardous substances (radio active material); Spills; Dropping of material/equipment. | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
24 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Parking | Source: Vehicle not parked in designated parking area Exposure: Vehicle can roll out of control | Property damage even injury to people in the area | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8
25 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Authorised Artisan | Shutting Off / Isolation / Lock-Out | Source: Vehicle not shut off, isolated or locked out as required Exposure: Vehicle start, move, operate out of control / Unauthorised use | Property damage even injury to people in the area | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.6.1
1 | Equipment/Material/ Substances | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Vehicle Maintenance Schedule | Source: Unroadworthy vehicle; Warn tires; Warn shocks; Malfunctioning of lights/brakes. Exposure: Unable to stop timeously; Unable to give indication of actions. | Outcome :Body Harm Consequences: Personal injury/fatality | x |  |  |  | x | [7 empty] | x | 16 | None
2 | Equipment/Material/ Substances | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Emitions / Fluids / Hazardous Substances | Source: Refuelling / Raptured Pipeline / Overflow Exposure: Oil / Hazardous Substance Leaks / Emissions / Spillages | Outcome : Soil Contamination / Air Pollution / Rehabilitation Consequences: Environmental Fine or Prosecution / Emotion Taxes / Rehabilitation Costs |  |  | x |  |  |  |  | x |  |  | x |  |  | 22 | NEMA, APPA,
1 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Any | Source: Monotony of Task Exposure: Loss of focus/concentration; At Risk behaviour | Outcome : Body Harm /Failure to adhere to Consequences: Property Damage / Loss of Production / Personal injury/fatality | x |  |  |  | x | [7 empty] | x | 16 | None
2 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Any | Source: Long distant driving Exposure: Fatigue, Loss of focus/concentration; At Risk behaviour | Outcome : Body Harm /Failure to adhere to Consequences: Property Damage / Loss of Production / Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
3 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Any | Source: Vibration Exposure: Fatigue / Over Exposure | Outcome : Body Harm / Health Impact Consequences: Disability / Loss of Production |  | x | [5 empty] | x |  |  | x |  |  | 22 | None
4 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Any | Source: Restricted Space / Close proximity Exposure: Contact with / Fatigue / Over Exposure | Outcome : Body Harm / Health Impact Consequences: Disability / Loss of Production |  | x | [5 empty] | x |  |  | x |  |  | 22 | None
1 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Breakdown / Mechanical Failure | Source: Vehicle breakdown due to mechanical failure / Flat tyre / Fuel Empty Exposure: Roadside Breakdown /Cause an accident if not visible or standing to close to shoulder of road | Incident leading to personal injuries. Unclear visibility that may escalate to a serious incident. Risk of being assaulted next to road resulting in personal injuries even fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None
2 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Single Vehicle Accident | Source: Collision / By-standers / Observers / Passengers Exposure: Struck by, Against, Cut, Crush /Cause a secondary accident if not visible or standing to close to shoulder of road | Outcome : Body Harm / Assault / Theft Consequences: Single or Multiple Fatalities / Property Damage / Loss of Production | x | [6 empty] | x |  |  |  | x |  | 24 | None
3 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Emergency Vehicle Access | Source: Emergency vehicles response and access Exposure: Make way for emergency vehicles, Delay in Emergency Assistance | Obstructing emergency vehicles can cause delays for emergency teams to get to point of emergency | x | [6 empty] | x |  |  |  | x |  | 24 | None
4 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Vehicle Recovery - Overturned Vehicle | Source: Accident scene and terrain / Vehicle Overturned Exposure: Cause a secondary accident if not visible or standing to close to shoulder of road, Possible fire, Cuts, Gradient | Incident leading to personal injuries. Unclear visibility that may escalate to a serious incident. | x | [6 empty] | x |  | x |  |  |  | 19 | None
5 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Remote Location / Off Road | Source: Isolated work / Unable to reach location Exposure: Animal/Human attack, Any Emergency Event | Risk of being assaulted or attacked by an animal next to road resulting in personal injuries even fatality; Lack of Emergency Assistance | x | [5 empty] | x |  |  |  | x |  |  | 18 | None
6 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Flooding / Land Slides | Source: Flooded river / stream / mudslide / Uprooted trees Exposure: Trapped in, Caught in, Stuck, Struck by | Outcome : Blocked roads / Vehicle Accident / Drowning Consequences: Loss of Production / Property Damage / Single or Multiple Fatalities | x | [6 empty] | x |  | x |  |  |  | 19 | None
7 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Potential fires | Source: None or inadequate fire fighting equipment (Fire extinguishers) Exposure: Caught by, caught in, burns by fire / Uncontrolled fire | Serious injury or possible multiple fatalities; Property damage. | x | [6 empty] | x |  |  |  | x |  | 24 | None
8 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Potential fires | Source: Flammable liquids , electrical faults Exposure: Employees exposed to smoke. Employees may be expose to extreme heat. | Incident inhalation of smoke and asphyxiations, that may escalate to a serious ill Health | x | x |  |  |  | x | [5 empty] | x |  | 17 | None
9 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Potential fires | Source: None or inadequate fire fighting equipment (Fire extinguishers) on Vehicle Exposure: Uncontrolled Fire, fire spreading | Environmental Impact - For more detail see Environmental Impact and Aspect Register |  |  | x |  |  |  | x |  |  |  |  | x |  | 21 | None
10 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Noise, Dust Potential Gas leaks, Chemical spillage, Radiation exposure | Source: Noise, Dust, Gas, Flammable liquids , substances and chemicals Exposure: Excessive Noise, Dust Employees may be expose to gasses or fumes, radiation | Incident leading to Health Impact with possible permanent disability - Noise Induced Hearing Loss |  | x |  |  |  | x | [5 empty] | x |  | 17 | None
11 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Evacuation / Emergency Exit | Source: Emergency Exits not available or working Exposure: Trapped, lack of emergency equipment | Incident leading to personal injuries. Medical treatment for burns that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  | x |  |  |  | 19 | None
12 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Potential Spillage, overflow, rupture of Chemical or Hazardous substances or material | Source: Gas, Flammable liquids , substances and chemicals Exposure: Employees may be expose to gasses or fumes, radiation | Environmental Impact - For more detail see Environmental Impact and Aspect Register - Suspensive Instruction Environmental Regulator - DOL - DOH / Legal Liability |  |  | x |  |  |  | x |  |  |  |  | x |  | 21 | None
13 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Labour Unrests | Source: Violent unrest or protest action. Exposure: Attacked or assault by. | Physical assault, serious personal injuries that may escalate to a single fatality. | x | [5 empty] | x |  |  | x |  |  |  | 14 | None
14 | Emergency | Adjacent Work Activities - Any work related activities performed by employees or other contractors | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Site Emergency, Mobile Machinery, Vehicles, Crane movement and operations | Source: Fire, Sparks, Moving Machinery Falling objects from lifting equipment/Incorrect lifting position, nib points (tools, equipment and materials). Exposure: Falling objects, struck by, caught in between. | Serious injuries, Fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | None
15 | Emergency | Adjacent Work Activities - Any work related activities performed by employees or other contractors | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Noise, Dust, Potential Gas leaks, Chemical spillage, Radiation exposure | Source: Noise, Dust, Gas, Flammable liquids , substances and chemicals Exposure: Excessive Noise, Dust Employees may be expose to gasses or fumes, radiation | Incident leading to Health Impact with possible permanent disability - Noise Induced Hearing Loss |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | None
16 | Emergency | Adjacent Work Activities - Any work related activities performed by employees or other contractors | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Operator - Driver - Visitor - Contractor - Any other employee | Potential Spillage, overflow, rupture of Chemical or Hazardous substances or material being transported | Source: Gas, Flammable liquids , substances and chemicals Exposure: Employees may be expose to gasses or fumes, radiation | Environmental Impact - For more detail see Environmental Impact and Aspect Register - Suspensive Instruction Environmental Regulator - DOL - DOH / Legal Liability |  |  | x |  |  | x | [5 empty] | x |  | 17 | None
17 | Emergency | BIP - Project | Any | Any Related Activity |  | x | Artisan - Artisan assistant - Any other employee | Any | Exposure: Structural collapse / failure | Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident. That may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  | x |  |  |  | 19 | None
18 | Emergency | BIP - Project | Any | Any Related Activity |  | x | Artisan - Artisan assistant - Any other employee | Any | Exposure: Incident / Accident to a person/s | Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident. That may escalate to permanent disability or a single fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | None
19 | Emergency | BIP - Project | Any | Any Related Activity |  | x | Artisan - Artisan assistant - Any other employee | Any | Exposure: Fire | Incident leading to personal injuries. Medical treatment for burns that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  |  |  | x |  | 24 | OHS Act, ERW 9
20 | Emergency | BIP - Project | Any | Any Related Activity |  | x | Artisan - Artisan assistant - Any other employee | Any | Exposure: Explosions / Flying Debris | Incident leading to personal injuries. Medical treatment for bruises, cuts, lacerations, fractures that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, ER 14
1 | General / Other | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | N/A | Exposure: Fatigue | Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
2 | General / Other | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | N/A | Exposure: Judgement error | Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
3 | General / Other | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | N/A | Exposure: Incompetency | Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
4 | General / Other - Employee working alone | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | Any isolated work related tasks - During ordinary or after working hours | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Physical / sexual assault, serious personal injuries that may escalate to a single fatality. | x | [6 empty] | x |  |  | x |  |  | 22 | DMR Instruction
5 | General / Other | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Operator - Driver - Visitor - Contractor - Any other employee | N/A | Exposure: At risk behaviour | Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None

## Construction Phase
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | BIP - Project | Vehicles - TMM's | Operating vehicles - TMM's | Walking and/or Standing | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 6 | 75 |  |  | x | x | x
2 | Geographical | BIP - Project | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 5.5 | 75 |  |  | x | x | x
3 | Geographical | BIP - Project | None | Walking | Walking | x |  | Employees, Supervisors, Management. | Source: Surface, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 9.75 | 25 |  |  |  | x | x
4 | Geographical | BIP - Project | None | Over-exposure to the sun | Any outdoor activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultraviolet light / radiation | Outcome: Skin infection Consequences : possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12.75 | 25 |  |  |  | x | x
5 | Geographical | BIP - Project | Machinery | Neighbouring processes | Any neighbouring activity | x |  | Employees, Supervisors, Management. | Source: Running machines (mixers / conveyors / generators / compressors and more) Exposure: Excessive noise | Outcome: Hearing loss Consequences : possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | BIP - Project | Scaffolding, man cage, platform | Working in a fall risk | Any working at heights activity and/or fall risk activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | BIP - Project | A variety of equipment / material / substances | Overhead lifting / working activities | Overhead activities | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
2 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling into trenches at weighbridge Exposure: Uncovered excavation/ trench | Outcome :Twisted/ fracture body parts Consequences: possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.2 | 1. Barricading SOP 2. Excavations SOP 3. Excavation permit 4. Signage 5. Physical Barricade | 1. BIP-SOP-SHE.008 2. BIP-SOP-SHE.011 |  | 4.55 | 65 |  |  | x | x
3 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: working on live currents Exposure: Heat | Outcome :Electrocution Consequences: possible - Burn wounds | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. SOP for lock-out 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 6 | 75 |  |  | x | x | x
4 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Slip/trip and fall uneven terrain/cross-overs, walkways/ stairs Exposure: Obstructed objects | Outcome :Twisted/ fracture body parts Consequences: possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
5 | Functional | BIP - Project | Electricity | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Lightning striking high masts, vehicles etc. Exposure: Heat | Outcome :damage equipment, electrical shock Consequences: possible - Serious injuries/Fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Lightning SOP 2. Risk Assessments & Mini-HIRA 3. Earthing standard 4. Early detection systems 5. Awareness | 1. BIP-SOP-SHE.006 |  | 7.7 | 65 |  |  | x | x
6 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Caught between two surfaces when using hand tools - loosening or fastening fasteners Exposure: Confined working space | Outcome :Body harm Consequences: possible - Injury/hand | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency/Training-employee/artisan 2. Risk Assessments 3. Awareness Training 4. VFL 5. PTO 6. PPE 7. Trained and competent supervisors |  |  | 9.75 | 25 |  |  |  | x | x
7 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Caught by nip point Exposure: Confined space | Outcome :Body harm Consequences: possible - Injury/hand | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency/Training-employee/artisan 2. Risk Assessments 3. Awareness Training 4. VFL 5. PTO 6. PPE 7. Trained and competent supervisors |  |  | 9.75 | 25 |  |  |  | x | x
8 | Functional | BIP - Project | Lights | Fitting light bulb | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Contact with broken glass Exposure: Sharp edges | Outcome :Finger cuts Consequences: possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency/Training-employee/artisan 2. Risk Assessments 3. Awareness Training 4. VFL 5. PTO 6. PPE 7. Trained and competent supervisors |  |  | 9.75 | 25 |  |  |  | x | x
9 | Functional | BIP - Project | Ladder | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Contractor Fall protection/Fall arrest plan 4. Ladder inspections 5. VFL 6. PTO 7. PPE 8. Buddy system |  |  | 3.25 | 75 |  |  | x | x | x
10 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling from elevated surfaces Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: possible - fatality/injury | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, GSR 6 & CR 9 | 1. EZTSR 2. ICFRC 3. Contractor Fall protection/Fall arrest plan 4. VFL 5. PTO 6. PPE |  |  | 13.5 | 25 |  |  |  | x | x
11 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Caught in/between moving parts Exposure: Moving parts | Outcome :Finger cuts Consequences: possible - Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 20.4 / 20.5 | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. Guards 5. Guarding standard 6. PPE |  |  | 4.25 | 75 |  |  | x | x | x
12 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: rain Exposure: Slippery surfaces | Outcome :Slip and fall Consequences: possible - Personal Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. Inclement weather SOP |  |  | 11.05 | 15 |  |  |  | x
13 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Unsafe acts Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Lock-out SOP 2. Guarding standard 3. COP for Conveyors 4. ICFRC 5. EZTSR 6. Lock-out devices 7. PPE | 1. BIP-SOP-ENG.003 2. VVV 3. BIP-COP-012 |  | 6 | 75 |  |  | x | x | x
14 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Wearing Incorrect or damaged PPE Exposure: Sharp edges | Outcome :Finger cuts Consequences: possible - Injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | None | 1. PPE SOP 2. COP for PPE for WIM 3. Risk Assessments 4. Inspections | 1. BIP-SOP-SHE.005 2. BIP-COP-006 |  | 15.75 | 25 |  |  |  | x | x
15 | Functional | BIP - Project | Hand tools | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Working under unsafe conditions – No HIRA done Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: possible - Personal Injury/fatality | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 20.4 / 20.5 / 21.6.1 | 1. ICFRC 2. EZTSR 3. Mini-HIRA 4. Disciplinary code |  |  | 11.05 | 15 |  |  |  | x
16 | Functional | BIP - Project | Hand tools | Lock out procedure | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Accessing without locking out / incorrect / improper lock out. Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Lock-out SOP 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 6 | 75 |  |  | x | x | x
17 | Functional | BIP - Project | Hand tools | Lock out procedure | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Accidental/inadvertent start up Exposure: Electricity/ moving parts | Outcome :Body harm Consequences: possible - fatality/injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3 | 1. Lock-out SOP 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 6 | 75 |  |  | x | x | x
18 | Functional | BIP - Project | Computers | Inspection, repair, maintenance | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Trip and fall over cables Exposure: Obstructed objects | Outcome :Body harm Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Risk Assessment & Mini-HIRA 2. Cable routing/trunking |  |  | 4.55 | 65 |  |  | x | x
19 | Functional | BIP - Project | Light bulb | Replacing bulbs | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Contact with broken glass Exposure: Mercury | Outcome :Finger cuts/poison Consequences: possible - Injury/ health risk | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. PPE SOP 2. COP for PPE for WIM 3. Risk Assessments & Mini-HIRA 4. Disposal of fluorescent globes SOP | 1. BIP-SOP-SHE.005 2. BIP-COP-006 |  | 9.75 | 25 |  |  |  | x | x
20 | Functional | BIP - Project | Ladder | Replacing bulbs | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Contractor Fall protection/Fall arrest plan 4. VFL 5. PTO 6. PPE |  |  | 9.75 | 25 |  |  |  | x | x
21 | Functional | BIP - Project | Hand tools | Replacing plugs/switches | Installation/ maintenance/repairs | x |  | Authorised Artisan | Source: Contact with electricity Exposure: Electricity | Outcome :electrical shock Consequences: possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.6.1 | 1. Lock-out SOP 2. Permits 3. Personal locks 4. Risk Assessments 5. PPE | 1. BIP-SOP-ENG.003 |  | 3.25 | 75 |  |  | x | x | x
1 | Equipment/Material/ Substances | BIP - Project | Hand tools (screw driver / wrench / hammer / pliers) | Using / operating / walking with / | Installations, services, maintenance, ad hoc | x |  | Authorised Artisan & Assistant - Employee | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: possible - Personal injury/fatality | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 12 | 25 |  |  |  | x | x
2 | Equipment/Material/ Substances | BIP - Project | Testing Apparatus | Using / operating / | Installations, services, maintenance, ad hoc | x |  | Authorised Artisan & Assistant - Employee | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Operational standard 2. Monthly Checklist 3. Calibration certificate (as per OEM specs) 4. PPE |  |  | 16.5 | 25 |  |  |  | x | x

## 11kV-High Voltage
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 .Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | High Voltage/11kV Reticulation Area | Vehicles - TMM's | Operating vehicles - TMM's | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 6 | 75 |  |  | x | x | x
2 | Geographical | High Voltage/11kV Reticulation Area | Flammable liquids | Combustion | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 5.5 | 75 |  |  | x | x | x
3 | Geographical | High Voltage/11kV Reticulation Area | None | Walking | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 9.75 | 25 |  |  |  | x | x
4 | Geographical | High Voltage/11kV Reticulation Area | None | Over-exposure to the sun | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12.75 | 25 |  |  |  | x | x
5 | Geographical | High Voltage/11kV Reticulation Area | Machinery | Neighbouring processes | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | High Voltage/11kV Reticulation Area | Scaffolding, man cage, platform | Working in a fall risk | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | High Voltage/11kV Reticulation Area | A variety of equipment / material / substances | Overhead lifting / working activities | Any Related Activities | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Functional | High Voltage/11kV Reticulation Area | Electricity | Unauthorised entrance to the mine Please explain how activity and occupation talk to process or task if the latter is unauthorised access but the artisan is authorised and still it resorts under installation/inspection and maintenance | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Improper lock out Exposure: Open wires | Outcome : Electrocution Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.2 | 1. Access Control SOP 2. Contractor Management SOP 3. Controlled access 4. Trained and competent artisan 5. Locked electrical facilities | 1. BIP-SOP-RIS.001 2. BIP-SOP-SHE.007
2 | Functional | High Voltage/11kV Reticulation Area | Electricity | Inspection of HV/11kV network | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: wires/ conductors is earthed through people Exposure: Electricity | Outcome : Electrocution Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15(b)(i)(ii) | 1. Controlled access to electrical facilities 2 Trained and competent artisan 3. Locked electrical facilities 4. Lock-out CoP 5. Personal locks
3 | Functional | High Voltage/11kV Reticulation Area | Electricity | Inspection of HV/11kV network | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: damage to switchgear and cables Exposure: Electrical flashover | Outcome : Electrocution Consequences: Possible - Personal Injury / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.1 | 1. Controlled access to electrical facilities 2 Trained and competent artisan 3. Locked electrical facilities 4. Lock-out CoP 5. Personal locks
4 | Functional | High Voltage/11kV Reticulation Area | Electricity | Inspection of HV/11kV network | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: short-circuiting / flashover Exposure: Heat | Outcome : Electrical fires Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.2 | 1. Controlled access 2. Trained and competent artisan 3. Locked electrical facilities 4 Fire Prevention CoP 5. PPE
5 | Functional | High Voltage/11kV Reticulation Area | Electricity | Inspection of HV/11kV network | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Personnel close to energised electrical components. Exposure: Heat | Outcome :Electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.3 | 1. Controlled access 2. Trained and competent artisan 3. Locked electrical facilities 4. HT Switching procedure 5. Personal locks 6. PPE
6 | Functional | High Voltage/11kV Reticulation Area | Electricity | Inspection of HV/11kV network | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.1.2 | 1. Access Control SOP 2. Contractor Management SOP 3. Controlled access 4. Trained and competent artisan 5. Locked electrical facilities
7 | Functional | High Voltage/11kV Reticulation Area | Electricity | HT switching. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.1.1.2 | 1. Controlled access 2. Trained and competent artisan 3. Locked electrical facilities 4. Personal locks 5. Lock-out CoP 6. PPE
8 | Functional | High Voltage/11kV Reticulation Area | Electricity | Failure to isolate, lockout, test and tag, obtain permit. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.2 | 1. Controlled access 2. Trained and competent artisan 3. Locked electrical facilities 4. Personal locks 5. Disciplinary Code 6. Lock Out CoP
9 | Functional | High Voltage/11kV Reticulation Area | Electricity | Energised sources in contact with water. Please be more specific - what is the water source. Is it rain, water accumulation due to leaking pipe etc.? | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome : arcing /electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Controlled access 2. Trained and competent artisan 3. Locked electrical facilities 4. Hazard Identification Training 5. Design and construction principles in order to not have electrical distribution/structures in low laying areas
10 | Functional | High Voltage/11kV Reticulation Area | Electricity | Raising the load bin of a hauler under HT overhead power lines. loading under HT power lines. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing /electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.10.5 | 1. SoP - working in close proximity of overhead power lines 2. Trained and competent supervisors, artisans and operators
11 | Functional | High Voltage/11kV Reticulation Area | Electricity | Lifting operations under HT power lines. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.10.5 | 1. SoP - working in close proximity of overhead power lines 2. Trained and competent supervisors, artisans and operators
12 | Functional | High Voltage/11kV Reticulation Area | Electricity | Handling of damaged or faulty cables. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15 | 1. Isolation and lock-out CoP 2. Personal locks 3. PPE 4. Trained and competent Artisans 5. Permit system
13 | Functional | High Voltage/11kV Reticulation Area | Electricity | On or under overhead power lines. This is confusing - if you work on a powerline then work has a direct connection with the powerline. If you work under a power line the implication is that one may be working on tools or equipment not associated with the powerline | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds /fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.10.5
14 | Functional | High Voltage/11kV Reticulation Area | Electricity | Overheating or overloading causing loss of insulation. Is this an u/g cable. As far as I know we will not use insulated o/h electrical supply cables. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome : arcing /electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15 | 1. Earthing of u/g power supply cables 2. Standard on cable trench depth 3. Cable quality specification 4. CoP Isolation and lock-out 5. PPE
15 | Functional | High Voltage/11kV Reticulation Area | Electricity | Cables in contact with water. This description is vague. If the cable is energised it in all probability will be covered in a trench. The location and description of this cable in this entry needs more body | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
16 | Functional | High Voltage/11kV Reticulation Area | Electricity | Use of inadequate, inappropriate or faulty testing apparatus. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1.Project/contractor standard on equipment to be used 2. Artisan inspection and testing equipment before use 3. OEM Specification and end user guidelines 4. Supervisors conducting VFL's and PTO's on artisans 5. Trained and competent artisans
17 | Functional | High Voltage/11kV Reticulation Area | Electricity | The use of standard hook-sticks in wet conditions or where the possibility of carbon on or inside the stick exists. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Pre use inspections of equipment to be used 2. No work to be conducted in wet conditions 3. PPE
18 | Functional | High Voltage/11kV Reticulation Area | Electricity | Damaged, faulty, poorly maintained trailing cables and switch gear. This is normally associated with u/g operations and draglines - we will not be exposed to either. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.14.4 / 6
19 | Functional | High Voltage/11kV Reticulation Area | Electricity | Compromising safety systems e.g. (bridging out), | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wounds / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.1 | 1. Disciplinary Code 2. Trained and competent artisans
20 | Functional | High Voltage/11kV Reticulation Area | Electricity | Unauthorised, malicious or intentional bridging out, disconnection, overriding of fall to safe switches | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Unauthorised, malicious or intentional bridging out, disconnection, overriding of fall to safe switches arcing/electrocution Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury / burn wound s / fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.4 | 1. Disciplinary Code 2. Trained and competent artisans
21 | Functional | High Voltage/11kV Reticulation Area | Electricity | Criminal Intention | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Illegal removal of sections of electrical copper conductors. Exposure: Theft | Outcome : Violent attack / property damaged, theft. Consequences: Possible - fatality/injury/Serious financial losses | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. On-site security controls and patrols
22 | Functional | High Voltage/11kV Reticulation Area | Electricity | Earth leakage testing | Test | x |  | Authorised Artisan | Source: Personnel close to energised electrical components - Electrocution Exposure: Shock, heat | Outcome : Electrocution Consequences: Possible - fatality / injury / Serious | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.1 | 1. SoP on testing procedures 2. PPE 3. HIRA 4. Certified OEM equipment 5. Trained and competent artisans
23 | Functional | High Voltage/11kV Reticulation Area | Electricity | Changing fuses | Maintenance | x |  | Authorised Artisan | Source: Accessing without locking out / incorrect / improper lock out/ Accidental start-up Exposure: Shock, heat | Outcome : Electrocution Consequences: Possible - fatality / injury / Serious | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.2 | 1. Isolation and Lock-out CoP 2. PPE 3. Personal locks 4. Trained and competent artisans HIRA
1 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Oxy- Acetelyne Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: equipment and hoses Exposure: Caught between / caught by / struck by / trip & fall over equipment and hoses | Outcome :Body harm Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 9
2 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Oxy- Acetelyne Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: Acetylene Exposure: Highly flammable gas | Outcome :Explosion Consequences: Possible - Personal injury/fatality/ property damage | x | [5 empty] | x |  |  |  |  | x |  | 21 | OHS Act, GSR 9
3 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Pneumatic power hand tools | use / operation | use / operation | x |  | Authorised Artisan | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
4 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Hand tools (screw driver / wrench / hammer / pliers) | Installation / Maintenance / Repair | use / operation | x |  | Authorised Artisan | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
5 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Hand tools - Stanley knife | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
6 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Hand tools - Stanley knife | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
7 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Testing Apparatus | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Operational standard 2. Monthly Checklist 3. Calibration certificate (as per OEM specs) 4. PPE |  |  | 16.5 | 25 |  |  |  | x | x
8 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Power Tools (Drill/grinder etc.) | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
9 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Arc Welder | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
10 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Arc Welder | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Ultra violet radiation Exposure: Harmful radiation | Outcome :Eye/skin irritations Consequences: Possible - Cancer/ permanent damage to eyes | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
11 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | Link Stick | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Cracked/Dirty/Wet/Soiled Stick Exposure: Contact with | Outcome :Body harm Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
12 | Equipment, Material & Substances | High Voltage/11kV Reticulation Area | PPE | Installation / Maintenance / Repair | Any Related Activities | x |  | Authorised Artisan | Source: Failure to wear PPE Exposure: Chemicals, sharp edges, handling material | Outcome :Injuries to body part Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None

## Sub Stations
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Substation | Vehicles - TMM's | Operating vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Substation | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Substation | None | Walking | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Substation | None | Over-exposure to the sun | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Substation | Machinery | Neighbouring processes | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Substation | Scaffolding, man cage, platform | Working in a fall risk | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Substation | A variety of equipment / material / substances | Overhead lifting / working activities | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Functional | Substation | Electricity | Maintenance of substation One would normally associate maintenance with a running operation and not so much with a project under construction Please see entries below as well | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: No maintenance is done on Sub Station Exposure: Power failure | Outcome: Safety risk Consequences: Possible - fatality or injuries/ Property theft, damage, financial loss | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.15(b)(i)(ii)
2 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: oil in the mini sub & Transformers, whilst in operation. Exposure: High temp/ heat | Outcome: Overheating Consequences: Possible - fatality or injuries/ This description is vague. What is overheating - a person or the equipment and if it is a person is he/she trapped inside? Hazard and risk really do not talk to each other | x | [5 empty] | x |  |  |  |  | x |  | 21 | None
3 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Emergency exits - Outlet door jammed or shut Exposure: High temp/ heat | Outcome: Burn wounds Consequences: Possible - fatality or injuries/ Similar to above. If a door is shut or stuck then what? There must be something else here that warrant this entry. These areas are normally temperature controlled | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.1.3(f)
4 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Switching | x |  | Authorised Artisan | Source: Switching of High Voltage/11kV . inside the Sub station when tripping happens Exposure: High temp/ heat? An elec electrical flash will be more prone to occur if switching is done incorrectly and that may lead to burn wounds | Outcome: Burn wounds Consequences: Possible - fatality or injuries/ | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.1.1.2
5 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Falling into cable trenches at sub station Exposure: Unprotected open cable trenches | Outcome: Body harm Consequences: Possible - injuries | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.2 | 1. Sub Station design includes grating to cover trenches 2. Inspections and over inspections 3. Well lit structures 4. Safety device inoperable - Disciplinary Code
6 | Functional | Substation | Electricity | Housekeeping | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Poor housekeeping - Storing flammable substances in sub station Exposure: Heat | Outcome: Fire/explosion Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Chemical storage standard 2. Chemicals training 3. Disciplinary code 4. Hazard awareness Training 5. Mini HIRA 6. Inspections and over inspections
7 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Live 11 kV electricity in the sub station whilst person in sub station. - Electrocution Exposure: Heat | Outcome: Fire/explosion Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.15(b)(i)(ii) | 1. Standard procedure to access live working areas 2. Permit system 3. Isolation and lockout CoP 4. HIRA 5. Switching standard
8 | Functional | Substation | Multi-meter | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Use of defective testing equipment when testing on is taking place. Exposure: Electricity | Outcome: Burn wounds Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. OEM Spec testing equipment 2. Trained and competent artisans and supervisors 3. HIRA 4. VFL 5. Testing Procedure 6. PPE
9 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Damaged roof - Rain entering sub station due to holes in roof - Lead to Exposure: Slippery surface/ water contact with electricity - shock | Outcome: explosion fire/ Slip and fall Consequences: Possible - injuries /fatality/ damage to equipment | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.1.3( c ) | 1. Isolation and lockout CoP 2. Emergency CoP 3. Fail to safe equipment
10 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Electrocution when working on live currents Exposure: Heat, electricity | Outcome: explosion fire Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.2 | 1. Working on live equipment standard 2. Permit system 3. Testing procedure 4. PPE
11 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Stack and storage - Dirty oil rags and flammable liquid - Fires Exposure: Heat, electricity | Outcome: Fires Consequences: Possible - injuries /fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. Housekeeping standard 2. Chemical storage standard 3. Inspections and over inspections 4. VFL 5. Trained and competent artisans and supervisors
12 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Switching | x |  | Authorised Artisan | Source: Switching High Voltage/11kV after it tripped - High Voltage/11kV Electricity - Faulty procedures Exposure: Heat, electricity Similar to line 22 | Outcome: Electrocution Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.1.1.2
13 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Defective fire equipment -Not able to contain fire Exposure: Heat, electricity | Outcome: Electrocution/ burn wounds Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Fire fighting CoP 2. Periodic fire fighting equipment inspections 3. Fire fighting team CoP Isolation and lock-out
14 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Unauthorised entry Exposure: Heat, electricity | Outcome: Electrocution/ burn wounds Consequences: Possible - injuries /fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.2 | 1. Locked and access controlled facilities 2. Only trained and competent persons allowed in facilities 3. Disciplinary Code
15 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Struck by falling objects Exposure: Unsecure/ unstable objects from heights Would this be during the construction phase because once a sub or similar is completed nothing gets stored inside that can fall from height | Outcome: Head injuries Consequences: Possible - injuries /fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | None
16 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Slip/trip and fall Exposure: slippery and surfaces | Outcome: Twisted/fracture body limbs Consequences: Possible - injuries | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. HIRA 2. PPE 3. Hazard awareness training
17 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Attack by criminal intent Exposure: sabotage | Outcome: Attack by Consequences: Possible - fatality or injury /Damage to equipment | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Dedicated site security
18 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Fire/explosion caused by faulty wiring Exposure: Heat | Outcome: Fire/explosion Consequences: Possible - fatality or injury /Damage to equipment | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15 | 1. Fail to safe equipment 2.
19 | Functional | Substation | Electricity | Inspection, repair, cleaning and maintenance | Maintenance, repairs, services, ad hoc | x |  | Authorised Artisan | Source: Lightning Striking high masts, vehicles etc. Exposure: Heat The geographical area is sub-stations right? | Outcome: Fire/explosion/electrical shock Consequences: Possible - Serious injuries/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None
20 | Functional | Substation | Electricity | Lock out & Isolation | Lock out procedure | x |  | Authorised Artisan | Source: Accessing without locking out / incorrect / improper lock out. Exposure: Open wires | Outcome :Electrocution Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.2 | 1. CoP on isolation and lockout 2. Disciplinary Code 3. Trained and competent artisans HIRA 4. Hazard awareness training 5. PPE
21 | Functional | Substation | Electricity | Lock out & Isolation | Lock out procedure | x |  | Authorised Artisan | Source: Accidental/unauthorised start up Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Personal Injury/ fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. CoP isolation and lockout 2. Personal locks 3. Multi function lockout units 4. Disciplinary Code
53 | Engineering |  | Electricity
1 | Equipment, Material & Substances | Substation | Oxy- Acetylene Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: equipment and hoses Exposure: Caught between / caught by / struck by / trip & fall over equipment and hoses | Outcome :Body harm Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 9
2 | Equipment, Material & Substances | Substation | Oxy- Acetylene Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: Acetylene Exposure: Highly flammable gas | Outcome :Explosion Consequences: Possible - Personal injury/fatality/ property damage | x | [5 empty] | x |  |  |  |  | x |  | 21 | OHS Act, GSR 9
3 | Equipment, Material & Substances | Substation | Pneumatic power hand tools | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
4 | Equipment, Material & Substances | Substation | Hand tools (screw driver / wrench / hammer / pliers) | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
5 | Equipment, Material & Substances | Substation | Hand tools - Stanley knife | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
6 | Equipment, Material & Substances | Substation | Hand tools - Stanley knife | Installation / Maintenance / Repair | Use | x |  | Artisan - Artisan assistant | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
7 | Equipment, Material & Substances | Substation | Testing Apparatus | Installation / Maintenance / Repair | Use | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
8 | Equipment, Material & Substances | Substation | Power Tools (Drill/grinder etc.) | Installation / Maintenance / Repair | Use | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
9 | Equipment, Material & Substances | Substation | Arc Welder | Installation / Maintenance / Repair | use | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
10 | Equipment, Material & Substances | Substation | Arc Welder | Installation / Maintenance / Repair | Use | x |  | Artisan - Artisan assistant | Source: Ultra violet radiation Exposure: Harmful radiation | Outcome :Eye/skin irritations Consequences: Possible - Cancer/ permanent damage to eyes | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
11 | Equipment, Material & Substances | Substation | Link Stick | Installation / Maintenance / Repair | Use | x |  | Artisan - Artisan assistant | Source: Cracked/Dirty/Wet/Soiled Stick Exposure: Contact with | Outcome :Body harm Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
12 | Equipment, Material & Substances | Substation | PPE | Installation / Maintenance / Repair | Use | x |  | Artisan - Artisan assistant | Source: Failure to wear PPE Exposure: Chemicals, sharp edges, handling material | Outcome :Injuries to body part Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
Engineering

## Low Voltage Ret.
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Low Voltage Reticulation | Vehicles - TMM's | Operating vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Low Voltage Reticulation | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Low Voltage Reticulation | None | Walking | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Low Voltage Reticulation | None | Over-exposure to the sun | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Low Voltage Reticulation | Machinery | Neighbouring processes | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Low Voltage Reticulation | Scaffolding, man cage, platform | Working in a fall risk | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Low Voltage Reticulation | A variety of equipment / material / substances | Overhead lifting / working activities | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Functional | Low Voltage Reticulation | Electricity | Unauthorised entrance to the mine Please see 11kV note | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Improper lock out Exposure: Open wires | Outcome :Electrocution Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.2 | 1. Access Control SOP 2. Contractor Management SOP | 1. BIP-SOP-RIS.001 2. BIP-SOP-SHE.007
2 | Functional | Low Voltage Reticulation | Electricity | Inspection of Low Voltage installations | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: wires/ conductors is earthed through people Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15(b)(i)(ii) | 1. Controlled facility access. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment
3 | Functional | Low Voltage Reticulation | Electricity | Inspection of Low Voltage installations | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: damage to switchgear and cables Exposure: Electrical flashover | Outcome :Electrocution Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.1 | 1. Controlled facility access. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment
4 | Functional | Low Voltage Reticulation | Electricity | Inspection of Low Voltage installations | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: short-circuiting / flashover Exposure: Heat | Outcome :Electrical fires Consequences: Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.2 | 1. Controlled facility access. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment
5 | Functional | Low Voltage Reticulation | Electricity | Inspection of Low Voltage installations | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Personnel close to energised electrical components. Exposure: Heat | Outcome :Electrocution Consequences: Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.3 | 1. Controlled facility access e.g. panels. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment
6 | Functional | Low Voltage Reticulation | Electricity | Inspection of Low Voltage installations | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.1.1.1 | 1. Controlled facility access e.g. panels. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment
7 | Functional | Low Voltage Reticulation | Electricity | Failure to isolate, lockout, test and tag, obtain permit. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.2 | 1. Controlled facility access e.g. panels. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment 5. Disciplinary Code 6. CoP Isolation and lock-out
8 | Functional | Low Voltage Reticulation | Electricity | Maintenance/servicing/replacing | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Possible - fatality/injury damage to equipment | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.1.1.1 | 1. Controlled facility access e.g. panels. 2. Equipment earthing. 3. PPE 4. OEM Spec testing equipment 5. Disciplinary Code 6. CoP Isolation and lock-out
9 | Functional | Low Voltage Reticulation | Electricity | Handling of damaged or faulty cables/wires | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15 | 1. Cable inspection before installation 2. OEM test certificate 3. PPE
10 | Functional | Low Voltage Reticulation | Electricity | Overheating or overloading causing loss of insulation. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.15 | 1. Cable load spec 2. Trained and competent artisans 3. Supervisor inspections 4. Earthing std
11 | Functional | Low Voltage Reticulation | Electricity | Cables in contact with water. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with energised and exposed electrical wires, cables, components, panels, conductors Exposure: Heat/ Shock | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Controlled access 2. Trained and competent artisan 3. Locked electrical facilities 4. Hazard Identification Training 5. Design and construction principles in order to not have electrical distribution/structures in low laying areas
12 | Functional | Low Voltage Reticulation | Electricity | Use of inadequate, inappropriate or faulty testing apparatus. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with energised and exposed electrical wires, cables, components, panels, conductors Exposure: Heat/ Shock | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Testing Procedure 2. OEM Spec testing equipment Trained and competent Artisans 5.PPE
13 | Functional | Low Voltage Reticulation | Electricity | Damaged, faulty, poorly maintained trailing cables and switch gear. | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with energised and exposed electrical wires, cables, components, panels, conductors Exposure: Heat/ Shock | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.14.4 / 6 | Underground activity
14 | Functional | Low Voltage Reticulation | Electricity | Compromising safety systems e.g. (bridging out), | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Contact with energised and exposed electrical wires, cables, components, panels, conductors Exposure: Heat/ Shock | Outcome :arcing/electrocution Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.3.1 | 1. Disciplinary code 2. Trained and competent artisans and supervisors 3. Inspections and over inspections
15 | Functional | Low Voltage Reticulation | Electricity | Unauthorised, malicious or intentional bridging out, disconnection, overriding of fall to safe switches | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Unauthorised/Malicious actions Exposure: Theft, attack | Outcome :Body harm Consequences: Possible - Personal Injury/ burn wounds/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.4 | 1. Disciplinary code 2. Trained and competent artisans and supervisors 3. Inspections and over inspections
16 | Functional | Low Voltage Reticulation | Electricity | Criminal Intention | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Source: Illegal removal of sections of electrical copper conductors. Exposure: Theft | Outcome :Violence attack/ property damaged, stolen Consequences: Possible - fatality/injury/Serious financial losses | x | [6 empty] | x |  |  | x |  |  | 22 | None | Dedicated site security
17 | Functional | Low Voltage Reticulation | Electricity | Earth leakage testing | Test | x |  | Authorised Artisan | Source: Personnel close to energised electrical components - Electrocution Exposure: Shock, heat | Outcome :Electrocution Consequences: Possible - Possible - fatality/injury/Serious | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.1 | 1. Testing Procedure 2. OEM Spec testing equipment 3. PPE 4. Trained and competent artisans and supervisors 5. VFL
18 | Functional | Low Voltage Reticulation | Electricity | Changing fuses | Maintenance | x |  | Authorised Artisan | Source: Accessing without locking out / incorrect / improper lock out/ Accidental start-up Exposure: Shock, heat | Outcome :Electrocution Consequences: Possible - fatality/injury/Serious | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.6.2 | 1. CoP isolation and lock-out 2. Trained and competent artisans and supervisors 3. PPE 4. VFL
1 | Equipment, Material & Substances | Low Voltage Reticulation | Oxy- Acetylene Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: equipment and hoses Exposure: Caught between / caught by / struck by / trip & fall over equipment and hoses | Outcome :Body harm Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 9
2 | Equipment, Material & Substances | Low Voltage Reticulation | Oxy- Acetylene Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: Acetylene Exposure: Highly flammable gas | Outcome :Explosion Consequences: Possible - Personal injury/fatality/ property damage | x | [5 empty] | x |  |  |  |  | x |  | 21 | OHS Act, GSR 9
3 | Equipment, Material & Substances | Low Voltage Reticulation | Pneumatic power hand tools | N/A | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
4 | Equipment, Material & Substances | Low Voltage Reticulation | Hand tools (screw driver / wrench / hammer / pliers) | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
5 | Equipment, Material & Substances | Low Voltage Reticulation | Hand tools - Stanley knife | Installation / Maintenance / Repair | Any Related Activity |  |  | Artisan - Artisan assistant | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
6 | Equipment, Material & Substances | Low Voltage Reticulation | Hand tools - Stanley knife | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
7 | Equipment, Material & Substances | Low Voltage Reticulation | Testing Apparatus | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
8 | Equipment, Material & Substances | Low Voltage Reticulation | Power Tools (Drill/grinder etc.) | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
9 | Equipment, Material & Substances | Low Voltage Reticulation | Arc Welder | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
10 | Equipment, Material & Substances | Low Voltage Reticulation | Arc Welder | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Ultra violet radiation Exposure: Harmful radiation | Outcome :Eye/skin irritations Consequences: Possible - Cancer/ permanent damage to eyes | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
11 | Equipment, Material & Substances | Low Voltage Reticulation | Link Stick | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Cracked/Dirty/Wet/Soiled Stick Exposure: Contact with | Outcome :Body harm Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
12 | Equipment, Material & Substances | Low Voltage Reticulation | PPE | Installation / Maintenance / Repair | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Failure to wear PPE Exposure: Chemicals, sharp edges, handling material | Outcome :Injuries to body part Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None

## Generators
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Generators | Vehicles - TMM's | Operating vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Generators | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Generators | None | Walking | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Generators | None | Over-exposure to the sun | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Generators | Machinery | Neighbouring processes | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Generators | Scaffolding, man cage, platform | Working in a fall risk | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Generators | A variety of equipment / material / substances | Overhead lifting / working activities | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Functional | Generators | Generator | Locking out | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Accessing without locking out / incorrect / improper lock out. Exposure: Electricity/ moving parts | Outcome :Electrocution, caught by Consequences: Possible - Personal Injury/ fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Disciplinary Code 2. CoP Isolation and lockout 3. Machine and related guards 4. Permit system 5. VFL 6. HIRA 7. Hazard identification training
2 | Functional | Generators | Generator | Locking out | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Accidental/inadvertent start up Exposure: Electricity/ moving parts | Outcome :Electrocution, caught by Consequences: Possible - Personal Injury/ fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3 | 1. Disciplinary Code 2. CoP Isolation and lockout 3. Machine and related guards 4. Permit system 5. VFL 6. HIRA 7. Hazard identification training
3 | Functional | Generators | Generator | Testing voltage | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Contact with electricity Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 21.6.1 | 1. Sleeved connections 2. OEM Spec testing equipment 3. Trained and competent artisans and supervisors 4. VFL 5. Hazard identification training and HIRA
4 | Functional | Generators | Generator | Inspecting generator for faults/defects | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Contact with electricity Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 21.6.2 | 1. Sleeved connections 2. OEM Spec testing equipment 3. Trained and competent artisans and supervisors 4. VFL 5. Hazard identification training and HIRA
5 | Functional | Generators | Transformer oil | Testing voltage How do you marry transformer oil and testing - temperature, levels and heat would be paramount here and not testing with a multi meter | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | None
6 | Functional | Generators | Electricity | Inspection, repair, cleaning and maintenance/testing | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Poor ventilation Exposure: overcome by carbon monoxide | Outcome :Air poisoning Consequences: Possible - fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Generators would be placed in areas with through ventilation 2. If contained in a building an exhaust system must be in place 3. HIRA 4. VFL 5. Hazard identification training
7 | Functional | Generators | Electricity | Inspection, repair, cleaning and maintenance | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Slip & fall on spilled chemicals Exposure: Slippery surface | Outcome :Twisted/ fractured limb Consequences: Possible - Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Housekeeping 2. Chemical control std 3. PPE 4. HIRA 5. FVL 6. Hazard identification training
8 | Functional | Generators | Electricity | Taking oil samples | Inspection/Maintenance/ Testing | x |  | Authorised Artisan | Source: Contact with hot surfaces - overheated generator Exposure: Heat | Outcome :Burn wounds Consequences: Possible - Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Oil sampling Std 2. PPE 3. HIRA 4. Hazard identification trg 5. VFL
9 | Functional | Generators | Oil | Changing oil | Inspection/Maintenance/ Testing | x |  | Contractor | Source: Contact with hot oil Exposure: Heat | Outcome :Burn wounds Consequences: Possible - Personal injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Oil Changing Std 2. PPE 3. HIRA 4. Hazard identification trg 5. VFL
1 | Equipment, Material & Substances | Generators | Pneumatic power hand tools | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Machine and related guards 2. Housekeeping
2 | Equipment, Material & Substances | Generators | Hand tools (screw driver / wrench / hammer / pliers) | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
3 | Equipment, Material & Substances | Generators | Hand tools - Stanley knife | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Stanley knife sop 2. PPE 3. Trained and competent artisans and supervisors 4. HIRA 5. Hazard identification trg 6. VFL
4 | Equipment, Material & Substances | Generators | Hand tools - Stanley knife | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Stanley knife sop 2. PPE 3. Trained and competent artisans and supervisors 4. HIRA 5. Hazard identification trg 6. VFL
5 | Equipment, Material & Substances | Generators | Testing Apparatus | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome : Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Equipment testing procedure 2. OEM spec testing equipment 3. Test equipment calibration and servicing 4. PPE 5. VFL 6. HIRA
6 | Equipment, Material & Substances | Generators | Power Tools (Drill/grinder etc.) | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Tool Bags 2. Housekeeping 3. Clear and obstruction free walkways 4. PPE 5. HIRA 6. Hazard awareness training
7 | Equipment, Material & Substances | Generators | Chemical - Generator oil | Any | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Source: Hot transformer oil Exposure: Hot liquid This is too broad. Hot oil whilst contained in pipes, sumps etc. is no more a danger than drinking coffee. If there is failure of some sort e.g. a burst pipe, failed gasket etc. then the picture changes. To just state that there is contact with hot oil without describing where and how it occurred is simply not enough. | Outcome :Burn wounds Consequences: Possible - Injury/ Fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | None

## Transformers
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Transformers | Vehicles - TMM's | Operating vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Transformers | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Transformers | None | Walking | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Transformers | None | Over-exposure to the sun | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Transformers | Machinery | Neighbouring processes | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Transformers | Scaffolding, man cage, platform | Working in a fall risk | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Transformers | A variety of equipment / material / substances | Overhead lifting / working activities | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Functional | Transformers | N/A | Inspection, repair, cleaning and maintenance | Any Related Activity | x |  | Authorised Artisan | Source: Wires/ conductors is earthed through people Exposure: Electricity | Outcome :Electrocution Consequences: Possible - fatality/ Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.0 | 1. Sleeved connections 2. Insulated cables 3. Equipment earthing 4. Trained and competent artisans and supervisors 5. PPE 6. VFL 7. HIRA and hazard awareness trg
2 | Functional | Transformers | N/A | Inspection, repair, cleaning and maintenance | Any Related Activity | x |  | Authorised Artisan | Source: Electrical short circuiting Exposure: flashover | Outcome :Damage to equipment Consequences: Equipment damage | x | [5 empty] | x |  |  |  | x |  |  | 18 | MHS Act, Reg. 21.6.1 | 1. Sleeved connections 2. Insulated cables 3. Equipment earthing 4. Trained and competent artisans and supervisors 5. PPE 6. VFL 7. HIRA and hazard awareness trg
3 | Functional | Transformers | Transformer oil | Inspection, repair, cleaning and maintenance | Any Related Activity | x |  | Authorised Artisan | Source: Oil leaks Exposure: Contaminated oil containing PCB's. | Outcome :Fire Consequences: Possible - contamination, Explosion |  |  | x |  |  |  | x |  |  |  |  | x |  | 21 | None | 1. Inspections and over inspections 2. Environmental clean-up procedure 3. CoP for fire fighting 4. CoP Emergencies 5. Spill kits 6. PPE 7. Fire fight teams 8. HIRA and hazard identification trg 9. VFL
4 | Functional | Transformers | Electricity | Inspection, repair, cleaning and maintenance | Any Related Activity | x |  | Authorised Artisan | Source: Contact with hot oil transformer Exposure: Heat | Outcome :Burn wounds Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. PPE 2. Trained and competent artisans and supervisors 3. On-site medics 4. VFL HIRA and hazard identification trg
5 | Functional | Transformers | Electricity | Taking oil samples If your geographical is transformers and you are taking oil samples how can your equipment be electricity? | Taking oil samples | x |  | Contractor | Source: Contact with hot oil transformer Exposure: Heat | Outcome :Burn wounds Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None
6 | Functional | Transformers | Oil | Changing oil | Changing oil | x |  | Contractor | Source: Contact with hot oil transformer Exposure: Heat | Outcome :Burn wounds Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Oil change Procedure 2. Trained and competent artisans and supervisors 3. On-site medics 4. VFL 5. HIRA and hazard identification trg
7 | Functional | Transformers | Silica gel | Changing gel | Changing gel | x |  | Authorised Artisan | Source: Contact with gel Exposure: Harmful chemicals | Outcome :Poisoning Consequences: Possible - Injury/ fatality | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Gel changing procedure 2. PPE 3. Trg in Gel changing 4. VFL 5. Trained and competent artisans and supervisors 6. HIRA and hazard identification trg
1 | Equipment, Material & Substances | Generators | Pneumatic power hand tools | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training
2 | Equipment, Material & Substances | Generators | Hand tools (screw driver / wrench / hammer / pliers) | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
3 | Equipment, Material & Substances | Generators | Hand tools - Stanley knife | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct use of Stanley knife trg 2. PPE 3. VFL 4. HIRA and hazard awareness trg 5. Competent artisans and supervisors
4 | Equipment, Material & Substances | Generators | Hand tools - Stanley knife | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct use of Stanley knife trg 2. PPE 3. VFL 4. HIRA and hazard awareness trg 5. Competent artisans and supervisors
5 | Equipment, Material & Substances | Generators | Testing Apparatus | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. OEM spec testing equipment 2. Sleeved Connections 3. Insulation 4. CoP - Isolation and lockout 5. Live equipment testing procedure 6. Permit system 7. Periodic calibration, servicing and repair of testers 8. PPE 9. VFL 10. HIRA and hazard awareness trg
6 | Equipment, Material & Substances | Generators | Power Tools (Drill/grinder etc.) | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Housekeeping std Tool bags Guards and covers PPE Dedicated and obstacle free walkways and access routes VFL Trained and competent artisans and supervisors HIRA and hazard identification trg
7 | Equipment, Material & Substances | Generators | Chemical - Transformer oil | Any | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Hot transformer oil Exposure: Hot liquid Your description is Chemical - Transformer oil but after that the chemical portion is ignored also see comments on hot oil in previous tabs | Outcome :Burn wounds Consequences: Possible - Injury/ Fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | None

## Engineering Workshop
HS No | Category / Issue | Geographical Area | Equipment / Material / Substances | Processes | Activities | Activity Type |  | Occupations | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[6 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Workshop | Vehicles - TMM's | Operating vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Workshop | Flammable liquids | Combustion | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Workshop | None | Walking | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Workshop | None | Over-exposure to the sun | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Workshop | Machinery | Neighbouring processes | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Workshop | Scaffolding, man cage, platform | Working in a fall risk | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Workshop | A variety of equipment / material / substances | Overhead lifting / working activities | Any Related Activity | x |  | Employees, Supervisors, Management. | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Functional | Workshop | Lifting gear | Manual handling / lifting tools, electrical equipment, material, electrical parts or electrical components. | Use / Operate | x |  | Artisan, artisan assistant | Source: lifting chain, roller and guides of forklift mast Exposure: Confined space | Outcome : Broken ribs, body harm Consequences: Possible - Personal Injury | x |  |  |  |  | x | [6 empty] | x | 20 | None | 1. PPE 2. Lifting and Rigging SoP 3. Trained and competent workmen 4. Demarcated work areas 5. VFL 6. HIRA and hazard awareness trg
2 | Functional | Workshop | Hand tools | Conduct repair or maintenance activities to electrical equipment - Loosening and tightening fasteners. | Use / Operate | x |  | Artisan, artisan assistant | Source: tool slipping when loosening or tightening fasteners Exposure: Sharp edges | Outcome : Pitch by causing body harm Consequences: Possible - Personal Injury | x |  |  |  |  | x | [6 empty] | x | 20 | None | 1. Job specific tools 2. PPE 3. Trained and competed artisans 4. VFL 5. HIRA and hazard awareness trg
3 | Functional | Workshop | Doors | Opening and closing panels and doors. | Use / Operate | x |  | Artisan, artisan assistant | Source: access doors and panels Exposure: Caught in pinch point | Outcome : caught in / struck by Consequences: Possible - Personal Injury, | x |  |  |  |  | x | [6 empty] | x | 20 | None
4 | Functional | Workshop | Grinder | Grinding (Use of pedestal, bench grinder or portable grinder - angle grinder | using / operating | x |  | Artisan, artisan assistant | Source: rotating parts of grinding machine Exposure: sharp grinding machine disc. | Outcome :Cut of fingers/ loss Consequences: Possible - Personal Injury | x |  |  |  |  | x | [6 empty] | x | 20 | MHS Act, Reg. 20.4 / 20.5 | 1. Equipment safety devices - covers and guards 2. Trained and competent artisans and supervisors 3. Grinder specific training 4. PPE 5. VFL 6. HIRA and hazard awareness trg
5 | Functional | Workshop | Drill | Drilling (Use pedestal or portable drill) | Use / Operate | x |  | Artisan, artisan assistant | Source: rotating parts of drilling machine Exposure: sharp shavings | Outcome :Cut of fingers/ loss Consequences: Possible - Personal Injury | x |  |  |  |  | x | [6 empty] | x | 20 | MHS Act, Reg. 20.4 / 20.6 | 1. Trained and competent artisans and supervisors 2. Job specific trg 3. Housekeeping Std 4. VFL 5. HIRA and hazard awareness trg
6 | Functional | Workshop | Lifting gear | Manual handling - tools / equipment | Workshop | x |  | Artisan, artisan assistant | Source: Falling/dropped tools, equipment, material, parts or components Exposure: Possible serious injuries | Outcome : falling equipment Consequences: Possible - Personal Injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | None
7 | Functional | Workshop | Fork lift | Lift electrical equipment with a forklift. | Use / Operate | x |  | Artisan, artisan assistant - operators? | Source: hydraulic or mechanical raising/lowering movement of forklift boom - mast - and forks Exposure: Moving electrical equipment by forklift - Only electrical equipment? | Outcome : Falling equipment results in head injuries Consequences: Possible - Serious injury or fatality | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. Rigging and lifting std - no person may walk or stand below a suspended load 2. Trained and competed operators, artisans and supervisors 3. VFL 4. HIRA and hazard awareness trg
8 | Functional | Workshop | Grinder | Grinding (Use of pedestal or portable grinder) | Use / Operate | x |  | Artisan, artisan assistant | Source: Sharp objects - edges on grinded material Exposure: Sharp edges | Outcome : Hand cuts Consequences: Possible - Body harm | x |  |  |  |  | x | [6 empty] | x | 20 | None | 1. PPE 2. VFL 3.HIRA and hazard awareness trg
9 | Functional | Workshop | Globes | Remove or install globes or lenses. | Replace | x |  | Artisan, artisan assistant | Source: Broken glass Exposure: Sharp edges | Outcome : Hand cuts Consequences: Possible - Body harm | x |  |  |  |  | x | [6 empty] | x | 20 | None | 1. Trained and competent workmen and artisans 2. Correct tools and equipment supply 3. PPE 4. VFL 5. HIRA and hazard awareness trg
10 | Functional | Workshop | Arc welder | Welding | Use / Operate | x |  | Artisan, artisan assistant | Source: Electricity Exposure: Electrocution | Outcome : Electrical Shock Consequences: Possible - Serious injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. Insulated power supply and welder leads 2. Pre-use inspections 3. Job specific trg 4. Trained and competent artisans and supervisors 5. PPE VFL HIRA and hazard awareness trg
11 | Functional | Workshop | Testing equipment | Conduct fault finding or testing of electrical equipment | Maintenance | x |  | Artisan, artisan assistant | Source: Electricity Exposure: Electrocution | Outcome : Electrical shock Consequences: Possible - Possible - Serious injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.2 | 1. OEM spec testing equipment 2. Sleeved Connections 3. Insulation 4. CoP - Isolation and lockout 5. Live equipment testing procedure 6. Permit system 7. Periodic calibration, servicing and repair of testers 8. PPE 9. VFL 10. HIRA and hazard awareness trg
12 | Functional | Workshop | Fluorescent tubes | Remove or install fluorescent tubes. | Replace | x |  | Artisan, artisan assistant | Source: Fluorescent tubes Exposure: Harmful chemicals | Outcome :Health risk to body Consequences: Possible - Mercury poisoning | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, HCS 15 | 1. PPE 2. VFL 3.HIRA and hazard awareness trg
13 | Functional | Workshop | Oxy- Acetylene Cutting Equipment | Gas Cutting with oxygen and acetylene gas | Flame Cutting | x |  | Artisan, artisan assistant | Source: Hot metal Exposure: heat | Outcome :Burn wounds Consequences: Possible - Personal injury, medical expenses | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. PPE 2. VFL 3.HIRA and hazard awareness trg
14 | Functional | Workshop | Grinder | Grinding (Use of pedestal or portable grinder) | Grinding | x |  | Artisan, artisan assistant | Source: Hot metal Exposure: heat | Outcome :Burn wounds Consequences: Possible - Personal injury, medical expenses | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. PPE 2. VFL 3.HIRA and hazard awareness trg
15 | Functional | Workshop | Drill | Drilling (Use pedestal or portable drill) | Drilling | x |  | Artisan, artisan assistant | Source: sharp objects - edges on drilled material Exposure: sharp objects | Outcome :Finger/ hand cuts Consequences: Possible - Personal injury, medical expenses, body harm | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. PPE 2. VFL 3.HIRA and hazard awareness trg
16 | Functional | Workshop | Electricity | Conduct cleaning and maintenance activities to electrical equipment. | Cleaning and maintenance | x |  | Artisan, artisan assistant | Source: Toxic chemicals - PCB's Exposure: Harmful chemicals | Outcome :Skin infection Consequences: Possible - Cancer | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, HCS 15 | 1. PPE 2. VFL 3.HIRA and hazard awareness trg
17 | Functional | Workshop | Compressor | Testing components inside the electrical panel of the Compressor | Maintaining | x |  | Artisan, artisan assistant | Source: Loose components Exposure: in contact with electricity | Outcome : Body harm Consequences: Possible - electrocution | x | [5 empty] | x |  |  |  | x |  |  | 18 | None
18 | Functional | Workshop | Grinder | Grinding (Use of pedestal or portable grinder) | Grinding | x |  | Artisan, artisan assistant | Source: Flammable liquid and gas Exposure: Harmful chemicals and gas | Outcome :Fire and explosion Consequences: Possible - Serious burn wounds, fatality | x | [6 empty] | x |  |  |  | x |  | 24 | OHS Act, ERW 9 | 1. Chemical handling std 2. MSDS 3. Housekeeping 4. Fire Fighting CoP 5. Fire fighting equipment 6. On-site medics 7. Trained and competent artisans and supervisors 8. VFL 9. HIRA and hazard awareness trg
19 | Functional | Workshop | Oxy- Acetylene Cutting Equipment | Gas cutting with oxygen and acetylene gas | Flame cutting | x |  | Artisan, artisan assistant | Source: Flammable liquid and gas Exposure: Harmful chemicals and gas | Outcome :Fire and explosion Consequences: Possible - Serious burn wounds, fatality | x | [6 empty] | x |  |  |  | x |  | 24 | OHS Act, ERW 9 | 1. Chemical handling std 2. MSDS 3. Housekeeping 4. Fire Fighting CoP 5. Fire fighting equipment 6. On-site medics 7. Trained and competent artisans and supervisors 8. VFL 9. HIRA and hazard awareness trg
20 | Functional | Workshop | Arc welder | Welding | Welding | x |  | Artisan, artisan assistant | Source: Flammable liquid and gas Exposure: Harmful chemicals and gas | Outcome :Fire and explosion Consequences: Possible - Serious burn wounds, fatality | x | [6 empty] | x |  |  |  | x |  | 24 | OHS Act, ERW 9 | 1. Chemical handling std 2. MSDS 3. Housekeeping 4. Fire Fighting CoP 5. Fire fighting equipment 6. On-site medics 7. Trained and competent artisans and supervisors 8. VFL 9. HIRA and hazard awareness trg
21 | Functional | Workshop | Oxy- Acetylene Cutting Equipment | Gas Cutting with oxygen and acetylene gas | Flame cutting | x |  | Artisan, artisan assistant | Source: Gas cutting mild steel with CO2 & Acetylene gas Exposure: Harmful gas | Outcome :Respiratory problems Consequences: Possible - Lung infections |  | x |  |  |  |  | x |  |  |  | x |  |  | 18 | OHS Act, ERW 5 | 1. PPE 2. Trained and competent artisans and supervisors 3. VFL 4. HIRA and hazard awareness trg
22 | Functional | Workshop | None | Move around inside and outside the workshop to conduct inspection, repair, cleaning or maintenance activities. | Walking | x |  | Artisan, artisan assistant | Source: Slip, Trip and Fall - Debris, rocks. Equipment, machine parts Exposure: Poor housekeeping | Outcome :Trip and fall Consequences: Possible - Twisted/ fractured body part | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. Housekeeping std 2. Dedicated walkways and access routes 3. PPE 4. VFL 5. HIRA and hazard awareness trg
23 | Functional | Workshop | Tubes/globes | Storage and disposal of fluorescent tubes / globes | Storage / disposal | x |  | Artisan, artisan assistant | Source: Spillage - Emission of hazardous chemical: Mercury Exposure: Harmful chemicals | Outcome :Skin infection with mercury Consequences: Possible - Body harm | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, HCS 15 | 1. Std on disposal of Fluorescent tubes 2. Environmental management plan 3. PPE 4. VFL 5. HIRA and hazard awareness trg
24 | Functional | Workshop | Grinder | Grinding (Use of pedestal or portable grinder) | Grinding | x |  | Artisan, artisan assistant |  | Outcome :Fire and contamination Consequences: Possible - Environmental risk |  |  | x |  |  |  | x |  |  |  | x |  |  | 18 | None
25 | Functional | Workshop | Transformer oil | Conduct inspection, cleaning and maintenance activities to transformers. | Inspection, Cleaning, Maintenance | x |  | Artisan, artisan assistant | Source: Transformer oil spill Exposure: Trip / Slip - and fall due to Spillage | Outcome :Hand and knee injuries Consequences: Possible - Personal injury/Environmental risk |  |  | x |  |  |  | x |  |  |  | x |  |  | 18 | None | 1. Oil spill kits 2. Environmental management plan 3. Drip trays 4. PPE 5. VFL 6. HIRA and hazard identification trg
26 | Functional | Workshop | Lifting equipment | Lifting - material / equipment equipment | Use / Operate | x |  | Artisan, artisan assistant | Source: Falling/dropped tools, electrical equipment, material, parts or components Exposure: Struck by Falling/dropped tools, electrical equipment, material, parts or components | Outcome :Head injuries Consequences: Possible - Personal injury | x | [5 empty] | x |  |  |  | x |  |  | 18 | None
27 | Functional | Workshop | Grinder | Grinding (Use of pedestal or portable grinder) | Grinding | x |  | Artisan, artisan assistant | Source: flying objects - grinding disc fragments or metal debris Exposure: Struck by flying objects | Outcome: Eye/ hand injuries Consequences: Possible - Permanent loss of eye sight | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. Equipment guards and covers 2. Pre-use inspections 3. Inspections and over inspections 4. PPE 5. Grinder safety trg 6. VFL 7. HIRA and hazard awareness trg
28 | Functional | Workshop | Drill | Drilling (Use pedestal or portable drill) | Drilling | x |  | Artisan, artisan assistant | Source: flying shavings or fragments of the drill bit, or by the work piece itself. Exposure: Struck by flying objects | Outcome :Eye/ hand injuries Consequences: Possible - Permanent loss of eye sight | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. Pre-use inspections 2. Inspections and over inspections 3. PPE 4. Grinder safety trg 5. VFL 6. HIRA and hazard awareness trg
29 | Functional | Workshop | Compressor | Using compressed air | Use / Operation | x |  | Artisan, artisan assistant | Source: pressure line components - couplers and fitting Exposure: Unsecure pressure line components | Outcome :Struck by pressure line components Consequences: Possible - Body harm by components | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. Safety slings 2. PPE 3. Job specific trg 4. Trained and competent artisans and supervisors 5. Inspections 6. VFL 7. HIRA and hazard awareness and training
1 | Equipment, Material & Substances | Workshop | Oxy- Acetylene Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: equipment and hoses Exposure: Caught between / caught by / struck by / trip & fall over equipment and hoses | Outcome :Body harm Consequences: Possible - Personal injury | x |  |  |  |  | x | [6 empty] | x | 20 | OHS Act, GSR 9
2 | Equipment, Material & Substances | Workshop | Oxy- Acetylene Cutting Equipment | Flame cutting | Flame cutting | x |  | Artisan - Artisan assistant | Source: Acetylene Exposure: Highly flammable gas | Outcome :Explosion Consequences: Possible - Personal injury/fatality/ property damage | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, GSR 9
3 | Equipment, Material & Substances | Workshop | Pneumatic power hand tools | Use / operate | Any Related Activity | x |  | Artisan - Artisan assistant | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
4 | Equipment, Material & Substances | Workshop | Hand tools (screw driver / wrench / hammer / pliers) | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
5 | Equipment, Material & Substances | Workshop | Hand tools - Stanley knife | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
6 | Equipment, Material & Substances | Workshop | Hand tools - Stanley knife | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
7 | Equipment, Material & Substances | Workshop | Testing Apparatus | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
8 | Equipment, Material & Substances | Workshop | Power Tools (Drill/grinder etc.) | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
9 | Equipment, Material & Substances | Workshop | Arc Welder | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
10 | Equipment, Material & Substances | Workshop | Arc Welder | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Ultra violet radiation Exposure: Harmful radiation | Outcome :Eye/skin irritations Consequences: Possible - Cancer/ permanent damage to eyes |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | None
11 | Equipment, Material & Substances | Workshop | Link Stick | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Cracked/Dirty/Wet/Soiled Stick Exposure: Contact with | Outcome :Body harm Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
12 | Equipment, Material & Substances | Workshop | PPE | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: Failure to wear PPE Exposure: Chemicals, sharp edges, handling material | Outcome :Injuries to body part Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
13 | Equipment, Material & Substances | Workshop | Compressor | Use / operate | Use / operate | x |  | Artisan - Artisan assistant | Source: equipment and hoses Exposure: Caught between / caught by / struck by / trip & fall over equipment and hoses | Outcome :Body harm Consequences: Possible - Personal injury | x |  |  |  |  | x | [6 empty] | x | 20 | None

## Weighbridges
HS No | Category | Geographical Area | Equipment / Material / Substances | Activities | Activity Type |  | Occupation | Process / Task | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[5 empty] | Routine | Non Routine |  |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Weighbridges | Vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Operating vehicles - TMM's | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Weighbridges | Flammable liquids | Any Related Activity | x |  | Employees, Supervisors, Management. | Combustion | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Weighbridges | None | Any Related Activity | x |  | Employees, Supervisors, Management. | Walking | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Weighbridges | None | Any Related Activity | x |  | Employees, Supervisors, Management. | Over-exposure to the sun | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Weighbridges | Machinery | Any Related Activity | x |  | Employees, Supervisors, Management. | Neighbouring processes | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Weighbridges | Scaffolding, man cage, platform | Any Related Activity | x |  | Employees, Supervisors, Management. | Working in a fall risk | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Weighbridges | A variety of equipment / material / substances | Any Related Activity | x |  | Employees, Supervisors, Management. | Overhead lifting / working activities | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Nature | Weighbridges | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Over-exposure to the sun | Source: Sun Exposure: Ultra violet radiation | Outcome: Health risk, body harm Consequences: Possible - Skin damage, cancer, medical expenses | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 9.75 | 25 |  |  |  | x | x
2 | Nature | Weighbridges | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working outdoor and/or at heights in the presence of lightning | Source: lightning Exposure: Struck by | Outcome: Severe body harm / burn Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Lightning SOP 2. Early detection device | 1. BIP-SOP-SHE.006 |  | 7.7 | 65 |  |  | x | x
3 | Nature | Weighbridges | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working in dusty conditions | Source: Dust Exposure: Inhalation of dust | Outcome: Respiratory infections / irritations Consequences: Possible - Serious illness |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 9.2 & 11.6 & Mandatory COP | 1. COP for Airborne Pollutants 2. Dust suppression SOP 3. Hygiene monitoring 4. PPE | 1. BIP-COP-001 |  | 9.75 | 25 |  |  |  | x | x
4 | Nature | Weighbridges | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working in the veldt | Source: Spiders and insects Exposure: Been bitten by | Outcome: Poison of the human body Consequences: Possible - fatality / Serious injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Risk assessment for veld work 2. Awareness 3. Buddy System 4. PPE 5. On-site paramedics |  |  | 4.25 | 75 |  |  | x | x | x
5 | Nature | Weighbridges | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Unprotected / no protection / exposure | Source: Extreme weather conditions Exposure: Extreme heat or cold | Outcome: Health risk Consequences: Possible - Hypertension / freeze | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12 | 25 |  |  |  | x | x
6 | Nature | Weighbridges | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Unprotected / no protection / exposure | Source: rain Exposure: Slippery surfaces | Outcome :Slip and fall Consequences: Possible - Personal Injury | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Emergency COP 2. Risk Assessments 3. Awareness Training | 1. BIP-COP-010 |  | 13.6 | 15 |  |  |  | x
1 | Functional | Weighbridges | Electricity | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Poor maintenance on electrical systems Exposure: Heat Under construction not in operation at best commissioning and handover | Outcome :Power interruptions Consequences: Possible - Fatality or injuries, Production loss | x | [6 empty] | x |  |  |  | x |  | 24 | None
2 | Functional | Weighbridges | Electricity | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Falling into trenches at weighbridge Exposure: Uncovered excavation/ trench | Outcome :Twisted/ fracture body parts Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.2 | 1. Excavation standard 2. HIRA 3. VFL 4. Inspections and over-inspections Hazard awareness training
3 | Functional | Weighbridges | Electricity | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: working on live currents Exposure: Heat | Outcome :Electrocution Consequences: Possible - Burn wounds | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. Standard to world on live equipment 2. Permit system 3. OEM sect testers and equipment 4. Trained and competent artisans and supervisors 5. VFL 6. HIRA Hazard awareness training 7. PPE
4 | Functional | Weighbridges | Electricity | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Slip/trip and fall uneven terrain/cross-overs, walkways/ stairs Exposure: Obstructed objects | Outcome :Twisted/ fracture body parts Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Housekeeping 2, Dedicated walkways 3. VFL 4. Inspections 5. HIRA 6. Hazard awareness training
5 | Functional | Weighbridges | Electricity | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Lightning striking high masts, vehicles etc. Exposure: Heat | Outcome :damage equipment, electrical shock Consequences: Possible - Serious injuries/Fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Emergency CoP 2. Fire Fighting CoP 3. Fire fighting team 4. CoP Isolation and lockout 5.
6 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Caught between two surfaces when using hand tools - loosening or fastening fasteners Exposure: Confined space | Outcome :Body harm Consequences: Possible - Injury/hand | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct tools and equipment 2. Trained and competent artisans and supervisors 3. HIRA 4. VFL 5. Sop's Hazard awareness training 6. PPE
7 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Caught by nip point Exposure: Confined space | Outcome :Body harm Consequences: Possible - Injury/hand | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct tools and equipment 2. Trained and competent artisans and supervisors 3. HIRA 4. VFL 5. Sop's Hazard awareness training 6. PPE
8 | Functional | Weighbridges | Lights | Installation/ maintenance/repairs | x |  | Authorised Artisan | Fitting light bulb | Source: Contact with broken glass Exposure: Sharp edges | Outcome :Finger cuts Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct tools and equipment 2. Trained and competent artisans and supervisors 3. HIRA 4. VFL 5. Sop's Hazard awareness training 6. PPE
9 | Functional | Weighbridges | Ladder | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: Possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 | 1. Ladder standard 2. Working at Heights CoP 3. Fit for purpose ladders 4. HIRA 5. VFL 6. Hazard awareness training
10 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Falling from elevated surfaces Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: Possible - fatality/injury | x | [5 empty] | x |  |  |  | x |  |  | 18 | OHS Act, GSR 6 & CR 9 | 1. Ladder standard 2. Working at Heights CoP 3. Fit for purpose ladders 4. HIRA 5. VFL 6. Hazard awareness training
11 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Caught in/between moving parts Exposure: Moving parts | Outcome :Finger cuts Consequences: Possible - Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 20.4 / 20.5 | 1. Guards 2. PPE 3. VFL 4. Correct tools 5. Hazard awareness training 6. HIRA
12 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: rain Exposure: Slippery surfaces | Outcome :Slip and fall Consequences: Possible - Personal Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. PPE 2. HIRA 3. Hazard awareness Training VFL
13 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Unsafe acts Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Machine guards 2. Electrical Panel Covers 3. Disciplinary Code 4. VFL 5. HIRA 6. Hazard awareness trg 7. PPE
14 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Wearing Incorrect or damaged PPE Exposure: Sharp edges | Outcome :Finger cuts Consequences: Possible - Injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | None | 1. PPE inspection and issue std 2. PPE Stock 3. VFL 4. HIRA 5. Supervision
15 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Working under unsafe conditions – No HIRA done Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: Possible - Personal Injury/fatality | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 20.4 / 20.5 / 21.6.1 | 1. Machine guards 2. Electrical Panel Covers 3. Disciplinary Code 4. VFL 5. Supervision
16 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Lock out procedure | Source: Accessing without locking out / incorrect / improper lock out. Exposure: Moving parts/ electricity | Outcome :Body harm Consequences: Possible - Personal Injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. CoP isolation and lockout 2. Personal lock issues 3. Machine guards 4. Electrical panel covers 5. Disciplinary Code 6. VFL 7. Competent supervision
17 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Lock out procedure | Source: Accidental/inadvertent start up Exposure: Electricity/ moving parts | Outcome :Body harm Consequences: Possible - fatality/injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3 | 1. CoP isolation and lockout 2. Personal lock issues 3. Machine guards 4. Electrical panel covers 5. Disciplinary Code 6. VFL 7. Competent supervision
18 | Functional | Weighbridges | Computers | Installation/ maintenance/repairs | x |  | Authorised Artisan | Inspection, repair, maintenance | Source: Trip and fall over cables Exposure: Obstructed objects | Outcome :Body harm Consequences: Possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Housekeeping std 2. Dedicated walkways 3. HIRA 4. VFL 5. Hazard awareness training
19 | Functional | Weighbridges | Light bulb | Installation/ maintenance/repairs | x |  | Authorised Artisan | Replacing bulbs | Source: Contact with broken glass Exposure: Mercury | Outcome :Finger cuts/poison Consequences: Possible - Injury/ health risk | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Purpose built ladders 2. Working with a ladder std 3. PPE 4. VFL 5. HIRA 6. Hazard awareness training 7. Supervision
20 | Functional | Weighbridges | Ladder | Installation/ maintenance/repairs | x |  | Authorised Artisan | Replacing bulbs | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: Possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 | 1. Purpose built ladders 2. Working with a ladder std 3. PPE 4. VFL 5. HIRA 6. Hazard awareness training 7. Supervision CoP - working at heights
21 | Functional | Weighbridges | Hand tools | Installation/ maintenance/repairs | x |  | Authorised Artisan | Replacing plugs/switches | Source: Contact with electricity Exposure: Electricity | Outcome :electrical shock Consequences: Possible - injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.6.1 | 1. CoP - Isolation and lock-out 2. Trained and competent artisans 3. VFL 4. Supervision Hira
1 | Equipment/Material/ Substances | Weighbridges | Hand tools (screw driver / wrench / hammer / pliers) | Installations, services, maintenance, ad hoc | x |  | Authorised Artisan | Any | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 12 | 25 |  |  |  | x | x
2 | Equipment/Material/ Substances | Weighbridges | Testing Apparatus | Installations, services, maintenance, ad hoc | x |  | Authorised Artisan | Any | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
1 | General / Other | BIP - Project | Operation of vehicles, power tools, Scaffolding | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Fatigue | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. COP for fatigue 2. Awareness Training | 1. BIP-COP-007 |  | 18.7 | 15 |  |  |  | x
2 | General / Other | Weighbridges | Operation of vehicles, power tools | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Judgement error | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competent and Trained employees and supervisors 2. Risk assessments 3.Awareness Training 4. VFL 5.PTO |  |  | 18.7 | 15 |  |  |  | x
3 | General / Other | Weighbridges | Operation of vehicles, power tools, Erecting Scaffolding | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Incompetency | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Pre-screened employees 2. Competency/Training certificates 3. Risk assessments 4. Awareness Training 5. PTO's 6. VFL 7. Contractor Management SOP | 7. BIP-SOP-SHE.007 |  | 18.7 | 15 |  |  |  | x
4 | Employee working alone - General / Other | Weighbridges | None | Work | x | x | Employee - (Male / Female) | Any work related tasks - During ordinary working hours | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Possible - Physical / sexual assault, serious personal injuries that may escalate to a signal fatality. | x | [6 empty] | x |  |  | x |  |  | 22 | DMR Instruction | 1. Emergency COP 2. Buddy system 3. Risk assessment 4. Communication system | 1. BIP-COP-010 |  | 18.7 | 15 |  |  |  | x
5 | General / Other | Weighbridges | Any | Work | x |  | Employees, Artisans, Supervisors, Management. | Not following Safe work procedures | Exposure: At risk behaviour | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. PTO's 5. VFL 6. Disciplinary code |  |  | 18.7 | 15 |  |  |  | x

## Electrical Motors
HS No | Category | Geographical Area | Equipment / Material / Substances | Activities | Activity Type |  | Occupation | Process / Task | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[5 empty] | Routine | Non Routine |  |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Electrical Motors | Vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Operating vehicles - TMM's | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Electrical Motors | Flammable liquids | Any Related Activity | x |  | Employees, Supervisors, Management. | Combustion | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Electrical Motors | None | Any Related Activity | x |  | Employees, Supervisors, Management. | Walking | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Electrical Motors | None | Any Related Activity | x |  | Employees, Supervisors, Management. | Over-exposure to the sun | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Electrical Motors | Machinery | Any Related Activity | x |  | Employees, Supervisors, Management. | Neighbouring processes | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Electrical Motors | Scaffolding, man cage, platform | Any Related Activity | x |  | Employees, Supervisors, Management. | Working in a fall risk | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Electrical Motors | A variety of equipment / material / substances | Any Related Activity | x |  | Employees, Supervisors, Management. | Overhead lifting / working activities | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Nature | Electrical Motors | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Over-exposure to the sun | Source: Sun Exposure: Ultra violet radiation | Outcome: Health risk, body harm Consequences: Possible - Skin damage, cancer, medical expenses | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 9.75 | 25 |  |  |  | x | x
2 | Nature | Electrical Motors | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working outdoor and/or at heights in the presence of lightning | Source: lightning Exposure: Struck by | Outcome: Severe body harm / burn Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Lightning SOP 2. Early detection device | 1. BIP-SOP-SHE.006 |  | 7.7 | 65 |  |  | x | x
3 | Nature | Electrical Motors | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working in dusty conditions | Source: Dust Exposure: Inhalation of dust | Outcome: Respiratory infections / irritations Consequences: Possible - Serious illness |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 9.2 & 11.6 & Mandatory COP | 1. COP for Airborne Pollutants 2. Dust suppression SOP 3. Hygiene monitoring 4. PPE | 1. BIP-COP-001 |  | 9.75 | 25 |  |  |  | x | x
4 | Nature | Electrical Motors | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working in the veldt | Source: Spiders and insects Exposure: Been bitten by | Outcome: Poison of the human body Consequences: Possible - fatality / Serious injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Risk assessment for veld work 2. Awareness 3. Buddy System 4. PPE 5. On-site paramedics |  |  | 4.25 | 75 |  |  | x | x | x
5 | Nature | Electrical Motors | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Unprotected / no protection / exposure | Source: Extreme weather conditions Exposure: Extreme heat or cold | Outcome: Health risk Consequences: Possible - Hypertension / freeze | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12 | 25 |  |  |  | x | x
6 | Nature | Electrical Motors | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Unprotected / no protection / exposure | Source: rain Exposure: Slippery surfaces | Outcome :Slip and fall Consequences: Possible - Personal Injury | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Emergency COP 2. Risk Assessments 3. Awareness Training | 1. BIP-COP-010 |  | 13.6 | 15 |  |  |  | x
1 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Locking out | Source: Accessing without locking out / incorrect / improper lock out. Exposure: Moving machinery/ electricity | Outcome :Electrocution/ body harm Consequences: Possible - Serious injury/fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2 | 1. Disciplinary Code 2. CoP Isolation and lock out 3. Personal locks 4. Machine and equipment guards 5. VFL 6. Trained and competent artisans and supervisors 7. HIRA 8. VFL
2 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Locking out | Source: Accidental/inadvertent start up Exposure: Moving machinery | Outcome :body harm Consequences: Possible - Serious injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3 | 1. Disciplinary Code 2. CoP Isolation and lock out 3. Personal locks 4. Machine and equipment guards 5. VFL 6. Trained and competent artisans and supervisors 7. HIRA 8. VFL
3 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Testing voltage | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. OEM Spec testing equipment 2. Calibration, servicing and repair of testing equipment by OEM 3. Test SoP 4. PPE 5. Trained and competence artisans and supervisors 6. FVL HIRA Hazard awareness training
4 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspecting motor for faults/defects | Source: Contact with electricity Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [5 empty] | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 21.6.1 | 1. PPE 2. Guards and covers Trained and competent artisans VFL HIRA and hazard awareness training
5 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, cleaning and maintenance/testing | Source: Lifting/handling heavy equipment by hand Exposure: Injury lifting heavy material | Outcome :Spinal/lower back injury Consequences: Possible - Injury/ permanent disable | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Lifting procedure 2. Assistants available
6 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, cleaning and maintenance | Source: Contact with electrical supply to electrical motor, body parts or objects caught in cooling fan. Exposure: Electricity/ moving body parts | Outcome :Electrocution. Consequences: Possible - Electrical shock/injuries/amputation | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. PPE 2. Sleeved connections 3. Insulated cables 4. Fan guards 5. Inspections and over inspections 6. Housekeeping 7. VFL
7 | Functional | Electrical Motors | Electrical Motor | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, cleaning and maintenance | Source: Objects or body parts caught in/on exposed shaft, caught in drive coupling or v-belt and pulleys. Exposure: Electricity/ moving parts | Outcome :Electrocution/caught in cooling fan. Consequences: Possible - Electrical shock/injuries/amputation | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 | 1. PPE 2. Sleeved connections 3. Insulated cables 4. Machine/equipment guards 5. Inspections and over inspections 6. Housekeeping 7. VFL
8 | Functional | Electrical Motors | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Overheating of motor Exposure: Heat | Outcome :Burn wounds Consequences: Possible - Burn injuries | x | [5 empty] | x |  |  |  | x |  |  | 18 | None | 1. Frequent equipment inspections 2. PPE 3. OEM certified motors 4. HIRA 5. VFL
9 | Functional | Electrical Motors | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Falling into trenches at pumps Exposure: Open trenches | Outcome :Body harm Consequences: Possible - Twisted/ fractured body limbs | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.2 | 1. Barricades/fences/guards 2. Dedicated access routes 3. VFL 4. HIRA and hazard awareness trg
10 | Functional | Electrical Motors/Equipment | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: working on live currents Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injuries/ fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | MHS Act, Reg. 21.6.1 | 1. Live current Testing Procedure 2. Permit system 3. OEM Spec testing equipment 4. PPE 5. Trained and competent artisans and supervisors 6. VFL 7. HIRA and hazard identification training
11 | Functional | Electrical Motors/Equipment | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Grass and vegetation Exposure: Heat | Outcome :Fire Consequences: Possible - Injuries/ Burns | x | [5 empty] | x |  |  | x |  |  |  | 14 | None | 1. Housekeeping/Maintenace around motors 2. HIRA and hazard identification training
12 | Functional | Electrical Motors/Equipment | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Falling into water Exposure: Deep water | Outcome :Drowning Consequences: Possible - fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Buddy system 2. Fenced water bodies 3. Lifelines and buoys 4. VFL 5. HIRA and hazard identification trg
13 | Functional | Electrical Motors/Equipment | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Slip/trip and fall uneven terrain/cross-overs, walkways/ stairs Exposure: uneven terrain/cross-overs, walkways/ stairs | Outcome :Twisted/ fractured limb Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
14 | Functional | Electrical Motors/Equipment | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Attack by criminal intent - sabotage/Theft Exposure: Attacking/ assault | Outcome :Been shot Consequences: Possible - Personal injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
15 | Functional | Electrical Motors/Equipment | Electrical Pump | Inspection/Maintenance/ Testing | x |  | Authorised Artisan, artisan assistant | Inspection, repair, maintenance | Source: Faulty wiring Exposure: Heat | Outcome :Fire/ explosion Consequences: Possible - Burn wounds/ property, equipment damage | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1
1 | Equipment, Material & Substances | Generators | Pneumatic power hand tools | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Caught between / caught by / struck by / trip & fall Exposure: Caught between / caught by / struck by / trip & fall | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
2 | Equipment, Material & Substances | Generators | Hand tools (screw driver / wrench / hammer / pliers) | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
3 | Equipment, Material & Substances | Generators | Hand tools - Stanley knife | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct use of Stanley knife trg 2. PPE 3. VFL 4. HIRA and hazard awareness trg 5. Competent artisans and supervisors
4 | Equipment, Material & Substances | Generators | Hand tools - Stanley knife | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Correct use of Stanley knife trg 2. PPE 3. VFL 4. HIRA and hazard awareness trg 5. Competent artisans and supervisors
5 | Equipment, Material & Substances | Generators | Testing Apparatus | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Sleeved connections 2. Cable insulation 3. Testing SoP 4. PPE 5. OEM Spec testing equipment 6. Periodic OEM testing, calibration and repair of equipment 7. Trained and competent artisans and supervisors 8. VFL 9. HIRA and hazard awareness training
6 | Equipment, Material & Substances | Generators | Power Tools (Drill/grinder etc.) | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Tool Bags 2. Housekeeping 3. Clear and obstruction free walkways 4. PPE 5. HIRA 6. Hazard awareness training
7 | Equipment, Material & Substances | Generators | Chemical - Generator oil | Any Related Activity | x |  | Authorised Artisan, artisan assistant | Any | Source: Hot transformer oil Exposure: Hot liquid This is too broad. Hot oil whilst contained in pipes, sumps etc. is no more a danger than drinking coffee. If there is failure of some sort e.g. a burst pipe, failed gasket etc. then the picture changes. To just state that there is contact with hot oil without describing where and how it occurred is simply not enough. | Outcome :Burn wounds Consequences: Possible - Injury/ Fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | None
1 | General / Other | Electrical Motors | Operation of vehicles, power tools, Scaffolding | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Fatigue | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. COP for fatigue 2. Awareness Training | 1. BIP-COP-007 |  | 18.7 | 15 |  |  |  | x
2 | General / Other | Electrical Motors | Operation of vehicles, power tools | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Judgement error | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competent and Trained employees and supervisors 2. Risk assessments 3.Awareness Training 4. VFL 5.PTO |  |  | 18.7 | 15 |  |  |  | x
3 | General / Other | Electrical Motors | Operation of vehicles, power tools, Erecting Scaffolding | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Incompetency | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Pre-screened employees 2. Competency/Training certificates 3. Risk assessments 4. Awareness Training 5. PTO's 6. VFL 7. Contractor Management SOP | 7. BIP-SOP-SHE.007 |  | 18.7 | 15 |  |  |  | x
4 | Employee working alone - General / Other | Electrical Motors | None | Work | x | x | Employee - (Male / Female) | Any work related tasks - During ordinary working hours | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Possible - Physical / sexual assault, serious personal injuries that may escalate to a signal fatality. | x | [6 empty] | x |  |  | x |  |  | 22 | DMR Instruction | 1. Emergency COP 2. Buddy system 3. Risk assessment 4. Communication system | 1. BIP-COP-010 |  | 18.7 | 15 |  |  |  | x
5 | General / Other | Electrical Motors | Any | Work | x |  | Employees, Artisans, Supervisors, Management. | Not following Safe work procedures | Exposure: At risk behaviour | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. PTO's 5. VFL 6. Disciplinary code |  |  | 18.7 | 15 |  |  |  | x

## Siding- Electrical
HS No | Category | Geographical Area | Equipment / Material / Substances | Activities | Activity Type |  | Occupation | Process / Task | Hazard | Risk - Consequence | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | RAW RISK RATING | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[26 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[5 empty] | Routine | Non Routine |  |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Geographical | Siding Electrical | Vehicles - TMM's | Any Related Activity | x |  | Employees, Supervisors, Management. | Operating vehicles - TMM's | Source: Moving Vehicles Exposure: Struck by | Outcome: Interaction between men and equipment Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 8.8. | 1. COP for TMM's 2. Traffic Management Plan 3. Signage 4. PPE | 1. BIP-COP-008 2. BIP-TPL-SHE.001 |  | 18 | 25 |  |  |  | x | x
2 | Geographical | Siding Electrical | Flammable liquids | Any Related Activity | x |  | Employees, Supervisors, Management. | Combustion | Source: Flammable liquids and fumes Exposure: Ignition / Heat | Outcome: Fire Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 | 1. COP for Firefighting and prevention 2. Firebreaks 3. Firefighting LDV 4. Fire teams | 1. BIP-COP-011 |  | 16.5 | 25 |  |  |  | x | x
3 | Geographical | Siding Electrical | None | Any Related Activity | x |  | Employees, Supervisors, Management. | Walking | Source: Material, uneven ground, loose rocks Exposure: Slip, trip and fall | Outcome: Slip, Trip and fall Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Contractor RA & Mini-HIRA 2. Toolbox Talks 3. Awareness 4. Housekeeping 5. Dedicated walkways 6. Some areas will be engineered surfaces |  |  | 3.25 | 75 |  |  | x | x | x
4 | Geographical | Siding Electrical | None | Any Related Activity | x |  | Employees, Supervisors, Management. | Over-exposure to the sun | Source: Sun Exposure: Ultra violet radiation | Outcome: Skin infection Consequences : Possible - Cancer |  | x |  |  |  | x | [5 empty] | x |  | 17 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 4.25 | 75 |  |  | x | x | x
5 | Geographical | Siding Electrical | Machinery | Any Related Activity | x |  | Employees, Supervisors, Management. | Neighbouring processes | Source: Conveyors and neighbouring processes Exposure: Excessive noise | Outcome: Hearing loss Consequences : Possible - Health risk |  | x |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 9.2 & 11.4 & Mandatory COP | 1. COP for Noise 2. PPE SOP 3. COP for PPE for WIM | 1. BIP-COP-002 2. BIP-SOP-SHE.005 3. BIP-COP-006 |  | 12.75 | 25 |  |  |  | x | x
6 | Geographical | Siding Electrical | Scaffolding, man cage, platform | Any Related Activity | x |  | Employees, Supervisors, Management. | Working in a fall risk | Source: Heights Exposure: Fall | Outcome: Faulty equipment / lack of training Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | OHS Act, GSR 6 & CR 8 | 1. EZTSR 2. ICFRC 3. Fall protection/Fall arrest plan (Contractors) 4. Working at heights training 5. PPE |  |  | 5.5 | 75 |  |  | x | x | x
7 | Geographical | Siding Electrical | A variety of equipment / material / substances | Any Related Activity | x |  | Employees, Supervisors, Management. | Overhead lifting / working activities | Source: Falling objects Exposure: Struck by falling objects | Outcome: Unsecure materials / objects Consequences: Possible - Serious injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Lifting and Support of equipment SOP 2. Risk Assessments 3. EZTSR 4. ICFRC 5. PPE | 1. BIP-SOP-ENG.002 |  | 3.25 | 75 |  |  | x | x | x
Any
1 | Nature | Siding Electrical | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Over-exposure to the sun | Source: Sun Exposure: Ultra violet radiation | Outcome: Health risk, body harm Consequences: Possible - Skin damage, cancer, medical expenses | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 9.75 | 25 |  |  |  | x | x
2 | Nature | Siding Electrical | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working outdoor and/or at heights in the presence of lightning | Source: lightning Exposure: Struck by | Outcome: Severe body harm / burn Consequences: Possible - fatality / Serious injury | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Lightning SOP 2. Early detection device | 1. BIP-SOP-SHE.006 |  | 7.7 | 65 |  |  | x | x
3 | Nature | Siding Electrical | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working in dusty conditions | Source: Dust Exposure: Inhalation of dust | Outcome: Respiratory infections / irritations Consequences: Possible - Serious illness |  | x |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 9.2 & 11.6 & Mandatory COP | 1. COP for Airborne Pollutants 2. Dust suppression SOP 3. Hygiene monitoring 4. PPE | 1. BIP-COP-001 |  | 9.75 | 25 |  |  |  | x | x
4 | Nature | Siding Electrical | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Working in the veldt | Source: Spiders and insects Exposure: Been bitten by | Outcome: Poison of the human body Consequences: Possible - fatality / Serious injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Risk assessment for veld work 2. Awareness 3. Buddy System 4. PPE 5. On-site paramedics |  |  | 4.25 | 75 |  |  | x | x | x
5 | Nature | Siding Electrical | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Unprotected / no protection / exposure | Source: Extreme weather conditions Exposure: Extreme heat or cold | Outcome: Health risk Consequences: Possible - Hypertension / freeze | x |  |  |  | x | [7 empty] | x | 16 | MHS Act, Reg. 9.2 & Mandatory COP | 1. COP for Thermal Stress 2. Inclement weather SOP 3. PPE | 1. BIP-COP-004 |  | 12 | 25 |  |  |  | x | x
6 | Nature | Siding Electrical | None | Any / All outdoor activities | x |  | Employees, Supervisors, Management. | Unprotected / no protection / exposure | Source: rain Exposure: Slippery surfaces | Outcome :Slip and fall Consequences: Possible - Personal Injury | x |  |  |  | x | [7 empty] | x | 16 | None | 1. Emergency COP 2. Risk Assessments 3. Awareness Training | 1. BIP-COP-010 |  | 13.6 | 15 |  |  |  | x
1 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorised Artisan | Failure to isolate, lockout, test and tag, obtain permit. | Source: Contact with electrified structures, components or equipment Exposure: Heat | Outcome :arcing/electrocution Consequences: Possible - fatality/injury | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 20.4 / 20.5 / 21.6.1 | 1. Isolation and Lock-out CoP 2. Disciplinary Code 3.Competent artisans and supervisors 4.Personal locks Permit system 5. VFL
2 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: damage to switchgear and cables Exposure: Electrical flashover | Outcome :Electrocution Consequences: Possible - Personal Injury/fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | MHS Act, Reg. 21.3.1 | 1. Isolation and Lock-out CoP 2. Disciplinary Code 3.Competent artisans and supervisors 4.Personal locks Permit system 5. VFL
3 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: short-circuiting / flashover Exposure: Heat | Outcome :Electrical fires Consequences: Personal Injury/ burn wounds/fatality | x | [5 empty] | x |  |  |  | x |  |  | 18 | MHS Act, Reg. 21.6.1 | 1. Isolation and Lock-out CoP 2. Disciplinary Code 3.Competent artisans and supervisors 4.HIRA 5. VFL
4 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Struck by/trapped under - failure of structure Exposure: Unstable, unsecure structure | Outcome :Broken bones/ neck Consequences: Possible - fatality/injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | None | 1. Hazard identification training 2. VFL 3. Structural design criteria 4. Construction based on design criteria
5 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Falling from heights - ladders Exposure: Falling from heights | Outcome :Broken bones/ neck Consequences: Possible - fatality/injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | OHS Act, GSR 6 & CR 8 | 1. Fit for purpose ladders 2. Working at heights CoP and standard 3. Permit system 4. Buddy system 5. VFL 6. Competent supervisors and artisans
6 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Contact with exposed wires - electrocution Exposure: Heat | Outcome :Burn wounds Consequences: Possible - fatality/injury | x | [6 empty] | x |  |  |  | x |  | 24 | None | 1. CoP Isolation and lockout 2. PPE 3. VFL 4. Hazard identification training 5. Sleeved connections
7 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Failure to wear PPE when working with high mast lights Exposure: Sharp edges | Outcome :Finger cuts Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Disciplinary code 2. Free issue, job specific PPE 3. Competent artisans and supervisors 4. VFL 5. Hazard identification training 6. HIRA
8 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Replacing lights | Source: Contact with broken glass Exposure: Sharp edges | Outcome :Finger cuts Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None | 1. Free issue, job specific PPE 3. Competent artisans and supervisors 4. VFL 5. Hazard identification training 6. HIRA
9 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Caught in/between moving parts Exposure: Moving parts | Outcome :Finger cuts Consequences: Possible - Injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 20.4 / 20.5 | 1. Machine and related guarding 2. Approved tools and equipment 3. Hazard identification training 4. VFL 5. Trained and competent artisans and supervisors
10 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Caught/trapped between parts e.g. cable/winch drum Exposure: Moving parts | Outcome :Body cuts Consequences: Possible - Serious Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | MHS Act, Reg. 20.4 / 20.5 | 1. Machine and related guarding 2. Approved tools and equipment 3. Hazard identification training 4. VFL 5. Trained and competent artisans and supervisors
11 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Unauthorised alterations/modifications on circuitry - Exposure: Heat | Outcome :fire/explosion Consequences: Possible - fatality/injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.4 | 1. Disciplinary Code 2. Circuit design criteria 3. Fire fighting CoP 4. VFL 5. HIRA 6. Hazard identification training 7. Trained and competent supervisors and artisans
12 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Absenteeism - Working alone Exposure: Lack of knowledge | Outcome :fire/explosion Consequences: Possible - Serious Injury | x |  |  |  |  | x | [5 empty] | x |  | 17 | None | 1. Buddy system 2. Refusal to conduct dangerous work CoP
13 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Inspection, repair, replacing lights and maintenance | Source: Not authorised artisan Exposure: Lack of knowledge | Outcome :fire/explosion Consequences: Possible - fatality/injury | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 | 1. Disciplinary Code 2. Trained and competent supervisors and artisans 3. Access control to facilities VFL
14 | Functional | Siding Electrical | Electricity | Installation/Inspection /Maintenance | x |  | Authorized Artisan | Lock out procedure | Source: Accidental/inadvertent start up Exposure: Electricity | Outcome :fire/explosion Consequences: Possible - fatality/injury | x | [5 empty] | x |  |  |  |  | x |  | 21 | MHS Act, Reg. 20.4 / 20.5 / 21.6.3 | 1. Isolation and lockout CoP 2. Permit system 3. Personal locks 4. Inspections and over inspections 5. VFL Multi port lockout devices
1 | Equipment, Material & Substances | Siding Electrical | Hand tools (screw driver / wrench / hammer / pliers) | Any Related Activity | x |  | Artisan /Artisan assistant | N/A | Source: Struck by / trip & fall / in contact with / fall onto Exposure: Struck by / trip & fall / in contact with / fall onto | Outcome :Body Harm Consequences: Possible - Personal injury/fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Risk Assessments & Mini-HIRA 2. Competent and trained workers 3. Tool carry bags 4. Housekeeping 5. PPE 6. VFL 7. Awareness training |  |  | 16.5 | 25 |  |  |  | x | x
2 | Equipment, Material & Substances | Siding Electrical | Hand tools - Stanley knife | Any Related Activity | x |  | Artisan /Artisan assistant | N/A | Source: Wrong use of equipment Exposure: Cutting towards body | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
3 | Equipment, Material & Substances | Siding Electrical | Hand tools - Stanley knife | Any Related Activity | x |  | Artisan /Artisan assistant | N/A | Source: Careless handling of blades Exposure: Sharp edges | Outcome :Body cuts Consequences: Possible - Personal injury | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | None
4 | Equipment, Material & Substances | Siding Electrical | Testing Apparatus | Any Related Activity | x |  | Artisan /Artisan assistant | N/A | Source: Contact with electricity - electrocution - Multi-meter failure Exposure: Electricity | Outcome :Electrocution Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
5 | Equipment, Material & Substances | Siding Electrical | PPE | Any Related Activity | x |  | Artisan /Artisan assistant | N/A | Source: Failure to wear PPE Exposure: Chemicals, sharp edges, handling material | Outcome :Injuries to body part Consequences: Possible - Injury/ fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None
1 | General / Other | Siding Electrical | Operation of vehicles, power tools, Scaffolding | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Fatigue | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. COP for fatigue 2. Awareness Training | 1. BIP-COP-007 |  | 18.7 | 15 |  |  |  | x
2 | General / Other | Siding Electrical | Operation of vehicles, power tools | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Judgement error | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competent and Trained employees and supervisors 2. Risk assessments 3.Awareness Training 4. VFL 5.PTO |  |  | 18.7 | 15 |  |  |  | x
3 | General / Other | Siding Electrical | Operation of vehicles, power tools, Erecting Scaffolding | Operation / use | x |  | Employees, Artisans, Supervisors, Management. | Operation / use | Exposure: Incompetency | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Pre-screened employees 2. Competency/Training certificates 3. Risk assessments 4. Awareness Training 5. PTO's 6. VFL 7. Contractor Management SOP | 7. BIP-SOP-SHE.007 |  | 18.7 | 15 |  |  |  | x
4 | Employee working alone - General / Other | Siding Electrical | None | Work | x | x | Employee - (Male / Female) | Any work related tasks - During ordinary working hours | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Possible - Physical / sexual assault, serious personal injuries that may escalate to a signal fatality. | x | [6 empty] | x |  |  | x |  |  | 22 | DMR Instruction | 1. Emergency COP 2. Buddy system 3. Risk assessment 4. Communication system | 1. BIP-COP-010 |  | 18.7 | 15 |  |  |  | x
5 | General / Other | Siding Electrical | Any | Work | x |  | Employees, Artisans, Supervisors, Management. | Not following Safe work procedures | Exposure: At risk behaviour | Possible - Incident leading to personal injuries. Medical treatment, escalating to a serious incident that may escalate to permanent disability or a single fatality | x | [6 empty] | x |  |  | x |  |  | 22 | None | 1. Competency Training 2. Risk assessments 3. Awareness Training 4. PTO's 5. VFL 6. Disciplinary code |  |  | 18.7 | 15 |  |  |  | x