## WBC (hidden)
INSTRUCTIONS: | [7 empty] | Legal and Other Requirements | System Reference |  |  | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
Open Master Workbook | [8 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  |  |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
First: select Excel Workbook to be used. | [7 empty] | Legal Reference | Operational Controls Description | Operational Controls Reference | Management Programme |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
Second: select Module1.bas
Click button to start:
If you click save and the message "The following features cannot be saved in macro-free workbooks:" click YES
CONTROL SHEET FOR VARIABLES (If any of the values below are different, call Len)
Risk Matrix Column Start: | A | 1
Risk Matrix Column End: | H | 8
Risk Matrix Row Start: | 10
Risk Matrix Row End: | 14
Risk Matrix Name: | RiskMatrix
Starting Row: | 4
Ending Row: | 131
Scoring on Risk rating Column: | AA | 27
Scoring on Risk rating Name: | RawRiskClm
Scoring on Risk rating Formula:
Risk Reduction Rating Column: | AF | 32
Risk Reduction Rating Name: | RawReductClm
Risk Reduction Rating Formula:
Risk Control Measure Rating Column: | AG | 33
Risk Control Measure Rating Formula:
Likelihood |  | (Consider near hits as well as actual events) | Risk Rating
5 | (Almost Certain) | The unwanted event has occurred frequently; occurs in order of one or more times per year & is likely to reoccur within 1 year | 11 (M) | 16 (H) | 20 (H) | 23 (Ex) | 25 (Ex)
4 | (Likely) | The unwanted event has occurred infrequently; occurs in order of less than once per year & is likely to reoccur within 5 years | 7 (M) | 12 (M) | 17 (H) | 21 (Ex) | 24 (Ex)
3 | (Possible) | The unwanted event has happened in the business at some time; or could happen within 10 years | 4 (L) | 8 (M) | 13 (H) | 18 (H) | 22 (Ex)
2 | (Unlikely) | The unwanted event has happened in the business at some time; or could happen within 20 years | 2 (L) | 5 (L) | 9 (M) | 14 (H) | 19 (H)
1 | (Rare) | The unwanted event has never been known to occur in the business; or it is highly unlikely that it will occur within 20 years | 1 (L) | 3 (L) | 6 (M) | 10 (M) | 15 (H)
(Ex) – Extreme | 21 | RiskEX
(H) – High | 13 | RiskH
(M) – Medium | 6 | RiskM
(L) – Low | 1 | RiskL
Process Excel Workbook

## Scoring on Risk rating
EXXARO SHEC Risk Matrix by Functions |  |  | Hazard Effect / Consequence Where an event has more than one “Loss Type; choose the ‘Consequence’ with the highest rating)
Impact |  |  | 1 Negligible | 2 Moderate | 3 High | 4 Major | 5 Extreme
Harm to People (S ) |  |  | First aid case / | Medical treatment case | Lost time injury / Loss of shift or hospitalisation however with reversible loss of quality of life | Lost time injury / Irreversible Loss of quality of life | Single and/or Multiple fatalities
Health (H) |  |  | Medical monitoring variance [where deviations are identified through medical screening] | Temporary accommodate [where an employee cannot resume their normal or similar work duties for less than 4 days] | Temporary disability / Lost Time Illness [where an employee cannot resume their normal of similar work duties for 4 or more days] | Permanent disability resulting in irreversible loss of quality of life | fatality / Multiple permanent disability [where a fatality occurred directly linked to an occupational disease or a permanent change in occupation or work area]
Hygiene (HY) |  |  | Exposure ≥ 10% of OEL | Exposure between 10% and 50% of OEL | Exposure between 50% and 100% of OEL | Exposure exceeding OEL | Acute exposure ≥ double the OEL
Environmental Impact (E) |  |  | Minimal environmental harm L1 incident | Moderate environmental effect / short term reversible ecological disturbance – L2 incident Remediable short term within LOM | Significant reportable environmental harm with reversible ecological damage L2 incident Remediable within LOM | Major environmental harm with long term irreversible ecological damage L2 incident Remediable post LOM (Life of Mine) Minor adverse local/public/ media attention and complaints. | Extreme environmental harm Irreversible ecological damage L3 incident Serious national public media outcry
Business Interruption / Material Damage & Other Consequential Losses |  |  | Negligible or minor or superficial damage / business interruption to facility resulting in production losses of less than 1 week. | Moderate damage / business interruption to facility resulting in production losses for a period of 1 to 2 weeks at. | Major damage/ business interruption to facility resulting in production losses for a period of 2 to 3 weeks | Future operations significantly affected by production losses for a period of 3 to 4 weeks | Total loss of production / Future operations untenable for a period of more than a month.
Impact on Reputation / Social / Community (C) |  |  | Minor adverse attention and complaints from authorities, affected and interested parties | Adverse attention and complaints from authorities, affected and interested parties (district level) | Significant adverse attention and complaints from authorities, affected and interested parties (district & regional level) | Major adverse attention and complaints from authorities, affected and interested parties that can lead to revoking of mining right and/or negative JSE/SRI rating (National level) | Extreme adverse attention and complaints from authorities, affected and interested parties that lead to revoking of mining right and negative JSE/SRI rating
Likelihood |  | (Consider near hits as well as actual events) | Risk Rating
5 | (Almost Certain) | The unwanted event has occurred frequently; occurs in order of one or more times per year & is likely to reoccur within 1 year | 11 (M) | 16 (H) | 20 (H) | 23 (Ex) | 25 (Ex)
4 | (Likely) | The unwanted event has occurred infrequently; occurs in order of less than once per year & is likely to reoccur within 5 years | 7 (M) | 12 (M) | 17 (H) | 21 (Ex) | 24 (Ex)
3 | (Possible) | The unwanted event has happened in the business at some time; or could happen within 10 years | 4 (L) | 8 (M) | 13 (H) | 18 (H) | 22 (Ex)
2 | (Unlikely) | The unwanted event has happened in the business at some time; or could happen within 20 years | 2 (L) | 5 (L) | 9 (M) | 14 (H) | 19 (H)
1 | (Rare) | The unwanted event has never been known to occur in the business; or it is highly unlikely that it will occur within 20 years | 1 (L) | 3 (L) | 6 (M) | 10 (M) | 15 (H)
Risk Rating |  | Risk Level | Guidelines for Risk Matrix
21 to 25 |  | (Ex) – Extreme | Eliminate, avoid, implement specific action plans/procedures to manage & monitor
13 to 20 |  | (H) – High | Proactively manage
6 to 12 |  | (M) – Medium | Actively manage
1 t0 5 |  | (L) – Low | Monitor & manage as appropriate

## Sheet1
BELFAST IMPLEMENTATION PROJECT
EXXARO
COMPILED BY: |  |  |  | ACCEPTED AND APPROVED BY:
TITLE | SIGNATURE |  |  | TITLE | SIGNATURE |  | DATE
Daniell Prinsloo |  |  |  | John Thom
RECOMMENDED BY:
TITLE | SIGNATURE
Deon van Zyl
DOCUMENT PROPERTIES
Project / Contract Number |  | Knowledge Area |  | Document Type |  | Doc Control No
ECC-000004 |  | Risk Management | RIS | Guideline | #REF! | ECC-000004-0000-AAA00-SHE-RIS-0002
Project WBS
[7 empty] | Version: | 1

## Traffic Management HIRA
Baseline Trackless Mobile Machinary Risk Assessment
HS Nr | Category | Geographical Area | Equipment / Material / Substances | Activities | Activity Type |  | Process / Task | Hazard | Risk | Impact To: |  |  | Hazard Effect / Consequence |  |  |  |  | Likelihood |  |  |  |  | Raw Risk Rating | System and Legal Reference | RISK REDUCTION RATING | Risk Reduction Hierarchy | Elimination | Substitution | Engineering Controls Controls at Source | Administrative Controls | Personal Protective Equipment
[24 empty] | Mitigation, Projects, Safety Measures, Guards and Procedures |  | Risk Control Measure rating | 1 | 2 | 3 | 4 | 5
[5 empty] | Routine | Non Routine |  |  |  | Safety | Health | Environment | 1.Negligible | 2 . Moderate | 3 . High | 4 . Major | 5 . Extreme | 1.(Rare) | 2.(Unlikely) | 3.(Possible) | 4.(Likely) | 5.(Almost Certain) |  | Controls Description |  | Sum of = | 100% Elimination | 80% Substitution / Replace / Change | 50% Barriers; Guards; Safety Devices; Emergency stops; | 15% Signage; Warnings; Safe Operating Procedures; Instructions; Training; | 10% Gloves; Safety Glasses; Safety Shoes; Ear Protection;
1 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity on National Roads | x |  | License, Registration, Authorisation | Source: Vehicle / Driver / Operator Registration and Licensing Exposure: Expired Registration or License | Outcome: Traffic Fine / Vehicle/plant Unroadworthy / Stop Use / Impounded Consequences: Financial Fine / Legal Liability | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act, Sec 4, 12; CoP TMM, Traffic Management Plan, Awareness Training, Induction | 10.2 | 15 |  |  |  | x
2 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Vehicle Maintenance - (Roadworthiness; services; functioning of lights/brakes; tires) | x |  | Driving / Operating Properly Maintained Vehicle / Equipment | Source: Unroadworthy vehicle; Worn tires; Worn shocks; Malfunctioning of lights/brakes. Exposure: Unable to stop timeously; Unable to give indication of actions. | Outcome: May lead to Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Imprisonment | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, CoP TMM, Traffic Management Plan, Security inspections, Valid Vehicle licenses. | 20.4 | 15 |  |  |  | x
3 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Adherence to National Road Traffic Act - Speed Limit / Road Signs / Restrictions | Source: Driver / Operator Competency & Behaviour Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, Sec CoP TMM, Traffic Management Plan, Road signs, Vehicle/plant separation, demarcated travel/work areas. Valid relevant drivers license for class of vehicle | 20.4 | 15 |  |  |  | x
4 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Adherence to National Road Traffic Act - Passenger Transportation (PDP, Own seat with safety belt) | Source: Driver / Operator without PDP, Vehicle insufficient for passenger transportation Exposure: Lack of PDP License and Registration / Passengers unsecure / Illegal transportation of Passengers | Outcome: Traffic Violations / Vehicle accident(passengers flung from vehicle) / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | National Road Traffic Act, CoP TMM, Valid relevant drivers license for class of vehicle, Conducting inspections on all PDP requirements. Induction. | 8.4 | 65 |  |  | x | x
5 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Adherence to Traffic Management Plan | Source: Driver / Operator Competency & Behaviour / Lack of Enforcement/Discipline Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | Traffic Management Plan, Road signs, Vehicle/plant separation, demarcated travel/work areas. All driver/operators to complete Trackless Mobile equipment induction. Planned Task Observations, Visible Felt Leadership. Supervision. | 20.4 | 15 |  |  |  | x
6 | Legal | BIP - Project | All Abnormal / Oversize Mobile Equipment / Transportation / Vehicles | Abnormal Load Clearance and Notification | x |  | Abnormal Load Driving / Operating | Source: Route Not Authorised / Lack of Notification Exposure: Unable to transport | Outcome: Delay in logistics, Traffic Fine Consequences: Delay in Project, Financial Loss | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act, All contractors to ensure that authorisation from relevant departmental documentation is available. | 10.2 | 15 |  |  |  | x
8 | Legal | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity on National Roads | x |  | Vehicle Insurance / Third party Insurance / Employee Insurance (COID) | Source: Vehicle / Driver / Operator Insurance Liability Cover Exposure: Lack of or lapsed insurance policy or Letter of Good Standing | Outcome: Personal Injury Claim / Injury on duty claim / Damaged Equipment / Vehicle Consequences: Financial Loss / Legal Liability / Civil Claim | x |  |  |  | x | [6 empty] | x |  | 12 | National Road Traffic Act, COID Act. All contractors to submit proof of Legal Liability cover at contactor on-boarding process. | 10.2 | 15 |  |  |  | x
Any
1 | Geographical | BIP - Project - Access Gates / Booms | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Driving / Operating Trackless Mobile Equipment / Vehicles / Transportation | Source: Close proximity to other vehicles, equipment, structures, pedestrians / Perform Security Access Control Exposure: Struck by, Contact with, Caught between / Unauthorised Access / Intoxicated Driver / Operator | Outcome: Vehicle Accident / Unauthorised Entry / Environmental Impact Consequences: Injuries, Single or Multiple Fatalities / Legal Liability / Theft | x | [6 empty] | x |  |  | x |  |  | 22 | National Road Traffic Act, Sec 54, 55; MHS Act, Sect. 21 OHS Act, Sect 10 OHS Act, GSR 4 CoP TMM, Traffic Management Plan, People/Plant/vehicle and equipment according to Traffic Management plan. Road signs, Flag men, Access control. Intoxication tests, Spotter to be in pace where People and Plant interact. Clearly demarcated walkways. No operator to operate TMM within 1m of any structure without having a spotter to ensure that the TMM does not come in to contact with any structure. | 7.7 | 65 |  |  | x | x
2 | Geographical | BIP - Project - Waiting / Parking Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Driving / Operating Trackless Mobile Equipment / Vehicles / Transportation | Source: Close proximity to other vehicles, equipment, structures, pedestrians / Failure to observe / Failure to adhere to mandatory signage and traffic rules Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | Separation of People/Plant/vehicle and equipment according to Traffic Management plan. Road signs, Flag men, Access control. Intoxication tests, Spotter to be in pace where People and Plant interact. Clearly demarcated walkways. No operator to operate TMM within 1m of any structure without having a spotter to ensure that the TMM does not come in to contact with any structure. Supervision. 2-way radio communication. | 4.55 | 65 |  |  | x | x
3 | Geographical | BIP - Project - Delivery / Loading Zones | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Loading of Material / Equipment / Substances | Source: Interaction between different class mobile equipment / transportation / vehicles. Loading - Heavy Loads Exposure: Right of way / Speeding / Struck by | Outcome: Vehicle Accident / Over exertion / Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability |  | x |  |  |  | x | [5 empty] | x |  | 17 | CoP TMM, Traffic Management Plan, Traffic and other symbolic signs, Separation of People/Plant/vehicle and equipment according to Traffic Management plan. Flag men, General site induction. 2-way Radio communication. Supervision. | 5.95 | 65 |  |  | x | x
4 | Geographical | BIP - Project - Stockpile Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Building and removing Material from Stockpiles | Source: Interaction between mobile equipment / Failure of Stockpile. Exposure: Right of way / Speeding / Collision / Engulfed. | Outcome: Collision / Overturn Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability |  | x | [5 empty] | x |  |  |  | x |  | 24 | Safety Berms, Road width and road way construction and stockpile design. Traffic Management Plan. Issue based Risk Assessment for stockpiling of spoil and top soil. Competent operator, Symbolic Signs. Planned Task Observations. | 12 | 50 |  |  | x
5 | Geographical | BIP - Project - Laydown Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Off-Loading of Material / Equipment | Source: Interaction between Delivery Vehicles / Trucks; Heavy Materials / Equipment; Lifting Operations. Exposure: Caught Between, Under, Struck by, with / Collapse | Outcome: Collision / Contact / Engulf Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x | [6 empty] | x |  |  | x |  |  | 22 | CoP TMM, Traffic Management Plan, Traffic and other symbolic signs, Separation of People/Plant/vehicle and equipment according to Traffic Management plan. Flag men, General site induction. 2-way Radio communication. Supervision. Permit to work. During lifting operations areas to be demarcated. | 11 | 50 |  |  | x
7 | Geographical | BIP - Project - Bus/Taxi/ Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Transportation of Passengers | Source: Congestion of vehicles / Travelling within close proximity to other vehicles, equipment, structures, pedestrians Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Damage to Property / Legal Liability | x | [6 empty] | x |  |  | x |  |  | 22 | CoP TMM, Traffic Management Plan, Demarcated areas, Traffic and other symbolic signs, Demarcated walkways. Valid Drivers License and authorisations. Induction. Security inspections, BIP SHE Plan with regards to transporting employees to/on and from workplace. | 11 | 50 |  |  | x
9 | Geographical | BIP - Project - Dedicated Travel Ways | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Adherence to Designated Travel Ways | Source: Congestion of vehicles / Travelling within close proximity to other vehicles, equipment, structures, pedestrians Exposure: Struck by, Contact with, Caught between | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | CoP TMM, Traffic Management Plan, People/Plant/vehicle and equipment according to Traffic Management plan. Road signs, Flag men, Access control. Supervision. | 7.7 | 65 |  |  | x | x
10 | Geographical | BIP - Project - Adjacent Activities | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Adjacent Work Activities - Any work related activities performed by employees or other contractors | Source: Unknown Operations/Activities; Dust, Noise Exposure: Emergency Event; Flying debris | Serious injury or possible multiple fatalities; Property damage. |  | x | [5 empty] | x |  |  |  | x |  | 24 | Permit to work, Integration between contractors. Areas to be clearly demarcated. Site Specific Induction. Symbolic Signs. Daily continues Risk Assessment Process | 20.4 | 15 |  |  |  | x
11 | Geographical | BIP - Project - Road Signs / Demarcation | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Road Signs / Demarcation | Source: Driver / Operator Competency & Behaviour / Lack of Signage/Enforcement/Discipline Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | Traffic Management Plan, People/Plant/vehicle and equipment separation according to Traffic Management plan. Road and symbolic signs according to the Traffic management Plan, Flag men, Supervision. | 7.7 | 65 |  |  | x | x
13 | Geographical | BIP - Project - Road Surface - Tar | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Travelling on Tar Road Surfaces | Source: Driver / Operator Competency & Behaviour / Lack of Signage/Enforcement/Discipline Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking | Outcome: Traffic Violations / Vehicle accident / Negligence or Culpable Homicide Liability Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | National Road Traffic Act, Valid relevant drivers license for class of vehicle, Awareness training. | 7.7 | 65 |  |  | x | x
14 | Geographical | BIP - Project - Road Surface - Gravel Construction / Site Roads | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Travelling on Gravel/Dirt road and construction Roads Surfaces | Source: Driver / Operator Competency & Behaviour / Lack of Signage/Enforcement/Discipline, Loose Gravel/Sand Exposure: Not Yet Competent Driver / Operator, At Risk Behaviour / Unauthorised Operations / Speeding / Overtaking / Loss of Control / Dust | Outcome: Traffic Violations / Vehicle accident / Overturning Vehicle / Collision Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | Traffic Management Plan, Demarcated areas, Traffic and other symbolic signs. | 7.7 | 65 |  |  | x | x
18 | Geographical | BIP - Project - Overhead Power Lines | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Travelling Under / Close Proximity to Overhead Power Lines | Source: Unauthorised Access; Exceeding the high restriction; Overhead Electrical Lines Exposure: Incompetency; Electricity; Contact with | Outcome: Contact with Electrical Line / Electrocution Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  | x |  |  | 22 | CoP TMM, Traffic Management Plan, Demarcated areas, Permit System, Dummy Bars, adherence to Eskom permit conditions. | 11 | 50 |  |  | x
19 | Geographical | River Crossing / Bridges | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Travelling Through/Over River Crossings/Bridges | Source: Flooded river / stream / mudslide / Uprooted trees Exposure: Trapped in, Caught in, Stuck, Struck by | Outcome : Blocked roads / Vehicle Accident / Drowning Consequences: Loss of Production / Property Damage /Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | Hazard Awareness Training. Symbolic Signs. Weather Station. | 18.7 | 15 |  |  |  | x
22 | Geographical | Unauthorised Access - Pedestrians / Vehicles | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Security Access Control | Source: Lack of Access Control / Not adhering to traffic management plan Exposure: Un-Authorised Access; Unlicensed Operators / Drivers; Speeding; Un-Authorised Pedestrians on site | Outcome: Unauthorised Driver / Operator performing activities on site / Pedestrians on site Consequences: Environmental Financial Fine / Production Loss / Legal Liability | x |  |  |  |  | x | [5 empty] | x |  | 17 | Full time access control. | 5.95 | 65 |  |  | x | x
23 | Geographical | Ramps / Platforms | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Driving on Ramps / Platforms | Source: Failure to observe / Failure to adhere to mandatory signage and traffic rules / Failure to adjust Speed Exposure: Contact with, Overturn, Gravity/Momentum | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  |  | x |  | 24 | Ramp and platform designs, Safety Berms, Trained and Competent Operators/drivers. | 8.4 | 65 |  |  | x | x
25 | Geographical | Brake Test Ramp | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Perform Brake Ramp Tests | Source: Failure to observe / Failure to adhere to mandatory signage and Brake Test Ramp Procedure / Failure to adjust Speed or apply Brakes Exposure: Contact with, Overturn, Run-away Vehicle due to Gravity/Momentum | Outcome: Failure of Brakes / Vehicle accident / Collision / Loss of Control Consequences: Financial Fine / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | Vehicle servicing and maintenance schedules including record keeping thereof, Pre-use inspections, Supervision. Dynamic brake testing to be done prior to perform brake test on brake test Ramp. | 7.7 | 65 |  |  | x | x
26 | Geographical | Road Intersections | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Crossing Intersections / Slipways / T-Junctions | Source: Failure to observe / Failure to adhere to mandatory signage and traffic rules / Failure to adjust Speed/Stop Exposure: Contact with, Speeding Vehicles | Outcome: Vehicle accident / Collision / Loss of Control Consequences: Property Damage / Legal Liability / Single or Multiple Fatalities | x | [6 empty] | x |  |  | x |  |  | 22 | Road Signs, Trained and Licenced operators, COP TMM, Traffic Management Plan. Induction. Flagmen | 7.7 | 65 |  |  | x | x
27 | Geographical | BIP - Project - Remote Off-Road Areas | All Mobile Equipment / Transportation / Vehicles | Traffic Management - Driving / Operating / Transporting | x |  | Driving in Remote Areas / Any isolated work related tasks - During ordinary or after working hours | Being attacked by someone - Intruder / Robber / fellow employee - person with devious plans. Employee being injured and cannot call for help / assistance. Being exposed to an emergency situation. Be exposed to a personal medical condition.. | Physical / sexual assault, serious personal injuries that may escalate to a single fatality. | x | [5 empty] | x |  |  |  | x |  |  | 18 | Buddy System, Lockable vehicle doors, Roll-up windows, on-site communication | 6.3 | 65 |  |  | x | x
Any
1 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Sun Direction related to Travel Direction | Source: Sun Exposure: Blinding of Vision | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | PPE , vehicle sun visors. | 9.6 | 60 |  |  | x |  | x
2 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Rain Causing Wet Slippery Road Surface | Source: Rain - Slippery road conditions Exposure: Loss of Control / Spinning / Sliding | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | Road maintenance, vehicle maintenance schedule including tyre checks, pre-use inspections. Operating speed to be reduced according to road condition. | 8.4 | 65 |  |  | x | x
3 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Poor / Obscured Vision due to Heavy Mist / Rain | Source: Mist / Rain - Exposure: Obscured Vision - Loss of Control / Incorrect Steering Direction | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | Strobe light always on while driving on-site, reduced speed , Supervision, | 20.4 | 15 |  |  |  | x
4 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Driving / Operating Related Activity | x |  | Poor / Obscured Vision due to Dust | Source: Heavy Dust - Lack of Dust Suppression Exposure: Obscured Vision - Loss of Control / Incorrect Steering Direction | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | Dust control, designed roads, reduced speed limit 40km/h maximum. Supervision | 12 | 50 |  |  | x
6 | Natural | BIP - Project - All Roads | All Mobile Equipment / Transportation / Vehicles | Any Night Time Driving / Operating Related Activity | x |  | Darkness / Poor Vision | Source: Night Operations / Activities Exposure: Poor Vision - Loss of Control | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | Reflective clothing, demarcated walkways, headlights on plant and vehicles, maintenance schedules for plant and vehicles, CoP TMM, Traffic Management Plant. | 6 | 75 |  |  | x | x | x
3 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Adherence to Designated Travel Ways / Route per Classification (LDV, Bus, Taxi, Trucks, Heavy Mobile Equipment, TLB, etc.) | Source: Interaction between different class mobile equipment / transportation / vehicles. Exposure: Right of way / Speeding / Collision. | Outcome: Vehicle Accident Consequences: Injuries, Single or Multiple Fatalities / Legal Liability Prosecution, Exxaro Reputation, 3rd Party Claims | x | [6 empty] | x |  |  | x |  |  | 22 | MHS Act, Reg. 21.2 Traffic Management Plan, Trained and Competent Drivers and Operators, Site specific operator and driver evaluation, Pre-selection criteria of TMM operators | 18.7 | 15 |  |  |  | x
4 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Travel times | Source: Fatigue / Exceeding the speed limit / Sun direction / Traffic volume Exposure: Falling Asleep / Speeding / Traffic violations / Collision | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 21.6.1 Travel Policy, Fatigue Management CoP and Plan,TMM licensing authorization | 20.4 | 15 |  |  |  | x
5 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Mental / Physical Health | Source: Driving when tired / Medication effects; Exposure: Falling asleep whilst driving or feeling drowsy | Outcome: Vehicle accident / Collision With Consequences: Injuries, serious injuries, disabling injuries, single and/or multiple fatalities / Damage to Property / Equipment | x | [6 empty] | x |  |  | x |  |  | 22 | Travel Policy, Fatigue Management CoP and Plan, Medical | 18.7 | 15 |  |  |  | x
6 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Travel Routes | Source: Hi-jackers / Obstructed roads / Road conditions / Remote location Exposure: Armed hi-jacking / Armed Protesters / Potholes, Road works | Outcome : Theft / Personal Assault / Collision with/ Lack of Assistance Consequences: Property Loss / Damage to Property / Serious injuries/Fatality | x | [6 empty] | x |  |  | x |  |  | 22 | Travel Policy, pre-determined routes, lockable vehicle doors and roll-up windows | 7.7 | 65 |  |  | x | x
7 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Perform Pre-Use Inspection | Source: Non Adherence to perform Pre-use Inspection on Vehicle / TMM Exposure: Cause an accident / Loss of Control / Oils and Substances | Outcome: Vehicle breakdown due to mechanical failure or flat tyre / Damaged vehicles performing activities on site / Environmental Impact through Substance leaks/spills Consequences: Environmental Financial Fine / Production Loss / Legal Liability | x |  | x |  |  | x |  |  |  |  | x |  |  | 13 | Pre-use inspections, scheduled and recorded maintenance, | 11.05 | 15 |  |  |  | x
8 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Transportation of Passengers - Driver Competency / Authorisation / Licencing | Source: PDP (licensing of vehicle and license of driver) Exposure: Driving without the correct licensing | Outcome: Traffic Fine / Unauthorised Driver / Suspended Transportation / Vehicle Impounded Consequences: Financial Fine / Production Loss / Legal Liability | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | PDP Requirements, Licenced Drivers, TMM CoP, Traffic Management plan | 11.05 | 15 |  |  |  | x
9 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Transportation of Passengers - Passenger Requirements (Each passenger to be secured by own safety belt) | Source: Not wearing a set belt; Seat and Safety belt not available Exposure: Unprotected movement of persons. | Minor injuries; Cuts and lacerations that may escalate to more serious injuries and even multiple fatalities. | x | [6 empty] | x |  |  | x |  |  | 22 | Vehicles are equipped with safety belts, CoP TMM, Induction | 7.7 | 65 |  |  | x | x
10 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Transportation of Material / Equipment / Goods | Source: Weight; Shape; Centre of gravity; Movement; Hazardous substances (radio active material). Exposure: Ergonomics; Caught under; Caught in between; Struck by; Exposure to hazardous substances (radio active material); Spills; Dropping of material/equipment. | Cuts; Lacerations; Sprains; Back injuries; Fractures; Hazardous Substance exposure. | x |  | x |  |  | x |  |  |  |  | x |  |  | 13 | Tie down straps, Trained and competent drivers and operators, | 4.55 | 65 |  |  | x | x
11 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Transportation of Hazardous Substances | Source: Refuelling / Raptured of Vessel / Overflow Exposure: Oil / Hazardous Substance Leaks / Emissions / Spillages | Outcome : Soil Contamination / Air Pollution / Rehabilitation Consequences: Environmental Fine or Prosecution / Emotion Taxes / Rehabilitation Costs |  |  | x |  |  | x |  |  |  |  | x |  |  | 13 | OHS Act, GSR 6 & CR 8 Fit for purpose transport, CoP TMM,SOP for refuelling of TMMs. Spill Kit to be available. | 5.2 | 60 |  |  | x |  | x
15 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Use of mobile phones while driving | Source: Mobile phone; Exposure: Use of mobile phone whilst driving | Loss in focus can result in accident causing personal injuries even fatality | x | [6 empty] | x |  |  |  | x |  | 24 | MHS Act, Reg. 20.4 / 20.5 / 21.6.2, Road Traffic Act, DMR Instruction, Self Discipline. Induction | 20.4 | 15 |  |  |  | X
24 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Parking | Source: Vehicle not parked in designated parking area Exposure: Vehicle can roll out of control | Property damage even injury to people in the area | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | Traffic Management Plan , dedicated parking areas, Disciplinary Code | 11.05 | 15 |  |  |  | x
25 | Functional | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Shutting Off / Isolation / Lock-Out | Source: Vehicle not shut off, isolated or locked out as required Exposure: Vehicle start, move, operate out of control / Unauthorised use | Property damage even injury to people in the area | x |  |  |  |  | x |  |  |  |  | x |  |  | 13 | MHS Act, Reg. 21.6.1 Lock out procedure, personal lock issues, CoP TMM, Key control. | 11.05 | 15 |  |  |  | x
1 | Equipment/Material/ Substances | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Vehicle Maintenance Schedule | Source: Unroadworthy vehicle; Worn tires; Warn shocks; Malfunctioning of lights/brakes. Exposure: Unable to stop timeously; Unable to give indication of actions. | Outcome :Body Harm Consequences: Personal injury/fatality | x |  |  |  | x | [7 empty] | x | 16 | Scheduled and recorded maintenance, Disciplinary Code | 13.6 | 15 |  |  |  | x
2 | Equipment/Material/ Substances | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Emissions / Fluids / Hazardous Substances | Source: Refuelling / Raptured Pipeline / Overflow Exposure: Oil / Hazardous Substance Leaks / Emissions / Spillages | Outcome : Soil Contamination / Air Pollution / Rehabilitation Consequences: Environmental Fine or Prosecution / Emission Taxes / Rehabilitation Costs |  |  | x |  |  | x |  |  |  |  | x |  |  | 13 | NEMA, APPA, Environmental Management Plan, Scheduled, Serviced and maintained plant and vehicles, | 4.55 | 65 |  |  | x | x
1 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Driving/ Operating | Source: Monotony of Task Exposure: Loss of focus/concentration; At Risk behaviour | Outcome : Body Harm /Failure to adhere to Consequences: Property Damage / Loss of Production / Personal injury/fatality | x | [5 empty] | X | [5 empty] | x | 23 | Fatigue management, CoP TMM, | 19.55 | 15 |  |  |  | X
2 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Driving/ Operating | Source: Long distant driving Exposure: Fatigue, Loss of focus/concentration; At Risk behaviour | Outcome : Body Harm /Failure to adhere to Consequences: Property Damage / Loss of Production / Personal injury/fatality | x | [5 empty] | X |  |  |  | x |  |  | 18 | Fatigue management, CoP TMM, Travel Policy | 15.3 | 15 |  |  |  | x
3 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Driving/ Operating | Source: Vibration Exposure: Fatigue / Over Exposure | Outcome : Body Harm / Health Impact Consequences: Disability / Loss of Production |  | x |  |  |  |  | x |  |  |  | x |  |  | 18 | Fatigue Management, Ergonomically designed Plant. Whole body Vibration measurements | 6.3 | 65 |  |  | x | x
4 | Ergonomics | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads | x |  | Driving/ Operating | Source: Restricted Space / Close proximity Exposure: Contact with / Fatigue / Over Exposure | Outcome : Body Harm / Health Impact Consequences: Disability / Loss of Production |  | x |  |  |  |  | x |  |  |  | x |  |  | 18 | Separation of People/Plant/vehicle and equipment according to Traffic Management plan. Road signs, Flag men, Access control. Intoxication tests, Spotter to be in pace where People and Plant interact. Clearly demarcated walkways. No operator to operate TMM within 1m of any structure without having a spotter to ensure that the TMM does not come in to contact with any structure. Supervision. 2-way radio communication. | 6.3 | 65 |  |  | x | x
1 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Breakdown / Mechanical Failure | Source: Vehicle breakdown due to mechanical failure / Flat tyre / Fuel Empty Exposure: Roadside Breakdown /Cause an accident if not visible or standing to close to shoulder of road | Incident leading to personal injuries. Unclear visibility that may escalate to a serious incident. Risk of being assaulted next to road resulting in personal injuries even fatality | x | [6 empty] | x |  |  |  | x |  | 24 | CoP TMM, Scheduled maintenance, pre-use inspections, Reflective triangles in all vehicles and plant | 8.4 | 65 |  |  | x | x
7 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Potential fires | Source: None or inadequate fire fighting equipment (Fire extinguishers) Exposure: Caught by, caught in, burns by fire / Uncontrolled fire | Serious injury or possible multiple fatalities; Property damage. | x | [6 empty] | x |  |  |  | x |  | 24 | Fire prevention and protection COP, COP for Emergency Preparedness and Response, on-board fire extinguishers | 20.4 | 15 |  |  |  | x
8 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Potential fires | Source: Flammable liquids , electrical faults Exposure: Employees exposed to smoke. Employees may be expose to extreme heat. | Incident inhalation of smoke and asphyxiations, that may escalate to a serious ill Health | x | x |  |  |  | x | [5 empty] | x |  | 17 | Fire prevention and protection COP, COP for Emergency Preparedness and Response, on-board fire extinguishers | 14.45 | 15 |  |  |  | x
9 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Potential fires | Source: None or inadequate fire fighting equipment (Fire extinguishers) on Vehicle Exposure: Uncontrolled Fire, fire spreading | Environmental Impact - For more detail see Environmental Impact and Aspect Register |  |  | x |  |  |  | x |  |  |  |  | x |  | 21 | Fire prevention and protection COP, COP for Emergency Preparedness and Response, on-board fire extinguishers | 17.85 | 15 |  |  |  | x
11 | Emergency | BIP - Project | All Mobile Equipment / Transportation / Vehicles | Driving vehicles on National, District Roads / Project Site Roads |  | x | Evacuation / Emergency Exit | Source: Emergency Exits not available or working Exposure: Trapped, lack of emergency equipment | Incident leading to personal injuries. Medical treatment for burns that may escalating to a serious incident that may escalate to permanent disability or a multiple fatality | x | [6 empty] | x |  | x |  |  |  | 19 | Periodic drills, inspections, clearly marked and maintained exits, induction to location of exits | 16.15 | 15 |  |  |  | x