## WBS
WBS1 |  | WBS2 |  | WBS3 - Combined Code |  | Cascading
A | Home Office | CC | Consulting Costs | ACC00 | XX-Overall | Home Office,Consulting Costs,XX-Overall
A | Home Office | CC | Consulting Costs | ACC01 | Infrastructure Construction & QA Support | Home Office,Consulting Costs,Infrastructure Construction & QA Support
A | Home Office | CC | Consulting Costs | ACC02 | Rail Siding Construction & QA Support | Home Office,Consulting Costs,Rail Siding Construction & QA Support
A | Home Office | CC | Consulting Costs | ACC03 | Discard Facility Construction & QA Support | Home Office,Consulting Costs,Discard Facility Construction & QA Support
A | Home Office | CC | Consulting Costs | ACC04 | Wetland Rehab Construction & QA Support | Home Office,Consulting Costs,Wetland Rehab Construction & QA Support
A | Home Office | CC | Consulting Costs | ACC05 | Resettlement Site Construction & QA Support | Home Office,Consulting Costs,Resettlement Site Construction & QA Support
A | Home Office | CC | Consulting Costs | ACC06 | Plant (CHPP) Construction & QA Support | Home Office,Consulting Costs,Plant (CHPP) Construction & QA Support
A | Home Office | CC | Consulting Costs | ACC07 | Stakeholder Management | Home Office,Consulting Costs,Stakeholder Management
A | Home Office | CC | Consulting Costs | ACC08 | Owners' Team Training & Development | Home Office,Consulting Costs,Owners' Team Training & Development
A | Home Office | CC | Consulting Costs | ACC09 | Site Construction Team Training Requirements | Home Office,Consulting Costs,Site Construction Team Training Requirements
A | Home Office | CC | Consulting Costs | ACC10 | Site Cleaning Services | Home Office,Consulting Costs,Site Cleaning Services
A | Home Office | CC | Consulting Costs | ACC11 | Site Domestic Waste Removal | Home Office,Consulting Costs,Site Domestic Waste Removal
A | Home Office | CC | Consulting Costs | ACC12 | Internal Auditing Services | Home Office,Consulting Costs,Internal Auditing Services
A | Home Office | CC | Consulting Costs | ACC13 | Energy Efficiency COC | Home Office,Consulting Costs,Energy Efficiency COC
A | Home Office | CC | Consulting Costs | ACC14 | Project Software & Licenses | Home Office,Consulting Costs,Project Software & Licenses
A | Home Office | CC | Consulting Costs | ACC15 | Quantity Surveying Services | Home Office,Consulting Costs,Quantity Surveying Services
A | Home Office | CC | Consulting Costs | ACC16 | Environmental Officer (HQ) - Tarryn Dale | Home Office,Consulting Costs,Environmental Officer (HQ) - Tarryn Dale
A | Home Office | CC | Consulting Costs | ACC17 | Environmental Compliance Officer - Site | Home Office,Consulting Costs,Environmental Compliance Officer - Site
A | Home Office | CC | Consulting Costs | ACC18 | Licensing Compliance Requirements | Home Office,Consulting Costs,Licensing Compliance Requirements
A | Home Office | CC | Consulting Costs | ACC19 | WUL Pans Research | Home Office,Consulting Costs,WUL Pans Research
A | Home Office | CC | Consulting Costs | ACC20 | Biodiversity Requirements (Fauna & Flora Programmes) | Home Office,Consulting Costs,Biodiversity Requirements (Fauna & Flora Programmes)
A | Home Office | CC | Consulting Costs | ACC21 | Emergency Services | Home Office,Consulting Costs,Emergency Services
A | Home Office | CC | Consulting Costs | ACC22 | Site Security Services | Home Office,Consulting Costs,Site Security Services
A | Home Office | CC | Consulting Costs | ACC23 | Environmental Baseline Monitoring - Golder Associates | Home Office,Consulting Costs,Environmental Baseline Monitoring - Golder Associates
A | Home Office | CC | Consulting Costs | ACC24 | Environmental Baseline Monitoring - Aquatico | Home Office,Consulting Costs,Environmental Baseline Monitoring - Aquatico
A | Home Office | CC | Consulting Costs | ACC25 | Health & Safety Recognitions | Home Office,Consulting Costs,Health & Safety Recognitions
A | Home Office | CC | Consulting Costs | ACC26 | Project Collaboration Services | Home Office,Consulting Costs,Project Collaboration Services
A | Home Office | CC | Consulting Costs | ACC27 | Legal Services | Home Office,Consulting Costs,Legal Services
A | Home Office | CC | Consulting Costs | ACC28 | Specialist Consulting Services | Home Office,Consulting Costs,Specialist Consulting Services
A | Home Office | CC | Consulting Costs | ACC29 | External QA Services | Home Office,Consulting Costs,External QA Services
A | Home Office | CC | Consulting Costs | ACC30 | Belfast Mine Sod Turning Ceremony | Home Office,Consulting Costs,Belfast Mine Sod Turning Ceremony
A | Home Office | CO | Consultants | ACO00 | XX-Overall | Home Office,Consultants,XX-Overall
A | Home Office | CO | Consultants | ACO01 | Cost Control Services | Home Office,Consultants,Cost Control Services
A | Home Office | CO | Consultants | ACO02 | Discard Disposal Engineering | Home Office,Consultants,Discard Disposal Engineering
A | Home Office | CO | Consultants | ACO04 | Environmental Consultant | Home Office,Consultants,Environmental Consultant
A | Home Office | CO | Consultants | ACO08 | Plant Engineering | Home Office,Consultants,Plant Engineering
A | Home Office | CO | Consultants | ACO10 | Quantity Surveying Services | Home Office,Consultants,Quantity Surveying Services
A | Home Office | CO | Consultants | ACO11 | Rail Engineering | Home Office,Consultants,Rail Engineering
A | Home Office | CO | Consultants | ACO14 | Infrastructure Engineering | Home Office,Consultants,Infrastructure Engineering
A | Home Office | CO | Consultants | ACO15 | Wetland Rehabilitation Engineering | Home Office,Consultants,Wetland Rehabilitation Engineering
A | Home Office | CO | Consultants | ACO16 | ROM Sizing Station Engineering | Home Office,Consultants,ROM Sizing Station Engineering
A | Home Office | CO | Consultants | ACO17 | Baseline Monitoring | Home Office,Consultants,Baseline Monitoring
A | Home Office | CO | Consultants | ACO18 | Sustainable Development Report | Home Office,Consultants,Sustainable Development Report
A | Home Office | CO | Consultants | ACO19 | PCO Services Controls Cost Planning Risk | Home Office,Consultants,PCO Services Controls Cost Planning Risk
A | Home Office | CO | Consultants | ACO20 | PCO Services Contract Admin Doc Control | Home Office,Consultants,PCO Services Contract Admin Doc Control
A | Home Office | CO | Consultants | ACO21 | Resettlement Detail Engineering | Home Office,Consultants,Resettlement Detail Engineering
A | Home Office | CO | Consultants | ACO22 | Project Collaboration System | Home Office,Consultants,Project Collaboration System
A | Home Office | OC | Owners Cost | AOC00 | XX-Overall | Home Office,Owners Cost,XX-Overall
A | Home Office | OC | Owners Cost | AOC01 | Accommodation | Home Office,Owners Cost,Accommodation
A | Home Office | OC | Owners Cost | AOC06 | HSE | Home Office,Owners Cost,HSE
A | Home Office | OC | Owners Cost | AOC08 | Salaries | Home Office,Owners Cost,Salaries
A | Home Office | OC | Owners Cost | AOC09 | Travelling | Home Office,Owners Cost,Travelling
A | Home Office | OC | Owners Cost | AOC11 | Sundries | Home Office,Owners Cost,Sundries
A | Home Office | OC | Owners Cost | AOC12 | Legal Cost | Home Office,Owners Cost,Legal Cost
A | Home Office | OC | Owners Cost | AOC14 | Social Labour Plan (SLP) | Home Office,Owners Cost,Social Labour Plan (SLP)
A | Home Office | OC | Owners Cost | AOC15 | Training & Development | Home Office,Owners Cost,Training & Development
A | Home Office | OC | Owners Cost | AOC16 | Health and Safety | Home Office,Owners Cost,Health and Safety
A | Home Office | OC | Owners Cost | AOC17 | IM Services | Home Office,Owners Cost,IM Services
A | Home Office | TC | Team & Home Office Costs | ATC00 | XX-Overall | Home Office,Team & Home Office Costs,XX-Overall
A | Home Office | TC | Team & Home Office Costs | ATC01 | Construction Diesel Supply | Home Office,Team & Home Office Costs,Construction Diesel Supply
A | Home Office | TC | Team & Home Office Costs | ATC02 | Project Team - Salaries & Labour Brokers | Home Office,Team & Home Office Costs,Project Team - Salaries & Labour Brokers
A | Home Office | TC | Team & Home Office Costs | ATC03 | Accommodation Costs | Home Office,Team & Home Office Costs,Accommodation Costs
A | Home Office | TC | Team & Home Office Costs | ATC04 | Travelling Costs | Home Office,Team & Home Office Costs,Travelling Costs
A | Home Office | TC | Team & Home Office Costs | ATC05 | Daily Allowance Costs | Home Office,Team & Home Office Costs,Daily Allowance Costs
A | Home Office | TC | Team & Home Office Costs | ATC06 | Sundries - Pretoria (Consumables, SHE etc) | Home Office,Team & Home Office Costs,Sundries - Pretoria (Consumables, SHE etc)
A | Home Office | TC | Team & Home Office Costs | ATC07 | Sundries - Site (Consumables, SHE, etc) | Home Office,Team & Home Office Costs,Sundries - Site (Consumables, SHE, etc)
A | Home Office | TC | Team & Home Office Costs | ATC08 | Cellphones | Home Office,Team & Home Office Costs,Cellphones
A | Home Office | TC | Team & Home Office Costs | ATC09 | Flights | Home Office,Team & Home Office Costs,Flights
A | Home Office | TC | Team & Home Office Costs | ATC10 | Geological Drilling (Previously under Box Cuts) | Home Office,Team & Home Office Costs,Geological Drilling (Previously under Box Cuts)
A | Home Office | TC | Team & Home Office Costs | ATC11 | Project Insurance | Home Office,Team & Home Office Costs,Project Insurance
A | Home Office | TC | Team & Home Office Costs | ATC12 | Short Term Incentive Bonusses (STI) | Home Office,Team & Home Office Costs,Short Term Incentive Bonusses (STI)
A | Home Office | TC | Team & Home Office Costs | ATC13 | SLP (Social Labour Plan) | Home Office,Team & Home Office Costs,SLP (Social Labour Plan)
A | Home Office | TC | Team & Home Office Costs | ATC14 | Project Team - Service Providers - PaCE | Home Office,Team & Home Office Costs,Project Team - Service Providers - PaCE
A | Home Office | TC | Team & Home Office Costs | ATC15 | Project Team - Service Providers - ProjectLink | Home Office,Team & Home Office Costs,Project Team - Service Providers - ProjectLink
A | Home Office | TI | Temporary Construction Infrastructure | ATI03 | Construction IM | Home Office,Temporary Construction Infrastructure,Construction IM
I | Infrastructure | BU | Buildings | IBU00 | XX-Overall | Infrastructure,Buildings,XX-Overall
I | Infrastructure | BU | Buildings | IBU01 | Conference Facility and Clinic | Infrastructure,Buildings,Conference Facility and Clinic
I | Infrastructure | BU | Buildings | IBU03 | Main 22KV Substation | Infrastructure,Buildings,Main 22KV Substation
I | Infrastructure | BU | Buildings | IBU04 | Main Office Block | Infrastructure,Buildings,Main Office Block
I | Infrastructure | BU | Buildings | IBU05 | Main Security and Induction | Infrastructure,Buildings,Main Security and Induction
I | Infrastructure | BU | Buildings | IBU06 | Mining Area Access Security | Infrastructure,Buildings,Mining Area Access Security
I | Infrastructure | BU | Buildings | IBU11 | Plant Changehouse | Infrastructure,Buildings,Plant Changehouse
I | Infrastructure | BU | Buildings | IBU12 | Plant Control Room | Infrastructure,Buildings,Plant Control Room
I | Infrastructure | BU | Buildings | IBU13 | Plant Workshop | Infrastructure,Buildings,Plant Workshop
I | Infrastructure | BU | Buildings | IBU14 | Primary and Secondary Crusher Substation | Infrastructure,Buildings,Primary and Secondary Crusher Substation
I | Infrastructure | BU | Buildings | IBU15 | Product Handling Substation | Infrastructure,Buildings,Product Handling Substation
I | Infrastructure | BU | Buildings | IBU19 | Supply Chain Management | Infrastructure,Buildings,Supply Chain Management
I | Infrastructure | BU | Buildings | IBU20 | Truck Entrance Ablution Block | Infrastructure,Buildings,Truck Entrance Ablution Block
I | Infrastructure | BU | Buildings | IBU21 | Truck Entrance Security | Infrastructure,Buildings,Truck Entrance Security
I | Infrastructure | BU | Buildings | IBU23 | Fire Pump Station | Infrastructure,Buildings,Fire Pump Station
I | Infrastructure | BU | Buildings | IBU25 | Turnstiles | Infrastructure,Buildings,Turnstiles
I | Infrastructure | CC | Communication Corridors | ICC01 | Communication Sleeves | Infrastructure,Communication Corridors,Communication Sleeves
I | Infrastructure | CO | Common | ICO01 | Infrastructure Common / Prelim & General | Infrastructure,Common,Infrastructure Common / Prelim & General
I | Infrastructure | DA | Discard Dump Area | IDA01 | Discard Dump | Infrastructure,Discard Dump Area,Discard Dump
I | Infrastructure | DL | Diesel and Lubricants | IDL01 | Total Diesel & Lubricants | Infrastructure,Diesel and Lubricants,Total Diesel & Lubricants
I | Infrastructure | DM | Dams | IDM00 | XX-Overall | Infrastructure,Dams,XX-Overall
I | Infrastructure | DM | Dams | IDM10 | D1 - Farm Dam | Infrastructure,Dams,D1 - Farm Dam
I | Infrastructure | DM | Dams | IDM21 | D2 - Stormwater Dam | Infrastructure,Dams,D2 - Stormwater Dam
I | Infrastructure | DM | Dams | IDM30 | D3 - Process Water Dam | Infrastructure,Dams,D3 - Process Water Dam
I | Infrastructure | DM | Dams | IDM40 | D4 - Return Stormwater Dam | Infrastructure,Dams,D4 - Return Stormwater Dam
I | Infrastructure | DM | Dams | IDM50 | D5 - Return Water Dam | Infrastructure,Dams,D5 - Return Water Dam
I | Infrastructure | DW | Dayworks | IDW01 | Dayworks | Infrastructure,Dayworks,Dayworks
I | Infrastructure | EB | Eastern Link Bridge | IEB01 | Bridges | Infrastructure,Eastern Link Bridge,Bridges
I | Infrastructure | EL | Electrical System | IEL00 | XX-Overall | Infrastructure,Electrical System,XX-Overall
I | Infrastructure | EL | Electrical System | IEL01 | Area Lighting | Infrastructure,Electrical System,Area Lighting
I | Infrastructure | EL | Electrical System | IEL02 | Earthing and Lightning Protection | Infrastructure,Electrical System,Earthing and Lightning Protection
I | Infrastructure | EL | Electrical System | IEL03 | Emergency Power | Infrastructure,Electrical System,Emergency Power
I | Infrastructure | EL | Electrical System | IEL05 | LV Switch Gear | Infrastructure,Electrical System,LV Switch Gear
I | Infrastructure | EL | Electrical System | IEL06 | Minisubs and Transformers | Infrastructure,Electrical System,Minisubs and Transformers
I | Infrastructure | EL | Electrical System | IEL07 | MV Switch Gear | Infrastructure,Electrical System,MV Switch Gear
I | Infrastructure | EL | Electrical System | IEL08 | MV/LV Reticulation | Infrastructure,Electrical System,MV/LV Reticulation
I | Infrastructure | EL | Electrical System | IEL09 | Power Factor Correction | Infrastructure,Electrical System,Power Factor Correction
I | Infrastructure | EP | Eskom Power Supply | IEP00 | XX-Overall | Infrastructure,Eskom Power Supply,XX-Overall
I | Infrastructure | EP | Eskom Power Supply | IEP01 | Electrical Energy 2015 | Infrastructure,Eskom Power Supply,Electrical Energy 2015
I | Infrastructure | EP | Eskom Power Supply | IEP02 | Electrical Energy 2016 | Infrastructure,Eskom Power Supply,Electrical Energy 2016
I | Infrastructure | EP | Eskom Power Supply | IEP03 | Eskom Power Supply | Infrastructure,Eskom Power Supply,Eskom Power Supply
I | Infrastructure | EW | Early Works | IEW00 | XX-Overall | Infrastructure,Early Works,XX-Overall
I | Infrastructure | EW | Early Works | IEW01 | Access Gate | Infrastructure,Early Works,Access Gate
I | Infrastructure | EW | Early Works | IEW02 | Construction Fencing | Infrastructure,Early Works,Construction Fencing
I | Infrastructure | EW | Early Works | IEW03 | Construction Offices | Infrastructure,Early Works,Construction Offices
I | Infrastructure | EW | Early Works | IEW04 | Construction Power | Infrastructure,Early Works,Construction Power
I | Infrastructure | EW | Early Works | IEW05 | Construction Roads | Infrastructure,Early Works,Construction Roads
I | Infrastructure | EW | Early Works | IEW06 | Construction Sewerage Treatment | Infrastructure,Early Works,Construction Sewerage Treatment
I | Infrastructure | EW | Early Works | IEW07 | Demolitions | Infrastructure,Early Works,Demolitions
I | Infrastructure | EW | Early Works | IEW09 | Laydown Areas | Infrastructure,Early Works,Laydown Areas
I | Infrastructure | EW | Early Works | IEW11 | Water Supply | Infrastructure,Early Works,Water Supply
I | Infrastructure | EX | Explosives - Prills and Matrix | IEX01 | SASOL | Infrastructure,Explosives - Prills and Matrix,SASOL
I | Infrastructure | FE | Fencing | IFE00 | XX-Overall | Infrastructure,Fencing,XX-Overall
I | Infrastructure | FE | Fencing | IFE01 | Explosive Magazine | Infrastructure,Fencing,Explosive Magazine
I | Infrastructure | FE | Fencing | IFE02 | Mine Area Fencing | Infrastructure,Fencing,Mine Area Fencing
I | Infrastructure | FE | Fencing | IFE03 | Plant Area Fencing | Infrastructure,Fencing,Plant Area Fencing
I | Infrastructure | FE | Fencing | IFE04 | Mine Perimeter Fencing | Infrastructure,Fencing,Mine Perimeter Fencing
I | Infrastructure | GS | Gas Installation | IGS01 | Plant Workshop | Infrastructure,Gas Installation,Plant Workshop
I | Infrastructure | GI | Geotechnical | IGI01 | Test Pitting | Infrastructure,Geotechnical,Test Pitting
I | Infrastructure | HA | Helipad Area | IHA01 | Helipad | Infrastructure,Helipad Area,Helipad
I | Infrastructure | IM | Information Management | IIM00 | XX-Overall | Infrastructure,Information Management,XX-Overall
I | Infrastructure | IM | Information Management | IIM01 | Access Control | Infrastructure,Information Management,Access Control
I | Infrastructure | IM | Information Management | IIM02 | Automation | Infrastructure,Information Management,Automation
I | Infrastructure | IM | Information Management | IIM03 | DMS | Infrastructure,Information Management,DMS
I | Infrastructure | IM | Information Management | IIM04 | End User Equipment | Infrastructure,Information Management,End User Equipment
I | Infrastructure | IM | Information Management | IIM05 | Finance and SCM | Infrastructure,Information Management,Finance and SCM
I | Infrastructure | IM | Information Management | IIM06 | HR | Infrastructure,Information Management,HR
I | Infrastructure | IM | Information Management | IIM07 | Marketing and Logistics | Infrastructure,Information Management,Marketing and Logistics
I | Infrastructure | IM | Information Management | IIM08 | MES Solutions | Infrastructure,Information Management,MES Solutions
I | Infrastructure | IM | Information Management | IIM09 | Mining | Infrastructure,Information Management,Mining
I | Infrastructure | IM | Information Management | IIM10 | Networking - Offices | Infrastructure,Information Management,Networking - Offices
I | Infrastructure | IM | Information Management | IIM11 | Networking - Process | Infrastructure,Information Management,Networking - Process
I | Infrastructure | IM | Information Management | IIM12 | PAM | Infrastructure,Information Management,PAM
I | Infrastructure | IM | Information Management | IIM13 | Radios | Infrastructure,Information Management,Radios
I | Infrastructure | IM | Information Management | IIM14 | Security (IM) | Infrastructure,Information Management,Security (IM)
I | Infrastructure | IM | Information Management | IIM15 | Servers | Infrastructure,Information Management,Servers
I | Infrastructure | IM | Information Management | IIM16 | SHEQ | Infrastructure,Information Management,SHEQ
I | Infrastructure | IM | Information Management | IIM17 | Software - Not Included Elsewhere | Infrastructure,Information Management,Software - Not Included Elsewhere
I | Infrastructure | IM | Information Management | IIM18 | Software - SAP Enterprise | Infrastructure,Information Management,Software - SAP Enterprise
I | Infrastructure | IM | Information Management | IIM19 | Telephones | Infrastructure,Information Management,Telephones
I | Infrastructure | IM | Information Management | IIM20 | Business Intelligence | Infrastructure,Information Management,Business Intelligence
I | Infrastructure | IM | Information Management | IIM21 | Site Preparation | Infrastructure,Information Management,Site Preparation
I | Infrastructure | IM | Information Management | IIM22 | Project Management | Infrastructure,Information Management,Project Management
I | Infrastructure | IM | Information Management | IIM23 | Construction Surveillance | Infrastructure,Information Management,Construction Surveillance
I | Infrastructure | IP | Internal Parking | IIP00 | XX-Overall | Infrastructure,Internal Parking,XX-Overall
I | Infrastructure | IP | Internal Parking | IIP02 | Changehouse Pick-up and Mine Vehicle Parking | Infrastructure,Internal Parking,Changehouse Pick-up and Mine Vehicle Parking
I | Infrastructure | IP | Internal Parking | IIP04 | Interlink Parking | Infrastructure,Internal Parking,Interlink Parking
I | Infrastructure | IP | Internal Parking | IIP06 | MCR Parking | Infrastructure,Internal Parking,MCR Parking
I | Infrastructure | IP | Internal Parking | IIP07 | Mine Drop-off Zone | Infrastructure,Internal Parking,Mine Drop-off Zone
I | Infrastructure | IP | Internal Parking | IIP08 | Mine Security Parking | Infrastructure,Internal Parking,Mine Security Parking
I | Infrastructure | IP | Internal Parking | IIP10 | Plant Area Visitors Parking | Infrastructure,Internal Parking,Plant Area Visitors Parking
I | Infrastructure | IP | Internal Parking | IIP11 | Plant Office Parking | Infrastructure,Internal Parking,Plant Office Parking
I | Infrastructure | IP | Internal Parking | IIP12 | Plant Workshop Parking | Infrastructure,Internal Parking,Plant Workshop Parking
I | Infrastructure | IP | Internal Parking | IIP14 | Supply Chain Parking | Infrastructure,Internal Parking,Supply Chain Parking
I | Infrastructure | IR | Internal Roads | IIR00 | XX-Overall | Infrastructure,Internal Roads,XX-Overall
I | Infrastructure | IR | Internal Roads | IIR01 | Haul Roads | Infrastructure,Internal Roads,Haul Roads
I | Infrastructure | IR | Internal Roads | IIR02 | Mining Area - Gravel Roads | Infrastructure,Internal Roads,Mining Area - Gravel Roads
I | Infrastructure | IR | Internal Roads | IIR03 | Plant Area - Gravel Roads | Infrastructure,Internal Roads,Plant Area - Gravel Roads
I | Infrastructure | IR | Internal Roads | IIR04 | Plant Area - Surfaced Roads | Infrastructure,Internal Roads,Plant Area - Surfaced Roads
I | Infrastructure | IR | Internal Roads | IIR05 | Mining Area - Surfaced Roads | Infrastructure,Internal Roads,Mining Area - Surfaced Roads
I | Infrastructure | IW | Internal Walkways | IIW01 | Mining Area | Infrastructure,Internal Walkways,Mining Area
I | Infrastructure | IW | Internal Walkways | IIW02 | Plant Area | Infrastructure,Internal Walkways,Plant Area
I | Infrastructure | LI | Landscaping and Irrigation | ILI01 | Main Offices Area | Infrastructure,Landscaping and Irrigation,Main Offices Area
I | Infrastructure | PR | Provincial Roads | IPR00 | XX-Overall | Infrastructure,Provincial Roads,XX-Overall
I | Infrastructure | PR | Provincial Roads | IPR01 | Provincial N4 to Mine D1110 - Overlay | Infrastructure,Provincial Roads,Provincial N4 to Mine D1110 - Overlay
I | Infrastructure | PR | Provincial Roads | IPR03 | Provincial N4 to Mine D1770 - New | Infrastructure,Provincial Roads,Provincial N4 to Mine D1770 - New
I | Infrastructure | SB | Exxaro Signage and Branding | ISB01 | External Signage | Infrastructure,Exxaro Signage and Branding,External Signage
I | Infrastructure | SB | Exxaro Signage and Branding | ISB02 | Internal Signage | Infrastructure,Exxaro Signage and Branding,Internal Signage
I | Infrastructure | SC | Site Cleanup | ISC01 | Removal of Infrastructure | Infrastructure,Site Cleanup,Removal of Infrastructure
I | Infrastructure | ST | Structures | IST00 | XX-Overall | Infrastructure,Structures,XX-Overall
I | Infrastructure | ST | Structures | IST01 | Explosives Storage Facility | Infrastructure,Structures,Explosives Storage Facility
I | Infrastructure | ST | Structures | IST02 | LDV Washbay | Infrastructure,Structures,LDV Washbay
I | Infrastructure | ST | Structures | IST09 | Pump Stations | Infrastructure,Structures,Pump Stations
I | Infrastructure | ST | Structures | IST12 | Weather Station | Infrastructure,Structures,Weather Station
I | Infrastructure | SW | Sewerage Management | ISW00 | XX-Overall | Infrastructure,Sewerage Management,XX-Overall
I | Infrastructure | SW | Sewerage Management | ISW02 | Plant Area Reticulation | Infrastructure,Sewerage Management,Plant Area Reticulation
I | Infrastructure | SW | Sewerage Management | ISW03 | Sewerage Treatment Package Plant | Infrastructure,Sewerage Management,Sewerage Treatment Package Plant
I | Infrastructure | TC | Terraces | ITC00 | XX-Overall | Infrastructure,Terraces,XX-Overall
I | Infrastructure | TC | Terraces | ITC01 | Ramp and Platform | Infrastructure,Terraces,Ramp and Platform
I | Infrastructure | TC | Terraces | ITC02 | Crushing and Screening Plant | Infrastructure,Terraces,Crushing and Screening Plant
I | Infrastructure | TC | Terraces | ITC03 | Reservoir and Pump House | Infrastructure,Terraces,Reservoir and Pump House
I | Infrastructure | TC | Terraces | ITC04 | Plant Workshop & Supply Chain (SCM) | Infrastructure,Terraces,Plant Workshop & Supply Chain (SCM)
I | Infrastructure | TC | Terraces | ITC05 | Export & Middlings Stockpile | Infrastructure,Terraces,Export & Middlings Stockpile
I | Infrastructure | TC | Terraces | ITC06 | Main 22kV Substation | Infrastructure,Terraces,Main 22kV Substation
I | Infrastructure | TC | Terraces | ITC07 | 3600T Stockpile | Infrastructure,Terraces,3600T Stockpile
I | Infrastructure | TC | Terraces | ITC08 | Helipad | Infrastructure,Terraces,Helipad
I | Infrastructure | TC | Terraces | ITC10 | Laboratory | Infrastructure,Terraces,Laboratory
I | Infrastructure | TC | Terraces | ITC11 | Main Security, Inductions & Changehouse | Infrastructure,Terraces,Main Security, Inductions & Changehouse
I | Infrastructure | TC | Terraces | ITC12 | Middlings Road Island | Infrastructure,Terraces,Middlings Road Island
I | Infrastructure | TC | Terraces | ITC13 | Waste Water Treatment | Infrastructure,Terraces,Waste Water Treatment
I | Infrastructure | TC | Terraces | ITC14 | Main Office Block | Infrastructure,Terraces,Main Office Block
I | Infrastructure | TC | Terraces | ITC15 | Truck Entrance Ablution | Infrastructure,Terraces,Truck Entrance Ablution
I | Infrastructure | TC | Terraces | ITC16 | Truck Entrance Security | Infrastructure,Terraces,Truck Entrance Security
I | Infrastructure | TC | Terraces | ITC17 | Primary Crusher | Infrastructure,Terraces,Primary Crusher
I | Infrastructure | TC | Terraces | ITC18 | Primary Crusher Substation | Infrastructure,Terraces,Primary Crusher Substation
I | Infrastructure | TC | Terraces | ITC19 | Discard Mobile Equipment Parking | Infrastructure,Terraces,Discard Mobile Equipment Parking
I | Infrastructure | TC | Terraces | ITC20 | Shovel Parking | Infrastructure,Terraces,Shovel Parking
I | Infrastructure | TC | Terraces | ITC21 | Mobile Equipment Yard | Infrastructure,Terraces,Mobile Equipment Yard
I | Infrastructure | TC | Terraces | ITC22 | Diesel Depot | Infrastructure,Terraces,Diesel Depot
I | Infrastructure | TC | Terraces | ITC23 | 150T Discard Stockpile | Infrastructure,Terraces,150T Discard Stockpile
I | Infrastructure | TC | Terraces | ITC24 | Changehouse / Management Office & Mining Office | Infrastructure,Terraces,Changehouse / Management Office & Mining Office
I | Infrastructure | TC | Terraces | ITC25 | Explosives Magazine | Infrastructure,Terraces,Explosives Magazine
I | Infrastructure | TC | Terraces | ITC26 | Mine Access Security | Infrastructure,Terraces,Mine Access Security
I | Infrastructure | TC | Terraces | ITC27 | Dust Suppression & WWTP | Infrastructure,Terraces,Dust Suppression & WWTP
I | Infrastructure | TE | Tools and Equipment | ITE00 | XX-Overall | Infrastructure,Tools and Equipment,XX-Overall
I | Infrastructure | TE | Tools and Equipment | ITE02 | Plant Support Mobile Equipment | Infrastructure,Tools and Equipment,Plant Support Mobile Equipment
I | Infrastructure | TE | Tools and Equipment | ITE03 | Plant Workshop Tools and Equipment | Infrastructure,Tools and Equipment,Plant Workshop Tools and Equipment
I | Infrastructure | WB | Weighbridges | IWB01 | Plant Area Weighbridges | Infrastructure,Weighbridges,Plant Area Weighbridges
I | Infrastructure | WM | Water Management | IWM00 | XX-Overall | Infrastructure,Water Management,XX-Overall
I | Infrastructure | WM | Water Management | IWM04 | Decant Water | Infrastructure,Water Management,Decant Water
I | Infrastructure | WM | Water Management | IWM05 | Dust Suppression | Infrastructure,Water Management,Dust Suppression
I | Infrastructure | WM | Water Management | IWM06 | Fire Water | Infrastructure,Water Management,Fire Water
I | Infrastructure | WM | Water Management | IWM07 | In-Pit Stormwater Pipeline | Infrastructure,Water Management,In-Pit Stormwater Pipeline
I | Infrastructure | WM | Water Management | IWM08 | Potable Water | Infrastructure,Water Management,Potable Water
I | Infrastructure | WM | Water Management | IWM09 | Raw Water | Infrastructure,Water Management,Raw Water
I | Infrastructure | WM | Water Management | IWM10 | Stormwater Channels | Infrastructure,Water Management,Stormwater Channels
I | Infrastructure | WM | Waste Management | IWT01 | Domestic Waste | Infrastructure,Waste Management,Domestic Waste
I | Infrastructure | WM | Waste Management | IWT02 | Hazardous Waste | Infrastructure,Waste Management,Hazardous Waste
L | Land and Servitudes | SI | Sidings | LSI01 | Rietkuil Servitudes | Land and Servitudes,Sidings,Rietkuil Servitudes
L | Land and Servitudes | WO | Wetland Offsets | LWO02 | Farm Purchases (Offsets) | Land and Servitudes,Wetland Offsets,Farm Purchases (Offsets)
L | Land and Servitudes | WO | Wetland Offsets | LWO03 | Wetland Rehabilitation | Land and Servitudes,Wetland Offsets,Wetland Rehabilitation
P | Plant | CSP | Plant Overall | PCSP00 | XX-Overall | Plant,Plant Overall,XX-Overall
P | Plant | FDC | 380 - Fines H.M. Process | PFDC00 | XX-Overall | Plant,380 - Fines H.M. Process,XX-Overall
P | Plant | FIP | 420 - Filtering Process | PFIP00 | XX-Overall | Plant,420 - Filtering Process,XX-Overall
P | Plant | HGP | 340/360 - High Gravity H.M. Process | PHGP00 | XX-Overall | Plant,340/360 - High Gravity H.M. Process,XX-Overall
P | Plant | LGP | 300/320 - Low Gravity H.M. Process | PLGP00 | XX-Overall | Plant,300/320 - Low Gravity H.M. Process,XX-Overall
P | Plant | PHP | 500/520/540 - Export/Middling's/Discard Handling Process | PPHP00 | XX-Overall | Plant,500/520/540 - Export/Middling's/Discard Handling Process,XX-Overall
P | Plant | RHP | 200 - ROM Handling | PRHP00 | XX-Overall | Plant,200 - ROM Handling,XX-Overall
P | Plant | RS | ROM Sizing Station | PRS02 | Primary Tip Bin | Plant,ROM Sizing Station,Primary Tip Bin
P | Plant | RS | ROM Sizing Station | PRS03 | Apron Feeder | Plant,ROM Sizing Station,Apron Feeder
P | Plant | RS | ROM Sizing Station | PRS04 | Primary Mineral Sizer | Plant,ROM Sizing Station,Primary Mineral Sizer
P | Plant | RS | ROM Sizing Station | PRS08 | Secondary Mineral Sizer | Plant,ROM Sizing Station,Secondary Mineral Sizer
P | Plant | RS | ROM Sizing Station | PRS00 | XX-Overall | Plant,ROM Sizing Station,XX-Overall
P | Plant | SPP | 600/620/640/660/680 - Plant Services | PSPP00 | XX-Overall | Plant,600/620/640/660/680 - Plant Services,XX-Overall
P | Plant | THP | 400 - Thickening Process | PTHP00 | XX-Overall | Plant,400 - Thickening Process,XX-Overall
A | Project Wide | AA | Project wide | AAA00 | XX-Overall | Project Wide,Project wide,XX-Overall
R | Rail | GE | Geotechnical | RGE01 | Geotech Works for Rietkuil Siding | Rail,Geotechnical,Geotech Works for Rietkuil Siding
R | Rail | RK | Rietkuil | RRK00 | XX-Overall | Rail,Rietkuil,XX-Overall
R | Rail | RK | Rietkuil | RRK01 | Access Roads | Rail,Rietkuil,Access Roads
R | Rail | RK | Rietkuil | RRK02 | Dams | Rail,Rietkuil,Dams
R | Rail | RK | Rietkuil | RRK03 | Earthworks | Rail,Rietkuil,Earthworks
R | Rail | RK | Rietkuil | RRK04 | Electrical | Rail,Rietkuil,Electrical
R | Rail | RK | Rietkuil | RRK05 | Fencing | Rail,Rietkuil,Fencing
R | Rail | RK | Rietkuil | RRK06 | Fuel Management | Rail,Rietkuil,Fuel Management
R | Rail | RK | Rietkuil | RRK07 | Internal Roads | Rail,Rietkuil,Internal Roads
R | Rail | RK | Rietkuil | RRK08 | Internal Walkways | Rail,Rietkuil,Internal Walkways
R | Rail | RK | Rietkuil | RRK09 | Overhead Transmission Equipment | Rail,Rietkuil,Overhead Transmission Equipment
R | Rail | RK | Rietkuil | RRK10 | PERWAY | Rail,Rietkuil,PERWAY
R | Rail | RK | Rietkuil | RRK11 | Potable Water | Rail,Rietkuil,Potable Water
R | Rail | RK | Rietkuil | RRK12 | Security Offices | Rail,Rietkuil,Security Offices
R | Rail | RK | Rietkuil | RRK13 | Sewerage | Rail,Rietkuil,Sewerage
R | Rail | RK | Rietkuil | RRK14 | Signalling | Rail,Rietkuil,Signalling
R | Rail | RK | Rietkuil | RRK15 | Site Office | Rail,Rietkuil,Site Office
R | Rail | RK | Rietkuil | RRK16 | Stormwater | Rail,Rietkuil,Stormwater
R | Rail | RK | Rietkuil | RRK17 | Rail Weighbridge Buildings | Rail,Rietkuil,Rail Weighbridge Buildings
R | Rail | RK | Rietkuil | RRK18 | Rail Weighbridge Equipment | Rail,Rietkuil,Rail Weighbridge Equipment
T | Resettlements | RS | Resettlements | TRS00 | XX-Overall | Resettlements,Resettlements,XX-Overall
T | Resettlements | RS | Resettlements | TRS01 | Civil Infrastructure | Resettlements,Resettlements,Civil Infrastructure
T | Resettlements | RS | Resettlements | TRS02 | Resettlement Action Plan Finalisation | Resettlements,Resettlements,Resettlement Action Plan Finalisation
T | Resettlements | RS | Resettlements | TRS03 | Grave Relocations | Resettlements,Resettlements,Grave Relocations
T | Resettlements | RS | Resettlements | TRS04 | RAP Monitoring & Management | Resettlements,Resettlements,RAP Monitoring & Management
T | Resettlements | RS | Resettlements | TRS05 | Top Structures | Resettlements,Resettlements,Top Structures
T | Resettlements | RS | Resettlements | TRS06 | Resettlements Electrical Installation | Resettlements,Resettlements,Resettlements Electrical Installation
T | Resettlements | RS | Resettlements | TRS07 | Other Resettlement Costs | Resettlements,Resettlements,Other Resettlement Costs
X | Risk | CT | Contingency | XCT01 | Contingency | Risk,Contingency,Contingency
X | Risk | ES | Escalation | XES01 | Escalation | Risk,Escalation,Escalation
X | Risk | MR | Management Reserve | XMR01 | Potential Savings | Risk,Management Reserve,Potential Savings

## Sheet1
Ramp and Platform
Crushing and Screening Plant
Reservoir and Pump House
Plant Workshop & Supply Chain (SCM)
Export & Middlings Stockpile
Main 22kV Substation
3600T Stockpile
Helipad
Laboratory
Main Security, Inductions & Changehouse
Middlings Road Island
Waste Water Treatment
Main Office Block
Truck Entrance Ablution
Truck Entrance Security
Primary Crusher
Primary Crusher Substation
Discard Mobile Equipment Parking
Shovel Parking
Mobile Equipment Yard
Diesel Depot
150T Discard Stockpile
Changehouse / Management Office & Mining Office
Explosives Magazine
Mine Access Security
Dust Suppression & WWTP