## Final
Belfast Implementation Project | [6 empty] | (
Outstanding information that may have potential impact on the contractual programme
2017-12-12
Activity | Start Date | Design/Contractual | [5 empty] | Scope of works | Comment
|  | Approved Drawings Issued (Yes/No) | Outstanding Information | Date when information was requested | Long Lead Items (Yes/No) assuming the information is received on the 13/12/2017 | Expected Delivery Date | Impact on the programme (Actual Start Date)
Parking Bays
Shade Ports | 2018-01-16 | No | Approved drawing not issued NBC-ARP-IF-0066 | Requested for information on 22/11/2017, Refer: ARP-RRQFI-000004; CON-RFI-000008 | No | N/A | 2018-02-12 | Supply and Installation of Shade Ports
Portable Water
Installation of borehole pump | 2017-12-06 | No | Arup to finalise design | Refer to Email correspondence with Millenium pumps regarding VSD for the borehole pump dated on 12/12/2018 | Yes, the pump | 3 weeks for pumps, 2 weeks for Medicals and inductions | 2018-01-26 | Installation only. Concor will supply pump from Grundfos | 3 week impact on programme
Installation of reservoirs | 2017-12-12 | No |  |  | No |  | 2018-01-15 | Installation only. Concor will supply storage tanks from Rototanks
Pipe work between borehole and reservoirs | 2018-01-16 | No |  |  | No | 2 weeks for material | 2018-02-23 | Supply and installation of pipework
Installation of water chlorination system and booster pump | 2018-02-05 | No |  |  | Yes | 3 weeks for procurment, 2 weeks for medicals and inductions | 2018-02-21 | Supply and installation of the potable water system and pump fittings | 2 week impact on programme
Construction Power
Generator Standby Power Supply | 2017-11-29 | No | Awaiting approval of revised spec from 250kv to 150kv | Email correspondence with JB Switchgear, Concor, Exxaro regarding specifications for the generator dated on the 08/12/2017 | Yes | 2 weeks | 2018-01-19 | Supply only | 2 week impact on the programme assuming that riggers will not be expected to do medicals
Enabling works electrical power supply | 2018-01-16 | No |  |  | Yes |  |  | Supply and installation of electrical works
Retaining Wall
Retaining Wall | 2017-11-10 | No | Arup to finalise design | Design clarification with Exxaro on the 20/10/2017 | Yes | 2018-02-16 | 2018-02-16 | Supervision for the retaining wall | 6 week impact on the programme. Key vendor Maccaferri
CONSTRUCTION FENCING
SECURITY FENCING
Clearing the fence line |  | Yes | Approved drawing not issued NBC-ARP-IF-0071 | Drawing requested on the 27/11/2017 , refer: EXX-MEMO-000670, EXX-MEMO-000652 | Yes, 30 days | 2018-02-19 | 2018-02-12 | Supply and Installtion of construction fencing | Estimated 30 days on the lead time for the galvinsed steel components
Clearing the fence line (2m wide strip) | 2018-01-16
Supply and erect new fencing material for new fences
b) Smooth wire: 2mm diam. galvanised wire | 2018-01-17
d) Welded Mesh (1.8m high x 2.5mm dia weld Diamond Mesh with 64 vert. x 64 hor. openings) | 2018-01-17
g) Droppers (0.56kg/m Ridgeback Pattern) | 2018-01-17
g) Standards (2450mm x 2.5kg/m "Y" section - Bituminous treated) | 2018-01-17
Straining/Corner/Gate posts, stays and anchors
i) Vertical
Steel posts fully galvanised steel tubing with steel cap 101.6mm diam. x 2.95mm x 2450mm complete as per Engineers specifications | 2018-01-17
ii) Inclined
Steel stays anchor fully galvanised steel tubing with 60.33mm diam. x 2,95mm x 2450mm complete as per Engineers specifications | 2018-01-17
New gates
Pedestrian Gate with locking device complete as per Engineers specification | 2018-01-17
3m single leaf gate with locking device complete as per Engineers specification | 2018-01-17
8m double leaf gate with locking device complete as per Engineers specification | 2018-01-17
STOCK PROOF FENCING
Clearing the fence line
Clearing the fence line (2m wide strip) | 2018-01-25
Supply and erect new fencing material for new fences
b) Barbed wire | 2018-02-01
g) Droppers (0.56kg/m Ridgeback Pattern) | 2018-02-01
g) Standards (1850mm x 2.5kg/m "Y" section - Bituminous treated) | 2018-02-01
Straining/Corner/Gate posts, stays and anchors
i) Vertical
Steel posts fully galvanised steel tubing with steel cap 101.6mm diam. x 2.95mm x 2100mm complete as per Engineers specifications | 2018-02-01
ii) Inclined
Steel stays anchor fully galvanised steel tubing with 60.33mm diam. x 2,95mm x 2100mm complete as per Engineers specifications | 2018-02-01
New gates
6m double leaf gate complete as per Engineers specification | 2018-02-01
8m double leaf gate complete as per Engineers specification | 2018-02-01
WALKWAY FENCING
Supply and erect new fencing material for new fences
b) Smooth wire: 4mm diam. galvanised wire | 2018-05-09
g) Standards (1500mm x 2.5kg/m "Y" section - Bituminous treated) | 2018-05-09